## Cost_Sch1
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun
Lingshui Semi | SEA CH | H | NOC | Own | 1 | 10439 | EPC | 700 | 3.1 | NEW | 67166.6667 | S | L | SEMI | 980 | L | 0.14888 | M | 0.76 | Not Availible
Bohai Ming Zhu | SEA CH | H | NOC | Own | 1 | 4350 | EPC | 259 | 0.4 | NEW | 40000 | VS | L | FPSO | 30 | N | 1 | N | 0.47104 | 0.25
Petrojarl Varg | NE | N | OC | Lease | 1 | 2240 | EPC | 816 | 0.46 | NEW | 65833.3333 | S | L | FPSO | 84 | N | 0.86582 | L | 0.28676 | 0.24
Stybarrow Venture MV16 | AUST/NZ | A | IOC | Lease | 3 | 5922 | EPC | 702 | 0.59843 | NEW | 87500 | S | A | FPSO | 825 | L | 0.91429 | M | -0.14387 | 0.27
Alima FPU | AFRICA | L | IOC | Own | 1 | 5720 | EPC | 994 | 1.133 | NEW | 100000 | M | N | BARGE | 600 | A | 0.9 | M | -0.022133 | 0.35
Jangkrik | SEA | M | OC | Own | 1 | 8824 | EPC | 1052 | 2.6765 | NEW | 79400 | S | L | BARGE | 120 | L | 0.055416 | A | 0.11407 | 0.17
Prelude | AUST/NZ | A | IOC | Own | 1 | 7814 | EPC | 2229 | 11.16 | NEW | 148333.3333 | UL | H | FLNG | 250 | N | 0.23596 | H | 0.24316 | 0.34409
CLOV FPSO | AFRICA | A | IOC | Own | 1 | 7534 | EPC | 1383 | 1.8 | NEW | 198333.3333 | L | L | FPSO | 1290 | M | 0.80672 | H | 0.0079537 | 0.055556
Dalia | AFRICA | M | IOC | Own | 1 | 4872 | EPC | 1306 | 3.4 | NEW | 287000 | UL | A | FPSO | 1360 | H | 0.83624 | L | 0.01072 | 0.17647
Girassol | AFRICA | M | IOC | Own | 1 | 3103 | EPC | 823 | 2.5 | NEW | 246666.6667 | VL | A | FPSO | 1350 | N | 0.81081 | N | 0.52126 | 0.12
Kaombo Norte | AFRICA | H | IOC | Own | 1 | 8871 | EPC | 1081 | 1.5 | CONV | 131666.6667 | M | L | FPSO | 1600 | L | 0.87342 | A | 0.44773 | Not Availible
Kaombo Sul | AFRICA | H | IOC | Own | 1 | 8871 | EPC | 1173 | 1.5 | CONV | 131666.6667 | M | L | FPSO | 1600 | L | 0.87342 | A | 0.54646 | Not Availible
Kizomba B | AFRICA | A | IOC | Own | 1 | 4756 | EPC | 1071 | 0.76 | NEW | 316666.6667 | UL | N | FPSO | 1250 | H | 0.78947 | L | -0.14006 | 0.13333
Mondo | AFRICA | M | IOC | Lease | 1 | 5866 | EPC | 797 | 0.75 | CONV | 115833.3333 | M | N | FPSO | 728 | A | 0.86331 | A | -0.10163 | 0
Saxi-Batuque | AFRICA | M | IOC | Lease | 3 | 5866 | EPC | 797 | 0.75 | CONV | 130000 | M | N | FPSO | 720 | A | 0.80769 | A | -0.084065 | 0
Greater Plutonio | AFRICA | A | IOC | Own | 1 | 5144 | EPC | 1124 | 1.73 | NEW | 305000 | UL | A | FPSO | 1350 | L | 0.81967 | H | 0.19039 | 0.85
PSVM FPSO | AFRICA | H | IOC | Own | 1 | 6755 | EPC | 1249 | 10 | CONV | 197833.3333 | L | H | FPSO | 2000 | L | 0.7936 | N | 0.29704 | 0.4
Sanha LPG | AFRICA | N | IOC | Own | 1 | 4687 | EPC | 821 | 1.9 | NEW | 37405.31 | L | A | FPSO | 58 | N | 0.99906 | A | 0.036541 | Not Availible
Baobab Ivoirien MV10 | AFRICA | N | OC | Lease | 3 | 4949 | EPC | 711 | 1.5 | CONV | 82500 | S | N | FPSO | 970 | A | 0.84848 | L | 0.067511 | 0
Prof. John Evans Atta Mills | AFRICA | M | IOC | Lease | 3 | 8617 | EPC | 1092 | 5 | CONV | 108333.3333 | M | N | FPSO | 1425 | L | 0.73846 | H | 0.015568 | 0
Agbami | AFRICA | L | IOC | Own | 2 | 5539 | EPC | 1126 | 4.1538 | NEW | 325000 | UL | L | FPSO | 1433 | L | 0.76923 | L | 0.11368 | 0.3
Akpo | AFRICA | M | IOC | Own | 1 | 5606 | TK | 1303 | 2.345 | NEW | 273333.3333 | UL | L | FPSO | 1325 | N | 0.67683 | A | 0.072141 | 1.55
Bonga | AFRICA | M | IOC | Own | 1 | 4049 | EPC | 1033 | 2.4 | NEW | 253333.3333 | UL | A | FPSO | 1250 | N | 0.88816 | A | 0.70765 | 0.5
Egina FPSO | AFRICA | H | IOC | Own | 1 | 8540 | EPC | 1595 | 16 | NEW | 260000 | UL | L | FPSO | 1600 | A | 0.76923 | L | 0.28715 | -0.09375
Erha | AFRICA | M | IOC | Own | 1 | 4671 | EPC | 1081 | 2.6 | NEW | 266666.6667 | UL | L | FPSO | 1180 | L | 0.7875 | L | 0.19334 | 0.57
Kizomba A | AFRICA | A | IOC | Own | 1 | 4253 | EPC | 1073 | 0.77 | NEW | 316666.6667 | UL | L | FPSO | 1250 | A | 0.78947 | L | 0.0055918 | 0.13333
Ichthys Venturer | AUST/NZ | M | IOC | Own | 1 | 8102 | EPC | 1743 | 2 | NEW | 85000 | S | H | FPSO | 250 | L | 1 | H | 0.37636 | 0.32353
Pyrenees Venture | AUST/NZ | A | IOC | Own | 2 | 6379 | EPC | 1014 | 1.66 | CONV | 106000 | M | M | FPSO | 200 | M | 0.90566 | H | 0.0019724 | 0.012028
Ngujima Yin | AUST/NZ | A | IOC | Own | 1 | 5993 | EPC | 716 | 0.72 | CONV | 136666.6667 | M | L | FPSO | 340 | L | 0.87805 | M | 0.14665 | 0.33333
P 50 | BRAZ | M | NOC | Own | 1 | 4557 | CL | 844 | 0.496 | CONV | 215000 | VL | N | FPSO | 1240 | M | 0.83721 | N | 0.66351 | 0.41129
P 43 | BRAZ | H | NOC | Own | 1 | 4199 | TK | 883 | 1.3 | CONV | 185000 | L | N | FPSO | 800 | M | 0.81081 | N | 0.43828 | 0.38462
P 74 | BRAZ | H | NOC | Own | 1 | 8110 | CL | 1630 | 1.1658 | CONV | 191166.6667 | L | N | FPSO | 2190 | M | 0.78466 | N | 0.36748 | Not Availible
P 75 | BRAZ | H | NOC | Own | 1 | 8110 | CL | 1721 | 1.22 | CONV | 191166.6667 | L | N | FPSO | 1875 | M | 0.78466 | N | 0.52992 | Not Availible
P 76 | BRAZ | H | NOC | Own | 1 | 8110 | CL | 1995 | 1.3242 | CONV | 191166.6667 | L | N | FPSO | 2030 | M | 0.78466 | N | 0.36491 | Not Availible
P 77 | BRAZ | H | NOC | Own | 1 | 8110 | CL | 2086 | 1.22 | CONV | 191166.6667 | L | N | FPSO | 1875 | M | 0.78466 | N | 0.30537 | Not Availible
P 48 | BRAZ | H | NOC | Own | 1 | 4199 | TK | 1066 | 1.3 | CONV | 185000 | L | N | FPSO | 1040 | L | 0.81081 | N | 0.25516 | 0.38462
Frade | BRAZ | A | IOC | Own | 1 | 6014 | EPC | 909 | 2 | CONV | 117666.6667 | M | L | FPSO | 1080 | N | 0.84986 | H | 0.20902 | 1.35
P 68 | BRAZ | H | NOC | Own | 1 | 7486 | CL | 2557 | 1.4 | NEW | 187000 | L | N | FPSO | 2165 | M | 0.80214 | N | 0.33907 | Not Availible
P 70 | BRAZ | H | NOC | Own | 1 | 7486 | EPC | 2557 | 1.4 | NEW | 185333.3333 | L | N | FPSO | 2240 | M | 0.80935 | N | 0.42785 | Not Availible
Cidade de Mangaratiba MV24 | BRAZ | A | NOC | Lease | 3 | 7971 | EPC | 1021 | 1.1 | CONV | 197166.6667 | L | N | FPSO | 2200 | A | 0.76078 | N | 0.059745 | Not Availible
P 57 | BRAZ | H | NOC | Lease | 2 | 6622 | EPC | 1041 | 1.195 | CONV | 191833.3333 | L | N | FPSO | 1300 | M | 0.93831 | N | -0.045149 | 0.0041841
Pioneiro de Libra | BRAZ | H | NOC | Lease | 3 | 8984 | PS | 831 | 1 | CONV | 73333.3333 | S | N | FPSO | 2200 | H | 0.68182 | N | 0.45728 | 0.59441
Cidade de Marica | BRAZ | H | NOC | Lease | 3 | 8481 | EPC | 1075 | 1.75 | CONV | 185000 | L | N | FPSO | 2120 | H | 0.81081 | L | -0.042791 | Not Availible
Cidade de Saquarema | BRAZ | H | NOC | Lease | 3 | 8460 | EPC | 1127 | 1.75 | CONV | 185000 | L | N | FPSO | 2200 | H | 0.81081 | L | -0.015084 | Not Availible
P 69 | BRAZ | M | NOC | Own | 1 | 7486 | CL | 2557 | 1.4 | NEW | 185333.3333 | L | N | FPSO | 2165 | M | 0.80935 | N | 0.18772 | Not Availible
P 67 | BRAZ | M | NOC | Own | 1 | 7486 | CL | 2084 | 1.4 | NEW | 179500 | L | N | FPSO | 2165 | M | 0.83565 | N | 0.50432 | Not Availible
P 66 | BRAZ | H | NOC | Own | 1 | 7486 | CL | 2024 | 1.4 | NEW | 191166.6667 | L | A | FPSO | 2165 | M | 0.78466 | N | 0.2332 | Not Availible
P 53 | BRAZ | M | NOC | Own | 2 | 5826 | EPC | 779 | 0.758 | CONV | 215000 | VL | L | FPSO | 1080 | L | 0.83721 | L | 0.38896 | Not Availible
P 63 | BRAZ | H | NOC | Own | 1 | 7213 | EPC | 1383 | 1.3 | CONV | 145833.3333 | M | N | FPSO | 1170 | L | 0.96 | L | 0.086768 | 0.25385
P 58 | BRAZ | H | NOC | Own | 1 | 7268 | EPC | 1481 | 1.03 | CONV | 215333.3333 | VL | N | FPSO | 1400 | M | 0.83591 | N | 0.39095 | Not Availible
Espirito Santo | BRAZ | H | IOC | Lease | 3 | 6153 | EPC | 787 | 1.5086 | CONV | 105000 | M | H | FPSO | 1780 | N | 0.95238 | A | 0.24778 | 1.32
P 54 | BRAZ | H | NOC | Own | 1 | 5272 | EPC | 1034 | 0.629 | CONV | 215000 | VL | L | FPSO | 1315 | H | 0.83721 | N | 0.24468 | 0.97138
P 62 | BRAZ | H | NOC | Own | 1 | 7336 | CL | 1413 | 1.01 | CONV | 215333.3333 | VL | N | FPSO | 1600 | M | 0.83591 | N | 0.22647 | Not Availible
Cidade de Ilhabela | BRAZ | M | NOC | Lease | 3 | 7851 | EPC | 1172 | 1.5 | CONV | 185333.3333 | L | N | FPSO | 2100 | L | 0.80935 | L | 0.052048 | Not Availible
Cidade de Campos dos Goytacazes MV29 | BRAZ | M | NOC | Lease | 3 | 9101 | EPC | 1018 | 1.263 | CONV | 179500 | L | L | FPSO | 765 | M | 0.83565 | N | 0.27898 | 0.0055424
Terra Nova | CAN | L | OC | Own | 1 | 2800 | EPC | 1157 | 1.3 | NEW | 175000 | L | H | FPSO | 90 | N | 0.85714 | L | 0.39412 | 0.30769
Sea Rose | CAN | A | OC | Own | 1 | 4476 | EPC | 1229 | 0.49 | NEW | 125000 | M | H | FPSO | 120 | N | 0.8 | M | 0.072417 | 0.2
Turritella | GOM | N | OC | Own | 1 | 8528 | EPC | 1149 | 1 | Conv | 62500 | S | M | FPSO | 2900 | L | 0.96 | H | 0.11227 | 0.311
Asgard A | NE | A | OC | Own | 1 | 2356 | TK | 870 | 5.2941 | NEW | 300000 | UL | M | FPSO | 300 | N | 0.66667 | A | 0.20805 | 0.36
Balder | NE | A | IOC | Own | 1 | 1826 | TK | 592 | 0.35 | NEW | 90500 | S | H | FPSO | 125 | N | 0.91713 | N | 1.9291 | 0.62
Goliat FPSO | NE | L | OC | Own | 1 | 7218 | EPC | 1364 | 3.9 | NEW | 122500 | M | H | FPSO | 400 | N | 0.81633 | M | 0.72361 | 0.52
Petrojarl Knarr | NE | L | OC | Lease | 3 | 7850 | EPC | 732 | 1.6119 | NEW | 70833.3333 | S | L | FPSO | 410 | L | 0.88941 | M | 0.85656 | 0.36975
Norne | NE | L | OC | Own | 1 | 1551 | EPC | 1334 | 4.7 | NEW | 261666.6667 | UL | M | FPSO | 380 | A | 0.84076 | M | -0.12519 | 0.6
Skarv | NE | L | IOC | Own | 1 | 6240 | EPC | 1245 | 5 | NEW | 167500 | L | M | FPSO | 370 | N | 0.47761 | M | 0.73494 | 0.7
Glen Lyon | NE | A | IOC | Own | 1 | 7729 | EPC | 1949 | 4.78 | NEW | 166666.6667 | L | L | FPSO | 424 | N | 0.78 | M | 0.16675 | 0.19247
Western Isles FPSO | NE | N | OC | Own | 1 | 8391 | EPC | 952 | 1.6 | NEW | 40000 | VS | A | FPSO | 165 | L | 1 | A | 0.8792 | 0.25
Belanak Natuna | SEA | M | IOC | Own | 1 | 4250 | TK | 1137 | 1.6 | NEW | 158333.3333 | L | M | FPSO | 100 | L | 0.63158 | M | 0.058927 | 0.078167
Kikeh FPSO | SEA | H | OC | Lease | 3 | 5513 | EPC | 939 | 0.8 | CONV | 143500 | M | L | FPSO | 1350 | N | 0.83624 | M | -0.015974 | 0.2
Song Doc Pride MV 19 | SEA | N | NOC | Lease | 1 | 6339 | EPC | 417 | 0.25 | CONV | 30000 | VS | N | FPSO | 55 | L | 1 | N | 0.35012 | 0.04087
Thai Binh Vn | SEA | N | NOC | Own | 1 | 4446 | EPC | 611 | 0.714 | NEW | 68333.3333 | S | N | FPSO | 48 | L | 0.95122 | A | 0.037643 | 0.044
Hai Yang Shi You 117 | SEA CH | M | NOC | Own | 1 | 5524 | EPC | 897 | 1.8 | NEW | 190000 | L | N | FPSO | 27 | N | 1 | A | 0.72798 | 0.38889
Hai Yang Shi You 116 | SEA CH | N | NOC | Own | 1 | 5804 | EPC | 723 | 1.2 | NEW | 106000 | M | N | FPSO | 125 | N | 1 | N | 0.3195 | 0.98
Unity | AFRICA | M | IOC | Own | 1 | 4018 | EPC | 545 | 1 | NEW | 125000 | M | L | FSO | 65 | A | 1 | L | 0.70092 | 0.4
Yoho EPS | AFRICA | A | IOC | Own | 1 | 4196 | EPC | 505 | 1.2 | CONV | 90000 | S | L | FSO | 56 | N | 1 | N | 0.20792 | 0.083333
Yoho | AFRICA | A | IOC | Own | 1 | 4623 | EPC | 761 | 1.2 | CONV | 116666.6667 | M | L | FSO | 56 | A | 0.85714 | L | 0.6636 | 0.083333
Hanne Knutsen | NE | L | IOC | Lease | 3 | 8124 | EPC | 1691 | 2.8649 | CONV | 100000 | M | L | FSO | 115 | N | 1 | L | 0.80958 | 0.85
Ailsa FSO | NE | L | IOC | Own | 1 | 9389 | EPC | 1364 | 4.7 | NEW | 108333.3333 | M | L | FSO | 90 | H | 0.23077 | H | 0 | 0
Gagak Rimang | SEA | H | IOC | Own | 1 | 7891 | EPC | 1110 | 1.2 | CONV | 165000 | L | L | FSO | 33 | N | 1 | A | 0.42973 | 1.1667
Rang Dong MV17 | SEA | N | NOC | Lease | 3 | 6038 | EPC | 763 | 0.5 | NEW | 60000 | S | N | FSO | 60 | L | 1 | N | 0.10747 | 0.04087
Ichthys Explorer | AUST/NZ | M | OC | Own | 1 | 8046 | EPC | 1810 | 3 | NEW | 361166.6667 | UL | M | SEMI | 250 | L | 0.23535 | H | 0.35635 | 0.32353
P 51 | BRAZ | H | NOC | Own | 1 | 5201 | EPC | 1418 | 0.83 | NEW | 215000 | VL | L | SEMI | 1250 | H | 0.83721 | N | 0.24401 | 0.25
P 56 | BRAZ | H | NOC | Own | 1 | 6478 | EPC | 1114 | 1.4 | NEW | 135000 | M | N | SEMI | 1670 | H | 0.74074 | N | 0.27379 | 0.071429
P 52 | BRAZ | H | NOC | Lease | 3 | 5060 | EPC | 1237 | 0.906 | NEW | 235000 | VL | L | SEMI | 1850 | A | 0.76596 | N | 0.19644 | 0.43488
P 55 | BRAZ | H | NOC | Own | 1 | 6517 | EPC | 1518 | 1.65 | NEW | 215333.3333 | VL | L | SEMI | 1790 | A | 0.83591 | N | 0.49144 | Not Availible
Atlantis | GOM | L | IOC | Own | 1 | 4533 | EPC | 1492 | 2.5 | NEW | 230000 | VL | L | SEMI | 2145 | M | 0.86957 | N | 0.60389 | 1.35
Delta House (Opti-Ex II) | GOM | N | OC | Own | 1 | 8158 | EPC | 1093 | 2 | NEW | 140000 | M | L | SEMI | 1372 | H | 0.71429 | L | -0.012809 | 0
Blind Faith | GOM | N | IOC | Own | 1 | 5802 | EPC | 846 | 1.151 | NEW | 52500 | S | L | SEMI | 2130 | N | 0.85714 | H | 0.28605 | 0.95
Thunder Hawk | GOM | N | OC | Lease | 3 | 6086 | EPC | 958 | 0.8 | NEW | 56666.6667 | S | N | SEMI | 1847 | M | 0.79412 | H | 0.087683 | 0
Thunder Horse | GOM | L | IOC | Own | 1 | 4624 | EPC | 1098 | 5 | NEW | 283333.3333 | UL | H | SEMI | 1830 | N | 0.88235 | H | 0.92623 | 2.68
Jack / St. Malo Semi | GOM | N | IOC | Own | 1 | 7270 | EPC | 1844 | 7.5 | NEW | 177166.6667 | L | N | SEMI | 2134 | M | 0.95955 | H | -0.005423 | 0
Asgard B | NE | M | OC | Own | 1 | 2356 | TK | 1570 | 1.3 | New | 351666.6667 | UL | N | SEMI | 300 | H | 0.38389 | M | 0 | 0
Gjoa | NE | L | OC | Own | 1 | 6025 | CL | 1461 | 4.4361 | NEW | 108333.3333 | M | M | SEMI | 380 | N | 0.46154 | M | 0.08898 | 0.33
Kristin | NE | M | OC | Own | 1 | 4368 | EPC | 1384 | 1.9 | New | 128000 | M | H | SEMI | 370 | N | 0.97656 | L | 0.023844 | 0.73684
Snorre B | NE | M | OC | Own | 1 | 3256 | EPC | 943 | 1.2821 | NEW | 115000 | M | N | SEMI | 310 | M | 1 | L | -0.064687 | 0.17
Troll C | NE | A | OC | Own | 1 | 2647 | EPC | 821 | 4.5 | NEW | 243333.3333 | VL | H | SEMI | 340 | M | 0.78082 | A | 0.18636 | Not Availible
Troll B | NE | A | OC | Own | 1 | 379 | EPC | 1263 | 2.9 | NEW | 317000 | UL | H | SEMI | 320 | L | 0.85174 | A | 0.35234 | 0.14
Visund | NE | H | OC | Own | 1 | 2251 | TK | 851 | 0.7 | NEW | 171333.3333 | L | H | SEMI | 335 | N | 0.65953 | L | 0.3396 | 0.45
Gumusut Semi | SEA | H | IOC | Lease | 3 | 6588 | EPC | 1233 | 1.6 | NEW | 200000 | VL | L | SEMI | 1220 | A | 0.75 | A | 0.99919 | 0.25
Perdido Spar | GOM | L | IOC | Own | 1 | 6025 | EPC | 974 | 3 | NEW | 133333.3333 | M | H | SPAR | 2440 | N | 0.75 | A | 0.40554 | Not Availible
Front Runner Spar | GOM | L | OC | Own | 1 | 4459 | TK | 728 | 0.2 | NEW | 78333.3333 | S | A | SPAR | 1015 | N | 0.76596 | N | 0.36676 | 0.075
Tahiti Spar | GOM | L | IOC | Own | 1 | 5597 | EPC | 1159 | 3.5 | NEW | 136666.6667 | M | A | SPAR | 1280 | L | 0.91463 | L | 0.26747 | 1.8
Holstein | GOM | N | IOC | Own | 1 | 4070 | EPC | 859 | 1 | NEW | 135000 | M | M | SPAR | 1345 | L | 0.81481 | A | 0.6135 | Not Availible
Mad Dog | GOM | N | IOC | Own | 1 | 4070 | EPC | 1397 | 1.82 | NEW | 66666.6667 | S | L | SPAR | 1370 | N | 0.9 | M | 0.022906 | 0.1
Heidelberg Spar | GOM | N | OC | Own | 1 | 8018 | EPC | 1649 | 6.745 | NEW | 93333.3333 | S | M | SPAR | 1620 | H | 0.85714 | H | -0.095816 | 0.0081542
Lucius Spar | GOM | N | OC | Own | 1 | 8002 | EPC | 1007 | 7.736 | NEW | 155000 | L | M | SPAR | 2165 | M | 0.51613 | H | 0.14002 | 0.008273
Medusa Spar | GOM | L | OC | Own | 1 | 4077 | TK | 579 | 0.2 | NEW | 58333.3333 | S | A | SPAR | 675 | N | 0.68571 | N | 0.74266 | 0.365
Gulfstar 1 | GOM | N | IOC | Lease | 3 | 7813 | EPC | 1132 | 2.3 | NEW | 109166.6667 | M | L | SPAR | 1310 | L | 0.73282 | A | 0.12191 | 0.30435
Devil's Tower Spar | GOM | A | OC | Lease | 3 | 4189 | TK | 739 | 0.2 | NEW | 66666.6667 | S | L | SPAR | 1710 | L | 0.9 | N | 0.41949 | 0.06
Kikeh Spar | SEA | H | OC | Own | 1 | 5513 | EPC | 939 | 0.5 | NEW | 142500 | M | M | SPAR | 1330 | N | 0.84 | M | -0.015974 | 0.28571
Kizomba A Wellhead TLP | AFRICA | M | IOC | Own | 1 | 4253 | EPC | 1073 | 0.65 | NEW | 250000 | UL | N | TLP | 1175 | A | 1 | L | 0.0055918 | 0.13333
Kizomba B Wellhead TLP | AFRICA | A | IOC | Own | 1 | 4756 | EPC | 1071 | 0.6 | NEW | 250000 | UL | N | TLP | 1250 | H | 1 | L | -0.14006 | 0.13333
Okume TLP | AFRICA | L | OC | Own | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | VS | N | TLP | 500 | M | 0.83333 | M | 0.04 | 0
Oveng TLP | AFRICA | L | OC | Own | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | VS | N | TLP | 280 | M | 0.83333 | M | 0.04 | 0
P 61 Wellhead TLP | BRAZ | H | NOC | Own | 1 | 7213 | EPC | 1475 | 1.07 | NEW | 145833.3333 | M | A | TLP | 1180 | N | 0.96 | L | 0.35051 | 0
Auger TLP | GOM | L | IOC | Own | 1 | 287 | EPC | 1233 | 0.86364 | NEW | 65000 | S | M | TLP | 870 | L | 0.61538 | M | 0.044607 | 0.38947
Magnolia TLP | GOM | N | IOC | Own | 1 | 4392 | EPC | 1040 | 0.6 | NEW | 75000 | S | M | TLP | 1432 | L | 0.66667 | H | 0.038462 | 0
Brutus TLP | GOM | N | IOC | Own | 1 | 3570 | EPC | 674 | 0.76 | NEW | 155000 | L | L | TLP | 910 | M | 0.83871 | M | 0.038576 | 0.078947
Stampede TLP | GOM | N | OC | Own | 1 | 8523 | EPC | 1982 | 6.2 | NEW | 86666.6667 | S | N | TLP | 1160 | M | 0.92308 | H | -0.1221 | -0.12903
Neptune TLP | GOM | L | OC | Own | 1 | 5670 | EPC | 887 | 0.85 | NEW | 58333.3333 | S | L | TLP | 1300 | L | 0.85714 | M | 0.2345 | 0.47882
Shenzi TLP | GOM | L | OC | Own | 1 | 6001 | EPC | 1119 | 4.41 | NEW | 116666.6667 | M | L | TLP | 1333 | L | 0.85714 | H | -0.088472 | 0
Mars TLP | GOM | N | IOC | Own | 1 | 1381 | EPC | 1098 | 1.2 | NEW | 230833.3333 | VL | L | TLP | 896 | M | 0.86643 | M | -0.090164 | -0.054167
Olympus TLP | GOM | N | IOC | Own | 1 | 7729 | EPC | 1202 | 3 | NEW | 116666.6667 | M | L | TLP | 945 | H | 0.85714 | H | -0.12562 | 0
Ursa TLP | GOM | N | IOC | Own | 1 | 2398 | EPC | 1040 | 1.45 | NEW | 216666.6667 | VL | A | TLP | 1160 | H | 0.69231 | M | -0.081731 | 0.043448
Ram Powell TLP | GOM | N | IOC | Own | 1 | 1885 | EPC | 915 | 1 | NEW | 93333.3333 | S | A | TLP | 990 | H | 0.64286 | M | 0.015301 | 0
Big Foot | GOM | M | IOC | Own | 1 | 7571 | EPC | 1529 | 4 | NEW | 79166.6667 | S | H | TLP | 1580 | N | 0.94737 | H | 0.94899 | 0.275
Heidrun TLP | NE | N | OC | Own | 1 | 504 | EPC | 1548 | 3.9 | NEW | 283333.3333 | UL | L | TLP | 350 | L | 0.88235 | H | 0.039406 | 0.076923
Malikai TLP | SEA | H | IOC | Own | 1 | 8439 | EPC | 1030 | 1.2825 | NEW | 68333.3333 | S | L | TLP | 470 | A | 0.87805 | H | 0.36796 | 0.077973

## Schedule
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun
Lingshui Semi | 8 | 5 | 3 | 2 | 1 | 10439 | 3 | 700 | 3.1 | 1 | 67166.6667 | 2 | 2 | 6 | 980 | 2 | 0.14888 | 4 | 0.76 | Not Availible
Bohai Ming Zhu | 8 | 5 | 3 | 2 | 1 | 4350 | 3 | 259 | 0.4 | 1 | 40000 | 1 | 2 | 5 | 30 | 1 | 1 | 1 | 0.47104 | 0.25
Petrojarl Varg | 7 | 1 | 1 | 1 | 1 | 2240 | 3 | 816 | 0.46 | 1 | 65833.3333 | 2 | 2 | 5 | 84 | 1 | 0.86582 | 2 | 0.28676 | 0.24
Stybarrow Venture MV16 | 4 | 3 | 2 | 1 | 3 | 5922 | 3 | 702 | 0.59843 | 1 | 87500 | 2 | 3 | 5 | 825 | 2 | 0.91429 | 4 | -0.14387 | 0.27
Alima FPU | 1 | 2 | 2 | 2 | 1 | 5720 | 3 | 994 | 1.133 | 1 | 100000 | 3 | 1 | 1 | 600 | 3 | 0.9 | 4 | -0.022133 | 0.35
Jangkrik | 2 | 4 | 1 | 2 | 1 | 8824 | 3 | 1052 | 2.6765 | 1 | 79400 | 2 | 2 | 1 | 120 | 2 | 0.055416 | 3 | 0.11407 | 0.17
Prelude | 4 | 3 | 2 | 2 | 1 | 7814 | 3 | 2229 | 11.16 | 1 | 148333.3333 | 6 | 5 | 4 | 250 | 1 | 0.23596 | 5 | 0.24316 | 0.34409
CLOV FPSO | 1 | 3 | 2 | 2 | 1 | 7534 | 3 | 1383 | 1.8 | 1 | 198333.3333 | 4 | 2 | 5 | 1290 | 4 | 0.80672 | 5 | 0.0079537 | 0.055556
Dalia | 1 | 4 | 2 | 2 | 1 | 4872 | 3 | 1306 | 3.4 | 1 | 287000 | 6 | 3 | 5 | 1360 | 5 | 0.83624 | 2 | 0.01072 | 0.17647
Girassol | 1 | 4 | 2 | 2 | 1 | 3103 | 3 | 823 | 2.5 | 1 | 246666.6667 | 5 | 3 | 5 | 1350 | 1 | 0.81081 | 1 | 0.52126 | 0.12
Kaombo Norte | 1 | 5 | 2 | 2 | 1 | 8871 | 3 | 1081 | 1.5 | 2 | 131666.6667 | 3 | 2 | 5 | 1600 | 2 | 0.87342 | 3 | 0.44773 | Not Availible
Kaombo Sul | 1 | 5 | 2 | 2 | 1 | 8871 | 3 | 1173 | 1.5 | 2 | 131666.6667 | 3 | 2 | 5 | 1600 | 2 | 0.87342 | 3 | 0.54646 | Not Availible
Kizomba B | 1 | 3 | 2 | 2 | 1 | 4756 | 3 | 1071 | 0.76 | 1 | 316666.6667 | 6 | 1 | 5 | 1250 | 5 | 0.78947 | 2 | -0.14006 | 0.13333
Mondo | 1 | 4 | 2 | 1 | 1 | 5866 | 3 | 797 | 0.75 | 2 | 115833.3333 | 3 | 1 | 5 | 728 | 3 | 0.86331 | 3 | -0.10163 | 0
Saxi-Batuque | 1 | 4 | 2 | 1 | 3 | 5866 | 3 | 797 | 0.75 | 2 | 130000 | 3 | 1 | 5 | 720 | 3 | 0.80769 | 3 | -0.084065 | 0
Greater Plutonio | 1 | 3 | 2 | 2 | 1 | 5144 | 3 | 1124 | 1.73 | 1 | 305000 | 6 | 3 | 5 | 1350 | 2 | 0.81967 | 5 | 0.19039 | 0.85
PSVM FPSO | 1 | 5 | 2 | 2 | 1 | 6755 | 3 | 1249 | 10 | 2 | 197833.3333 | 4 | 5 | 5 | 2000 | 2 | 0.7936 | 1 | 0.29704 | 0.4
Sanha LPG | 1 | 1 | 2 | 2 | 1 | 4687 | 3 | 821 | 1.9 | 1 | 37405.31 | 4 | 3 | 5 | 58 | 1 | 0.99906 | 3 | 0.036541 | Not Availible
Baobab Ivoirien MV10 | 1 | 1 | 1 | 1 | 3 | 4949 | 3 | 711 | 1.5 | 2 | 82500 | 2 | 1 | 5 | 970 | 3 | 0.84848 | 2 | 0.067511 | 0
Prof. John Evans Atta Mills | 1 | 4 | 2 | 1 | 3 | 8617 | 3 | 1092 | 5 | 2 | 108333.3333 | 3 | 1 | 5 | 1425 | 2 | 0.73846 | 5 | 0.015568 | 0
Agbami | 1 | 2 | 2 | 2 | 2 | 5539 | 3 | 1126 | 4.1538 | 1 | 325000 | 6 | 2 | 5 | 1433 | 2 | 0.76923 | 2 | 0.11368 | 0.3
Akpo | 1 | 4 | 2 | 2 | 1 | 5606 | 4 | 1303 | 2.345 | 1 | 273333.3333 | 6 | 2 | 5 | 1325 | 1 | 0.67683 | 3 | 0.072141 | 1.55
Bonga | 1 | 4 | 2 | 2 | 1 | 4049 | 3 | 1033 | 2.4 | 1 | 253333.3333 | 6 | 3 | 5 | 1250 | 1 | 0.88816 | 3 | 0.70765 | 0.5
Egina FPSO | 1 | 5 | 2 | 2 | 1 | 8540 | 3 | 1595 | 16 | 1 | 260000 | 6 | 2 | 5 | 1600 | 3 | 0.76923 | 2 | 0.28715 | -0.09375
Erha | 1 | 4 | 2 | 2 | 1 | 4671 | 3 | 1081 | 2.6 | 1 | 266666.6667 | 6 | 2 | 5 | 1180 | 2 | 0.7875 | 2 | 0.19334 | 0.57
Kizomba A | 1 | 3 | 2 | 2 | 1 | 4253 | 3 | 1073 | 0.77 | 1 | 316666.6667 | 6 | 2 | 5 | 1250 | 3 | 0.78947 | 2 | 0.0055918 | 0.13333
Ichthys Venturer | 4 | 4 | 2 | 2 | 1 | 8102 | 3 | 1743 | 2 | 1 | 85000 | 2 | 5 | 5 | 250 | 2 | 1 | 5 | 0.37636 | 0.32353
Pyrenees Venture | 4 | 3 | 2 | 2 | 2 | 6379 | 3 | 1014 | 1.66 | 2 | 106000 | 3 | 4 | 5 | 200 | 4 | 0.90566 | 5 | 0.0019724 | 0.012028
Ngujima Yin | 4 | 3 | 2 | 2 | 1 | 5993 | 3 | 716 | 0.72 | 2 | 136666.6667 | 3 | 2 | 5 | 340 | 2 | 0.87805 | 4 | 0.14665 | 0.33333
P 50 | 6 | 4 | 3 | 2 | 1 | 4557 | 2 | 844 | 0.496 | 2 | 215000 | 5 | 1 | 5 | 1240 | 4 | 0.83721 | 1 | 0.66351 | 0.41129
P 43 | 6 | 5 | 3 | 2 | 1 | 4199 | 4 | 883 | 1.3 | 2 | 185000 | 4 | 1 | 5 | 800 | 4 | 0.81081 | 1 | 0.43828 | 0.38462
P 74 | 6 | 5 | 3 | 2 | 1 | 8110 | 2 | 1630 | 1.1658 | 2 | 191166.6667 | 4 | 1 | 5 | 2190 | 4 | 0.78466 | 1 | 0.36748 | Not Availible
P 75 | 6 | 5 | 3 | 2 | 1 | 8110 | 2 | 1721 | 1.22 | 2 | 191166.6667 | 4 | 1 | 5 | 1875 | 4 | 0.78466 | 1 | 0.52992 | Not Availible
P 76 | 6 | 5 | 3 | 2 | 1 | 8110 | 2 | 1995 | 1.3242 | 2 | 191166.6667 | 4 | 1 | 5 | 2030 | 4 | 0.78466 | 1 | 0.36491 | Not Availible
P 77 | 6 | 5 | 3 | 2 | 1 | 8110 | 2 | 2086 | 1.22 | 2 | 191166.6667 | 4 | 1 | 5 | 1875 | 4 | 0.78466 | 1 | 0.30537 | Not Availible
P 48 | 6 | 5 | 3 | 2 | 1 | 4199 | 4 | 1066 | 1.3 | 2 | 185000 | 4 | 1 | 5 | 1040 | 2 | 0.81081 | 1 | 0.25516 | 0.38462
Frade | 6 | 3 | 2 | 2 | 1 | 6014 | 3 | 909 | 2 | 2 | 117666.6667 | 3 | 2 | 5 | 1080 | 1 | 0.84986 | 5 | 0.20902 | 1.35
P 68 | 6 | 5 | 3 | 2 | 1 | 7486 | 2 | 2557 | 1.4 | 1 | 187000 | 4 | 1 | 5 | 2165 | 4 | 0.80214 | 1 | 0.33907 | Not Availible
P 70 | 6 | 5 | 3 | 2 | 1 | 7486 | 3 | 2557 | 1.4 | 1 | 185333.3333 | 4 | 1 | 5 | 2240 | 4 | 0.80935 | 1 | 0.42785 | Not Availible
Cidade de Mangaratiba MV24 | 6 | 3 | 3 | 1 | 3 | 7971 | 3 | 1021 | 1.1 | 2 | 197166.6667 | 4 | 1 | 5 | 2200 | 3 | 0.76078 | 1 | 0.059745 | Not Availible
P 57 | 6 | 5 | 3 | 1 | 2 | 6622 | 3 | 1041 | 1.195 | 2 | 191833.3333 | 4 | 1 | 5 | 1300 | 4 | 0.93831 | 1 | -0.045149 | 0.0041841
Pioneiro de Libra | 6 | 5 | 3 | 1 | 3 | 8984 | 1 | 831 | 1 | 2 | 73333.3333 | 2 | 1 | 5 | 2200 | 5 | 0.68182 | 1 | 0.45728 | 0.59441
Cidade de Marica | 6 | 5 | 3 | 1 | 3 | 8481 | 3 | 1075 | 1.75 | 2 | 185000 | 4 | 1 | 5 | 2120 | 5 | 0.81081 | 2 | -0.042791 | Not Availible
Cidade de Saquarema | 6 | 5 | 3 | 1 | 3 | 8460 | 3 | 1127 | 1.75 | 2 | 185000 | 4 | 1 | 5 | 2200 | 5 | 0.81081 | 2 | -0.015084 | Not Availible
P 69 | 6 | 4 | 3 | 2 | 1 | 7486 | 2 | 2557 | 1.4 | 1 | 185333.3333 | 4 | 1 | 5 | 2165 | 4 | 0.80935 | 1 | 0.18772 | Not Availible
P 67 | 6 | 4 | 3 | 2 | 1 | 7486 | 2 | 2084 | 1.4 | 1 | 179500 | 4 | 1 | 5 | 2165 | 4 | 0.83565 | 1 | 0.50432 | Not Availible
P 66 | 6 | 5 | 3 | 2 | 1 | 7486 | 2 | 2024 | 1.4 | 1 | 191166.6667 | 4 | 3 | 5 | 2165 | 4 | 0.78466 | 1 | 0.2332 | Not Availible
P 53 | 6 | 4 | 3 | 2 | 2 | 5826 | 3 | 779 | 0.758 | 2 | 215000 | 5 | 2 | 5 | 1080 | 2 | 0.83721 | 2 | 0.38896 | Not Availible
P 63 | 6 | 5 | 3 | 2 | 1 | 7213 | 3 | 1383 | 1.3 | 2 | 145833.3333 | 3 | 1 | 5 | 1170 | 2 | 0.96 | 2 | 0.086768 | 0.25385
P 58 | 6 | 5 | 3 | 2 | 1 | 7268 | 3 | 1481 | 1.03 | 2 | 215333.3333 | 5 | 1 | 5 | 1400 | 4 | 0.83591 | 1 | 0.39095 | Not Availible
Espirito Santo | 6 | 5 | 2 | 1 | 3 | 6153 | 3 | 787 | 1.5086 | 2 | 105000 | 3 | 5 | 5 | 1780 | 1 | 0.95238 | 3 | 0.24778 | 1.32
P 54 | 6 | 5 | 3 | 2 | 1 | 5272 | 3 | 1034 | 0.629 | 2 | 215000 | 5 | 2 | 5 | 1315 | 5 | 0.83721 | 1 | 0.24468 | 0.97138
P 62 | 6 | 5 | 3 | 2 | 1 | 7336 | 2 | 1413 | 1.01 | 2 | 215333.3333 | 5 | 1 | 5 | 1600 | 4 | 0.83591 | 1 | 0.22647 | Not Availible
Cidade de Ilhabela | 6 | 4 | 3 | 1 | 3 | 7851 | 3 | 1172 | 1.5 | 2 | 185333.3333 | 4 | 1 | 5 | 2100 | 2 | 0.80935 | 2 | 0.052048 | Not Availible
Cidade de Campos dos Goytacazes MV29 | 6 | 4 | 3 | 1 | 3 | 9101 | 3 | 1018 | 1.263 | 2 | 179500 | 4 | 2 | 5 | 765 | 4 | 0.83565 | 1 | 0.27898 | 0.0055424
Terra Nova | 5 | 2 | 1 | 2 | 1 | 2800 | 3 | 1157 | 1.3 | 1 | 175000 | 4 | 5 | 5 | 90 | 1 | 0.85714 | 2 | 0.39412 | 0.30769
Sea Rose | 5 | 3 | 1 | 2 | 1 | 4476 | 3 | 1229 | 0.49 | 1 | 125000 | 3 | 5 | 5 | 120 | 1 | 0.8 | 4 | 0.072417 | 0.2
Turritella | 3 | 1 | 1 | 2 | 1 | 8528 | 3 | 1149 | 1 | 2 | 62500 | 2 | 4 | 5 | 2900 | 2 | 0.96 | 5 | 0.11227 | 0.311
Asgard A | 7 | 3 | 1 | 2 | 1 | 2356 | 4 | 870 | 5.2941 | 1 | 300000 | 6 | 4 | 5 | 300 | 1 | 0.66667 | 3 | 0.20805 | 0.36
Balder | 7 | 3 | 2 | 2 | 1 | 1826 | 4 | 592 | 0.35 | 1 | 90500 | 2 | 5 | 5 | 125 | 1 | 0.91713 | 1 | 1.9291 | 0.62
Goliat FPSO | 7 | 2 | 1 | 2 | 1 | 7218 | 3 | 1364 | 3.9 | 1 | 122500 | 3 | 5 | 5 | 400 | 1 | 0.81633 | 4 | 0.72361 | 0.52
Petrojarl Knarr | 7 | 2 | 1 | 1 | 3 | 7850 | 3 | 732 | 1.6119 | 1 | 70833.3333 | 2 | 2 | 5 | 410 | 2 | 0.88941 | 4 | 0.85656 | 0.36975
Norne | 7 | 2 | 1 | 2 | 1 | 1551 | 3 | 1334 | 4.7 | 1 | 261666.6667 | 6 | 4 | 5 | 380 | 3 | 0.84076 | 4 | -0.12519 | 0.6
Skarv | 7 | 2 | 2 | 2 | 1 | 6240 | 3 | 1245 | 5 | 1 | 167500 | 4 | 4 | 5 | 370 | 1 | 0.47761 | 4 | 0.73494 | 0.7
Glen Lyon | 7 | 3 | 2 | 2 | 1 | 7729 | 3 | 1949 | 4.78 | 1 | 166666.6667 | 4 | 2 | 5 | 424 | 1 | 0.78 | 4 | 0.16675 | 0.19247
Western Isles FPSO | 7 | 1 | 1 | 2 | 1 | 8391 | 3 | 952 | 1.6 | 1 | 40000 | 1 | 3 | 5 | 165 | 2 | 1 | 3 | 0.8792 | 0.25
Belanak Natuna | 2 | 4 | 2 | 2 | 1 | 4250 | 4 | 1137 | 1.6 | 1 | 158333.3333 | 4 | 4 | 5 | 100 | 2 | 0.63158 | 4 | 0.058927 | 0.078167
Kikeh FPSO | 2 | 5 | 1 | 1 | 3 | 5513 | 3 | 939 | 0.8 | 2 | 143500 | 3 | 2 | 5 | 1350 | 1 | 0.83624 | 4 | -0.015974 | 0.2
Song Doc Pride MV 19 | 2 | 1 | 3 | 1 | 1 | 6339 | 3 | 417 | 0.25 | 2 | 30000 | 1 | 1 | 5 | 55 | 2 | 1 | 1 | 0.35012 | 0.04087
Thai Binh Vn | 2 | 1 | 3 | 2 | 1 | 4446 | 3 | 611 | 0.714 | 1 | 68333.3333 | 2 | 1 | 5 | 48 | 2 | 0.95122 | 3 | 0.037643 | 0.044
Hai Yang Shi You 117 | 8 | 4 | 3 | 2 | 1 | 5524 | 3 | 897 | 1.8 | 1 | 190000 | 4 | 1 | 5 | 27 | 1 | 1 | 3 | 0.72798 | 0.38889
Hai Yang Shi You 116 | 8 | 1 | 3 | 2 | 1 | 5804 | 3 | 723 | 1.2 | 1 | 106000 | 3 | 1 | 5 | 125 | 1 | 1 | 1 | 0.3195 | 0.98
Unity | 1 | 4 | 2 | 2 | 1 | 4018 | 3 | 545 | 1 | 1 | 125000 | 3 | 2 | 7 | 65 | 3 | 1 | 2 | 0.70092 | 0.4
Yoho EPS | 1 | 3 | 2 | 2 | 1 | 4196 | 3 | 505 | 1.2 | 2 | 90000 | 2 | 2 | 7 | 56 | 1 | 1 | 1 | 0.20792 | 0.083333
Yoho | 1 | 3 | 2 | 2 | 1 | 4623 | 3 | 761 | 1.2 | 2 | 116666.6667 | 3 | 2 | 7 | 56 | 3 | 0.85714 | 2 | 0.6636 | 0.083333
Hanne Knutsen | 7 | 2 | 2 | 1 | 3 | 8124 | 3 | 1691 | 2.8649 | 2 | 100000 | 3 | 2 | 7 | 115 | 1 | 1 | 2 | 0.80958 | 0.85
Ailsa FSO | 7 | 2 | 2 | 2 | 1 | 9389 | 3 | 1364 | 4.7 | 1 | 108333.3333 | 3 | 2 | 7 | 90 | 5 | 0.23077 | 5 | 0 | 0
Gagak Rimang | 2 | 5 | 2 | 2 | 1 | 7891 | 3 | 1110 | 1.2 | 2 | 165000 | 4 | 2 | 7 | 33 | 1 | 1 | 3 | 0.42973 | 1.1667
Rang Dong MV17 | 2 | 1 | 3 | 1 | 3 | 6038 | 3 | 763 | 0.5 | 1 | 60000 | 2 | 1 | 7 | 60 | 2 | 1 | 1 | 0.10747 | 0.04087
Ichthys Explorer | 4 | 4 | 1 | 2 | 1 | 8046 | 3 | 1810 | 3 | 1 | 361166.6667 | 6 | 4 | 6 | 250 | 2 | 0.23535 | 5 | 0.35635 | 0.32353
P 51 | 6 | 5 | 3 | 2 | 1 | 5201 | 3 | 1418 | 0.83 | 1 | 215000 | 5 | 2 | 6 | 1250 | 5 | 0.83721 | 1 | 0.24401 | 0.25
P 56 | 6 | 5 | 3 | 2 | 1 | 6478 | 3 | 1114 | 1.4 | 1 | 135000 | 3 | 1 | 6 | 1670 | 5 | 0.74074 | 1 | 0.27379 | 0.071429
P 52 | 6 | 5 | 3 | 1 | 3 | 5060 | 3 | 1237 | 0.906 | 1 | 235000 | 5 | 2 | 6 | 1850 | 3 | 0.76596 | 1 | 0.19644 | 0.43488
P 55 | 6 | 5 | 3 | 2 | 1 | 6517 | 3 | 1518 | 1.65 | 1 | 215333.3333 | 5 | 2 | 6 | 1790 | 3 | 0.83591 | 1 | 0.49144 | Not Availible
Atlantis | 3 | 2 | 2 | 2 | 1 | 4533 | 3 | 1492 | 2.5 | 1 | 230000 | 5 | 2 | 6 | 2145 | 4 | 0.86957 | 1 | 0.60389 | 1.35
Delta House (Opti-Ex II) | 3 | 1 | 1 | 2 | 1 | 8158 | 3 | 1093 | 2 | 1 | 140000 | 3 | 2 | 6 | 1372 | 5 | 0.71429 | 2 | -0.012809 | 0
Blind Faith | 3 | 1 | 2 | 2 | 1 | 5802 | 3 | 846 | 1.151 | 1 | 52500 | 2 | 2 | 6 | 2130 | 1 | 0.85714 | 5 | 0.28605 | 0.95
Thunder Hawk | 3 | 1 | 1 | 1 | 3 | 6086 | 3 | 958 | 0.8 | 1 | 56666.6667 | 2 | 1 | 6 | 1847 | 4 | 0.79412 | 5 | 0.087683 | 0
Thunder Horse | 3 | 2 | 2 | 2 | 1 | 4624 | 3 | 1098 | 5 | 1 | 283333.3333 | 6 | 5 | 6 | 1830 | 1 | 0.88235 | 5 | 0.92623 | 2.68
Jack / St. Malo Semi | 3 | 1 | 2 | 2 | 1 | 7270 | 3 | 1844 | 7.5 | 1 | 177166.6667 | 4 | 1 | 6 | 2134 | 4 | 0.95955 | 5 | -0.005423 | 0
Asgard B | 7 | 4 | 1 | 2 | 1 | 2356 | 4 | 1570 | 1.3 | 1 | 351666.6667 | 6 | 1 | 6 | 300 | 5 | 0.38389 | 4 | 0 | 0
Gjoa | 7 | 2 | 1 | 2 | 1 | 6025 | 2 | 1461 | 4.4361 | 1 | 108333.3333 | 3 | 4 | 6 | 380 | 1 | 0.46154 | 4 | 0.08898 | 0.33
Kristin | 7 | 4 | 1 | 2 | 1 | 4368 | 3 | 1384 | 1.9 | 1 | 128000 | 3 | 5 | 6 | 370 | 1 | 0.97656 | 2 | 0.023844 | 0.73684
Snorre B | 7 | 4 | 1 | 2 | 1 | 3256 | 3 | 943 | 1.2821 | 1 | 115000 | 3 | 1 | 6 | 310 | 4 | 1 | 2 | -0.064687 | 0.17
Troll C | 7 | 3 | 1 | 2 | 1 | 2647 | 3 | 821 | 4.5 | 1 | 243333.3333 | 5 | 5 | 6 | 340 | 4 | 0.78082 | 3 | 0.18636 | Not Availible
Troll B | 7 | 3 | 1 | 2 | 1 | 379 | 3 | 1263 | 2.9 | 1 | 317000 | 6 | 5 | 6 | 320 | 2 | 0.85174 | 3 | 0.35234 | 0.14
Visund | 7 | 5 | 1 | 2 | 1 | 2251 | 4 | 851 | 0.7 | 1 | 171333.3333 | 4 | 5 | 6 | 335 | 1 | 0.65953 | 2 | 0.3396 | 0.45
Gumusut Semi | 2 | 5 | 2 | 1 | 3 | 6588 | 3 | 1233 | 1.6 | 1 | 200000 | 5 | 2 | 6 | 1220 | 3 | 0.75 | 3 | 0.99919 | 0.25
Perdido Spar | 3 | 2 | 2 | 2 | 1 | 6025 | 3 | 974 | 3 | 1 | 133333.3333 | 3 | 5 | 3 | 2440 | 1 | 0.75 | 3 | 0.40554 | Not Availible
Front Runner Spar | 3 | 2 | 1 | 2 | 1 | 4459 | 4 | 728 | 0.2 | 1 | 78333.3333 | 2 | 3 | 3 | 1015 | 1 | 0.76596 | 1 | 0.36676 | 0.075
Tahiti Spar | 3 | 2 | 2 | 2 | 1 | 5597 | 3 | 1159 | 3.5 | 1 | 136666.6667 | 3 | 3 | 3 | 1280 | 2 | 0.91463 | 2 | 0.26747 | 1.8
Holstein | 3 | 1 | 2 | 2 | 1 | 4070 | 3 | 859 | 1 | 1 | 135000 | 3 | 4 | 3 | 1345 | 2 | 0.81481 | 3 | 0.6135 | Not Availible
Mad Dog | 3 | 1 | 2 | 2 | 1 | 4070 | 3 | 1397 | 1.82 | 1 | 66666.6667 | 2 | 2 | 3 | 1370 | 1 | 0.9 | 4 | 0.022906 | 0.1
Heidelberg Spar | 3 | 1 | 1 | 2 | 1 | 8018 | 3 | 1649 | 6.745 | 1 | 93333.3333 | 2 | 4 | 3 | 1620 | 5 | 0.85714 | 5 | -0.095816 | 0.0081542
Lucius Spar | 3 | 1 | 1 | 2 | 1 | 8002 | 3 | 1007 | 7.736 | 1 | 155000 | 4 | 4 | 3 | 2165 | 4 | 0.51613 | 5 | 0.14002 | 0.008273
Medusa Spar | 3 | 2 | 1 | 2 | 1 | 4077 | 4 | 579 | 0.2 | 1 | 58333.3333 | 2 | 3 | 3 | 675 | 1 | 0.68571 | 1 | 0.74266 | 0.365
Gulfstar 1 | 3 | 1 | 2 | 1 | 3 | 7813 | 3 | 1132 | 2.3 | 1 | 109166.6667 | 3 | 2 | 3 | 1310 | 2 | 0.73282 | 3 | 0.12191 | 0.30435
Devil's Tower Spar | 3 | 3 | 1 | 1 | 3 | 4189 | 4 | 739 | 0.2 | 1 | 66666.6667 | 2 | 2 | 3 | 1710 | 2 | 0.9 | 1 | 0.41949 | 0.06
Kikeh Spar | 2 | 5 | 1 | 2 | 1 | 5513 | 3 | 939 | 0.5 | 1 | 142500 | 3 | 4 | 3 | 1330 | 1 | 0.84 | 4 | -0.015974 | 0.28571
Kizomba A Wellhead TLP | 1 | 4 | 2 | 2 | 1 | 4253 | 3 | 1073 | 0.65 | 1 | 250000 | 6 | 1 | 2 | 1175 | 3 | 1 | 2 | 0.0055918 | 0.13333
Kizomba B Wellhead TLP | 1 | 3 | 2 | 2 | 1 | 4756 | 3 | 1071 | 0.6 | 1 | 250000 | 6 | 1 | 2 | 1250 | 5 | 1 | 2 | -0.14006 | 0.13333
Okume TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.1425 | 1 | 30000 | 1 | 1 | 2 | 500 | 4 | 0.83333 | 4 | 0.04 | 0
Oveng TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.1425 | 1 | 30000 | 1 | 1 | 2 | 280 | 4 | 0.83333 | 4 | 0.04 | 0
P 61 Wellhead TLP | 6 | 5 | 3 | 2 | 1 | 7213 | 3 | 1475 | 1.07 | 1 | 145833.3333 | 3 | 3 | 2 | 1180 | 1 | 0.96 | 2 | 0.35051 | 0
Auger TLP | 3 | 2 | 2 | 2 | 1 | 287 | 3 | 1233 | 0.86364 | 1 | 65000 | 2 | 4 | 2 | 870 | 2 | 0.61538 | 4 | 0.044607 | 0.38947
Magnolia TLP | 3 | 1 | 2 | 2 | 1 | 4392 | 3 | 1040 | 0.6 | 1 | 75000 | 2 | 4 | 2 | 1432 | 2 | 0.66667 | 5 | 0.038462 | 0
Brutus TLP | 3 | 1 | 2 | 2 | 1 | 3570 | 3 | 674 | 0.76 | 1 | 155000 | 4 | 2 | 2 | 910 | 4 | 0.83871 | 4 | 0.038576 | 0.078947
Stampede TLP | 3 | 1 | 1 | 2 | 1 | 8523 | 3 | 1982 | 6.2 | 1 | 86666.6667 | 2 | 1 | 2 | 1160 | 4 | 0.92308 | 5 | -0.1221 | -0.12903
Neptune TLP | 3 | 2 | 1 | 2 | 1 | 5670 | 3 | 887 | 0.85 | 1 | 58333.3333 | 2 | 2 | 2 | 1300 | 2 | 0.85714 | 4 | 0.2345 | 0.47882
Shenzi TLP | 3 | 2 | 1 | 2 | 1 | 6001 | 3 | 1119 | 4.41 | 1 | 116666.6667 | 3 | 2 | 2 | 1333 | 2 | 0.85714 | 5 | -0.088472 | 0
Mars TLP | 3 | 1 | 2 | 2 | 1 | 1381 | 3 | 1098 | 1.2 | 1 | 230833.3333 | 5 | 2 | 2 | 896 | 4 | 0.86643 | 4 | -0.090164 | -0.054167
Olympus TLP | 3 | 1 | 2 | 2 | 1 | 7729 | 3 | 1202 | 3 | 1 | 116666.6667 | 3 | 2 | 2 | 945 | 5 | 0.85714 | 5 | -0.12562 | 0
Ursa TLP | 3 | 1 | 2 | 2 | 1 | 2398 | 3 | 1040 | 1.45 | 1 | 216666.6667 | 5 | 3 | 2 | 1160 | 5 | 0.69231 | 4 | -0.081731 | 0.043448
Ram Powell TLP | 3 | 1 | 2 | 2 | 1 | 1885 | 3 | 915 | 1 | 1 | 93333.3333 | 2 | 3 | 2 | 990 | 5 | 0.64286 | 4 | 0.015301 | 0
Big Foot | 3 | 4 | 2 | 2 | 1 | 7571 | 3 | 1529 | 4 | 1 | 79166.6667 | 2 | 5 | 2 | 1580 | 1 | 0.94737 | 5 | 0.94899 | 0.275
Heidrun TLP | 7 | 1 | 1 | 2 | 1 | 504 | 3 | 1548 | 3.9 | 1 | 283333.3333 | 6 | 2 | 2 | 350 | 2 | 0.88235 | 5 | 0.039406 | 0.076923
Malikai TLP | 2 | 5 | 2 | 2 | 1 | 8439 | 3 | 1030 | 1.2825 | 1 | 68333.3333 | 2 | 2 | 2 | 470 | 3 | 0.87805 | 5 | 0.36796 | 0.077973

## Cost_Sch2
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun
Bohai Ming Zhu | SEA CH | H | NOC | Own | 1 | 4350 | EPC | 259 | 0.4 | NEW | 40000 | VS | L | FPSO | 30 | N | 1 | N | 0.47104 | 0.25
Petrojarl Varg | NE | N | OC | Lease | 1 | 2240 | EPC | 816 | 0.46 | NEW | 65833.3333 | S | L | FPSO | 84 | N | 0.86582 | L | 0.28676 | 0.24
Stybarrow Venture MV16 | AUST/NZ | A | IOC | Lease | 3 | 5922 | EPC | 702 | 0.59843 | NEW | 87500 | S | A | FPSO | 825 | L | 0.91429 | M | -0.14387 | 0.27
Alima FPU | AFRICA | L | IOC | Own | 1 | 5720 | EPC | 994 | 1.133 | NEW | 100000 | M | N | BARGE | 600 | A | 0.9 | M | -0.022133 | 0.35
Jangkrik | SEA | M | OC | Own | 1 | 8824 | EPC | 1052 | 2.6765 | NEW | 79400 | S | L | BARGE | 120 | L | 0.055416 | A | 0.11407 | 0.17
Prelude | AUST/NZ | A | IOC | Own | 1 | 7814 | EPC | 2229 | 11.16 | NEW | 148333.3333 | UL | H | FLNG | 250 | N | 0.23596 | H | 0.24316 | 0.34409
CLOV FPSO | AFRICA | A | IOC | Own | 1 | 7534 | EPC | 1383 | 1.8 | NEW | 198333.3333 | L | L | FPSO | 1290 | M | 0.80672 | H | 0.0079537 | 0.055556
Dalia | AFRICA | M | IOC | Own | 1 | 4872 | EPC | 1306 | 3.4 | NEW | 287000 | UL | A | FPSO | 1360 | H | 0.83624 | L | 0.01072 | 0.17647
Girassol | AFRICA | M | IOC | Own | 1 | 3103 | EPC | 823 | 2.5 | NEW | 246666.6667 | VL | A | FPSO | 1350 | N | 0.81081 | N | 0.52126 | 0.12
Kizomba B | AFRICA | A | IOC | Own | 1 | 4756 | EPC | 1071 | 0.76 | NEW | 316666.6667 | UL | N | FPSO | 1250 | H | 0.78947 | L | -0.14006 | 0.13333
Mondo | AFRICA | M | IOC | Lease | 1 | 5866 | EPC | 797 | 0.75 | CONV | 115833.3333 | M | N | FPSO | 728 | A | 0.86331 | A | -0.10163 | 0
Saxi-Batuque | AFRICA | M | IOC | Lease | 3 | 5866 | EPC | 797 | 0.75 | CONV | 130000 | M | N | FPSO | 720 | A | 0.80769 | A | -0.084065 | 0
Greater Plutonio | AFRICA | A | IOC | Own | 1 | 5144 | EPC | 1124 | 1.73 | NEW | 305000 | UL | A | FPSO | 1350 | L | 0.81967 | H | 0.19039 | 0.85
PSVM FPSO | AFRICA | H | IOC | Own | 1 | 6755 | EPC | 1249 | 10 | CONV | 197833.3333 | L | H | FPSO | 2000 | L | 0.7936 | N | 0.29704 | 0.4
Baobab Ivoirien MV10 | AFRICA | N | OC | Lease | 3 | 4949 | EPC | 711 | 1.5 | CONV | 82500 | S | N | FPSO | 970 | A | 0.84848 | L | 0.067511 | 0
Prof. John Evans Atta Mills | AFRICA | M | IOC | Lease | 3 | 8617 | EPC | 1092 | 5 | CONV | 108333.3333 | M | N | FPSO | 1425 | L | 0.73846 | H | 0.015568 | 0
Agbami | AFRICA | L | IOC | Own | 2 | 5539 | EPC | 1126 | 4.1538 | NEW | 325000 | UL | L | FPSO | 1433 | L | 0.76923 | L | 0.11368 | 0.3
Akpo | AFRICA | M | IOC | Own | 1 | 5606 | TK | 1303 | 2.345 | NEW | 273333.3333 | UL | L | FPSO | 1325 | N | 0.67683 | A | 0.072141 | 1.55
Bonga | AFRICA | M | IOC | Own | 1 | 4049 | EPC | 1033 | 2.4 | NEW | 253333.3333 | UL | A | FPSO | 1250 | N | 0.88816 | A | 0.70765 | 0.5
Egina FPSO | AFRICA | H | IOC | Own | 1 | 8540 | EPC | 1595 | 16 | NEW | 260000 | UL | L | FPSO | 1600 | A | 0.76923 | L | 0.28715 | -0.09375
Erha | AFRICA | M | IOC | Own | 1 | 4671 | EPC | 1081 | 2.6 | NEW | 266666.6667 | UL | L | FPSO | 1180 | L | 0.7875 | L | 0.19334 | 0.57
Kizomba A | AFRICA | A | IOC | Own | 1 | 4253 | EPC | 1073 | 0.77 | NEW | 316666.6667 | UL | L | FPSO | 1250 | A | 0.78947 | L | 0.0055918 | 0.13333
Ichthys Venturer | AUST/NZ | M | IOC | Own | 1 | 8102 | EPC | 1743 | 2 | NEW | 85000 | S | H | FPSO | 250 | L | 1 | H | 0.37636 | 0.32353
Pyrenees Venture | AUST/NZ | A | IOC | Own | 2 | 6379 | EPC | 1014 | 1.66 | CONV | 106000 | M | M | FPSO | 200 | M | 0.90566 | H | 0.0019724 | 0.012028
Ngujima Yin | AUST/NZ | A | IOC | Own | 1 | 5993 | EPC | 716 | 0.72 | CONV | 136666.6667 | M | L | FPSO | 340 | L | 0.87805 | M | 0.14665 | 0.33333
P 50 | BRAZ | M | NOC | Own | 1 | 4557 | CL | 844 | 0.496 | CONV | 215000 | VL | N | FPSO | 1240 | M | 0.83721 | N | 0.66351 | 0.41129
P 43 | BRAZ | H | NOC | Own | 1 | 4199 | TK | 883 | 1.3 | CONV | 185000 | L | N | FPSO | 800 | M | 0.81081 | N | 0.43828 | 0.38462
P 48 | BRAZ | H | NOC | Own | 1 | 4199 | TK | 1066 | 1.3 | CONV | 185000 | L | N | FPSO | 1040 | L | 0.81081 | N | 0.25516 | 0.38462
Frade | BRAZ | A | IOC | Own | 1 | 6014 | EPC | 909 | 2 | CONV | 117666.6667 | M | L | FPSO | 1080 | N | 0.84986 | H | 0.20902 | 1.35
P 57 | BRAZ | H | NOC | Lease | 2 | 6622 | EPC | 1041 | 1.195 | CONV | 191833.3333 | L | N | FPSO | 1300 | M | 0.93831 | N | -0.045149 | 0.0041841
Pioneiro de Libra | BRAZ | H | NOC | Lease | 3 | 8984 | PS | 831 | 1 | CONV | 73333.3333 | S | N | FPSO | 2200 | H | 0.68182 | N | 0.45728 | 0.59441
P 63 | BRAZ | H | NOC | Own | 1 | 7213 | EPC | 1383 | 1.3 | CONV | 145833.3333 | M | N | FPSO | 1170 | L | 0.96 | L | 0.086768 | 0.25385
Espirito Santo | BRAZ | H | IOC | Lease | 3 | 6153 | EPC | 787 | 1.5086 | CONV | 105000 | M | H | FPSO | 1780 | N | 0.95238 | A | 0.24778 | 1.32
P 54 | BRAZ | H | NOC | Own | 1 | 5272 | EPC | 1034 | 0.629 | CONV | 215000 | VL | L | FPSO | 1315 | H | 0.83721 | N | 0.24468 | 0.97138
Cidade de Campos dos Goytacazes MV29 | BRAZ | M | NOC | Lease | 3 | 9101 | EPC | 1018 | 1.263 | CONV | 179500 | L | L | FPSO | 765 | M | 0.83565 | N | 0.27898 | 0.0055424
Terra Nova | CAN | L | OC | Own | 1 | 2800 | EPC | 1157 | 1.3 | NEW | 175000 | L | H | FPSO | 90 | N | 0.85714 | L | 0.39412 | 0.30769
Sea Rose | CAN | A | OC | Own | 1 | 4476 | EPC | 1229 | 0.49 | NEW | 125000 | M | H | FPSO | 120 | N | 0.8 | M | 0.072417 | 0.2
Turritella | GOM | N | OC | Own | 1 | 8528 | EPC | 1149 | 1 | Conv | 62500 | S | M | FPSO | 2900 | L | 0.96 | H | 0.11227 | 0.311
Asgard A | NE | A | OC | Own | 1 | 2356 | TK | 870 | 5.2941 | NEW | 300000 | UL | M | FPSO | 300 | N | 0.66667 | A | 0.20805 | 0.36
Balder | NE | A | IOC | Own | 1 | 1826 | TK | 592 | 0.35 | NEW | 90500 | S | H | FPSO | 125 | N | 0.91713 | N | 1.9291 | 0.62
Goliat FPSO | NE | L | OC | Own | 1 | 7218 | EPC | 1364 | 3.9 | NEW | 122500 | M | H | FPSO | 400 | N | 0.81633 | M | 0.72361 | 0.52
Petrojarl Knarr | NE | L | OC | Lease | 3 | 7850 | EPC | 732 | 1.6119 | NEW | 70833.3333 | S | L | FPSO | 410 | L | 0.88941 | M | 0.85656 | 0.36975
Norne | NE | L | OC | Own | 1 | 1551 | EPC | 1334 | 4.7 | NEW | 261666.6667 | UL | M | FPSO | 380 | A | 0.84076 | M | -0.12519 | 0.6
Skarv | NE | L | IOC | Own | 1 | 6240 | EPC | 1245 | 5 | NEW | 167500 | L | M | FPSO | 370 | N | 0.47761 | M | 0.73494 | 0.7
Glen Lyon | NE | A | IOC | Own | 1 | 7729 | EPC | 1949 | 4.78 | NEW | 166666.6667 | L | L | FPSO | 424 | N | 0.78 | M | 0.16675 | 0.19247
Western Isles FPSO | NE | N | OC | Own | 1 | 8391 | EPC | 952 | 1.6 | NEW | 40000 | VS | A | FPSO | 165 | L | 1 | A | 0.8792 | 0.25
Belanak Natuna | SEA | M | IOC | Own | 1 | 4250 | TK | 1137 | 1.6 | NEW | 158333.3333 | L | M | FPSO | 100 | L | 0.63158 | M | 0.058927 | 0.078167
Kikeh FPSO | SEA | H | OC | Lease | 3 | 5513 | EPC | 939 | 0.8 | CONV | 143500 | M | L | FPSO | 1350 | N | 0.83624 | M | -0.015974 | 0.2
Song Doc Pride MV 19 | SEA | N | NOC | Lease | 1 | 6339 | EPC | 417 | 0.25 | CONV | 30000 | VS | N | FPSO | 55 | L | 1 | N | 0.35012 | 0.04087
Thai Binh Vn | SEA | N | NOC | Own | 1 | 4446 | EPC | 611 | 0.714 | NEW | 68333.3333 | S | N | FPSO | 48 | L | 0.95122 | A | 0.037643 | 0.044
Hai Yang Shi You 117 | SEA CH | M | NOC | Own | 1 | 5524 | EPC | 897 | 1.8 | NEW | 190000 | L | N | FPSO | 27 | N | 1 | A | 0.72798 | 0.38889
Hai Yang Shi You 116 | SEA CH | N | NOC | Own | 1 | 5804 | EPC | 723 | 1.2 | NEW | 106000 | M | N | FPSO | 125 | N | 1 | N | 0.3195 | 0.98
Unity | AFRICA | M | IOC | Own | 1 | 4018 | EPC | 545 | 1 | NEW | 125000 | M | L | FSO | 65 | A | 1 | L | 0.70092 | 0.4
Yoho EPS | AFRICA | A | IOC | Own | 1 | 4196 | EPC | 505 | 1.2 | CONV | 90000 | S | L | FSO | 56 | N | 1 | N | 0.20792 | 0.083333
Yoho | AFRICA | A | IOC | Own | 1 | 4623 | EPC | 761 | 1.2 | CONV | 116666.6667 | M | L | FSO | 56 | A | 0.85714 | L | 0.6636 | 0.083333
Hanne Knutsen | NE | L | IOC | Lease | 3 | 8124 | EPC | 1691 | 2.8649 | CONV | 100000 | M | L | FSO | 115 | N | 1 | L | 0.80958 | 0.85
Ailsa FSO | NE | L | IOC | Own | 1 | 9389 | EPC | 1364 | 4.7 | NEW | 108333.3333 | M | L | FSO | 90 | H | 0.23077 | H | 0 | 0
Gagak Rimang | SEA | H | IOC | Own | 1 | 7891 | EPC | 1110 | 1.2 | CONV | 165000 | L | L | FSO | 33 | N | 1 | A | 0.42973 | 1.1667
Rang Dong MV17 | SEA | N | NOC | Lease | 3 | 6038 | EPC | 763 | 0.5 | NEW | 60000 | S | N | FSO | 60 | L | 1 | N | 0.10747 | 0.04087
Ichthys Explorer | AUST/NZ | M | OC | Own | 1 | 8046 | EPC | 1810 | 3 | NEW | 361166.6667 | UL | M | SEMI | 250 | L | 0.23535 | H | 0.35635 | 0.32353
P 51 | BRAZ | H | NOC | Own | 1 | 5201 | EPC | 1418 | 0.83 | NEW | 215000 | VL | L | SEMI | 1250 | H | 0.83721 | N | 0.24401 | 0.25
P 56 | BRAZ | H | NOC | Own | 1 | 6478 | EPC | 1114 | 1.4 | NEW | 135000 | M | N | SEMI | 1670 | H | 0.74074 | N | 0.27379 | 0.071429
P 52 | BRAZ | H | NOC | Lease | 3 | 5060 | EPC | 1237 | 0.906 | NEW | 235000 | VL | L | SEMI | 1850 | A | 0.76596 | N | 0.19644 | 0.43488
Atlantis | GOM | L | IOC | Own | 1 | 4533 | EPC | 1492 | 2.5 | NEW | 230000 | VL | L | SEMI | 2145 | M | 0.86957 | N | 0.60389 | 1.35
Delta House (Opti-Ex II) | GOM | N | OC | Own | 1 | 8158 | EPC | 1093 | 2 | NEW | 140000 | M | L | SEMI | 1372 | H | 0.71429 | L | -0.012809 | 0
Blind Faith | GOM | N | IOC | Own | 1 | 5802 | EPC | 846 | 1.151 | NEW | 52500 | S | L | SEMI | 2130 | N | 0.85714 | H | 0.28605 | 0.95
Thunder Hawk | GOM | N | OC | Lease | 3 | 6086 | EPC | 958 | 0.8 | NEW | 56666.6667 | S | N | SEMI | 1847 | M | 0.79412 | H | 0.087683 | 0
Thunder Horse | GOM | L | IOC | Own | 1 | 4624 | EPC | 1098 | 5 | NEW | 283333.3333 | UL | H | SEMI | 1830 | N | 0.88235 | H | 0.92623 | 2.68
Jack / St. Malo Semi | GOM | N | IOC | Own | 1 | 7270 | EPC | 1844 | 7.5 | NEW | 177166.6667 | L | N | SEMI | 2134 | M | 0.95955 | H | -0.005423 | 0
Asgard B | NE | M | OC | Own | 1 | 2356 | TK | 1570 | 1.3 | New | 351666.6667 | UL | N | SEMI | 300 | H | 0.38389 | M | 0 | 0
Gjoa | NE | L | OC | Own | 1 | 6025 | CL | 1461 | 4.4361 | NEW | 108333.3333 | M | M | SEMI | 380 | N | 0.46154 | M | 0.08898 | 0.33
Kristin | NE | M | OC | Own | 1 | 4368 | EPC | 1384 | 1.9 | New | 128000 | M | H | SEMI | 370 | N | 0.97656 | L | 0.023844 | 0.73684
Snorre B | NE | M | OC | Own | 1 | 3256 | EPC | 943 | 1.2821 | NEW | 115000 | M | N | SEMI | 310 | M | 1 | L | -0.064687 | 0.17
Troll B | NE | A | OC | Own | 1 | 379 | EPC | 1263 | 2.9 | NEW | 317000 | UL | H | SEMI | 320 | L | 0.85174 | A | 0.35234 | 0.14
Visund | NE | H | OC | Own | 1 | 2251 | TK | 851 | 0.7 | NEW | 171333.3333 | L | H | SEMI | 335 | N | 0.65953 | L | 0.3396 | 0.45
Gumusut Semi | SEA | H | IOC | Lease | 3 | 6588 | EPC | 1233 | 1.6 | NEW | 200000 | VL | L | SEMI | 1220 | A | 0.75 | A | 0.99919 | 0.25
Front Runner Spar | GOM | L | OC | Own | 1 | 4459 | TK | 728 | 0.2 | NEW | 78333.3333 | S | A | SPAR | 1015 | N | 0.76596 | N | 0.36676 | 0.075
Tahiti Spar | GOM | L | IOC | Own | 1 | 5597 | EPC | 1159 | 3.5 | NEW | 136666.6667 | M | A | SPAR | 1280 | L | 0.91463 | L | 0.26747 | 1.8
Mad Dog | GOM | N | IOC | Own | 1 | 4070 | EPC | 1397 | 1.82 | NEW | 66666.6667 | S | L | SPAR | 1370 | N | 0.9 | M | 0.022906 | 0.1
Heidelberg Spar | GOM | N | OC | Own | 1 | 8018 | EPC | 1649 | 6.745 | NEW | 93333.3333 | S | M | SPAR | 1620 | H | 0.85714 | H | -0.095816 | 0.0081542
Lucius Spar | GOM | N | OC | Own | 1 | 8002 | EPC | 1007 | 7.736 | NEW | 155000 | L | M | SPAR | 2165 | M | 0.51613 | H | 0.14002 | 0.008273
Medusa Spar | GOM | L | OC | Own | 1 | 4077 | TK | 579 | 0.2 | NEW | 58333.3333 | S | A | SPAR | 675 | N | 0.68571 | N | 0.74266 | 0.365
Gulfstar 1 | GOM | N | IOC | Lease | 3 | 7813 | EPC | 1132 | 2.3 | NEW | 109166.6667 | M | L | SPAR | 1310 | L | 0.73282 | A | 0.12191 | 0.30435
Devil's Tower Spar | GOM | A | OC | Lease | 3 | 4189 | TK | 739 | 0.2 | NEW | 66666.6667 | S | L | SPAR | 1710 | L | 0.9 | N | 0.41949 | 0.06
Kikeh Spar | SEA | H | OC | Own | 1 | 5513 | EPC | 939 | 0.5 | NEW | 142500 | M | M | SPAR | 1330 | N | 0.84 | M | -0.015974 | 0.28571
Kizomba A Wellhead TLP | AFRICA | M | IOC | Own | 1 | 4253 | EPC | 1073 | 0.65 | NEW | 250000 | UL | N | TLP | 1175 | A | 1 | L | 0.0055918 | 0.13333
Kizomba B Wellhead TLP | AFRICA | A | IOC | Own | 1 | 4756 | EPC | 1071 | 0.6 | NEW | 250000 | UL | N | TLP | 1250 | H | 1 | L | -0.14006 | 0.13333
Okume TLP | AFRICA | L | OC | Own | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | VS | N | TLP | 500 | M | 0.83333 | M | 0.04 | 0
Oveng TLP | AFRICA | L | OC | Own | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | VS | N | TLP | 280 | M | 0.83333 | M | 0.04 | 0
P 61 Wellhead TLP | BRAZ | H | NOC | Own | 1 | 7213 | EPC | 1475 | 1.07 | NEW | 145833.3333 | M | A | TLP | 1180 | N | 0.96 | L | 0.35051 | 0
Auger TLP | GOM | L | IOC | Own | 1 | 287 | EPC | 1233 | 0.86364 | NEW | 65000 | S | M | TLP | 870 | L | 0.61538 | M | 0.044607 | 0.38947
Magnolia TLP | GOM | N | IOC | Own | 1 | 4392 | EPC | 1040 | 0.6 | NEW | 75000 | S | M | TLP | 1432 | L | 0.66667 | H | 0.038462 | 0
Brutus TLP | GOM | N | IOC | Own | 1 | 3570 | EPC | 674 | 0.76 | NEW | 155000 | L | L | TLP | 910 | M | 0.83871 | M | 0.038576 | 0.078947
Stampede TLP | GOM | N | OC | Own | 1 | 8523 | EPC | 1982 | 6.2 | NEW | 86666.6667 | S | N | TLP | 1160 | M | 0.92308 | H | -0.1221 | -0.12903
Neptune TLP | GOM | L | OC | Own | 1 | 5670 | EPC | 887 | 0.85 | NEW | 58333.3333 | S | L | TLP | 1300 | L | 0.85714 | M | 0.2345 | 0.47882
Shenzi TLP | GOM | L | OC | Own | 1 | 6001 | EPC | 1119 | 4.41 | NEW | 116666.6667 | M | L | TLP | 1333 | L | 0.85714 | H | -0.088472 | 0
Mars TLP | GOM | N | IOC | Own | 1 | 1381 | EPC | 1098 | 1.2 | NEW | 230833.3333 | VL | L | TLP | 896 | M | 0.86643 | M | -0.090164 | -0.054167
Olympus TLP | GOM | N | IOC | Own | 1 | 7729 | EPC | 1202 | 3 | NEW | 116666.6667 | M | L | TLP | 945 | H | 0.85714 | H | -0.12562 | 0
Ursa TLP | GOM | N | IOC | Own | 1 | 2398 | EPC | 1040 | 1.45 | NEW | 216666.6667 | VL | A | TLP | 1160 | H | 0.69231 | M | -0.081731 | 0.043448
Ram Powell TLP | GOM | N | IOC | Own | 1 | 1885 | EPC | 915 | 1 | NEW | 93333.3333 | S | A | TLP | 990 | H | 0.64286 | M | 0.015301 | 0
Big Foot | GOM | M | IOC | Own | 1 | 7571 | EPC | 1529 | 4 | NEW | 79166.6667 | S | H | TLP | 1580 | N | 0.94737 | H | 0.94899 | 0.275
Heidrun TLP | NE | N | OC | Own | 1 | 504 | EPC | 1548 | 3.9 | NEW | 283333.3333 | UL | L | TLP | 350 | L | 0.88235 | H | 0.039406 | 0.076923
Malikai TLP | SEA | H | IOC | Own | 1 | 8439 | EPC | 1030 | 1.2825 | NEW | 68333.3333 | S | L | TLP | 470 | A | 0.87805 | H | 0.36796 | 0.077973

## Cost2
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Lease/ Own | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun
Bohai Ming Zhu | 8 | 5 | 2 | 1 | 40000 | 1 | 2 | 4 | 30 | 1 | 1 | 1 | 0.47104 | 0.25
Petrojarl Varg | 5 | 1 | 1 | 1 | 65833.3333 | 2 | 2 | 4 | 84 | 1 | 0.86582 | 2 | 0.28676 | 0.24
Stybarrow Venture MV16 | 4 | 3 | 1 | 1 | 87500 | 2 | 3 | 4 | 825 | 2 | 0.91429 | 4 | -0.14387 | 0.27
Alima FPU | 1 | 2 | 2 | 1 | 100000 | 3 | 1 | 2 | 600 | 3 | 0.9 | 4 | -0.022133 | 0.35
Jangkrik | 2 | 4 | 2 | 1 | 79400 | 2 | 2 | 2 | 120 | 2 | 0.055416 | 3 | 0.11407 | 0.17
Prelude | 4 | 3 | 2 | 1 | 148333.3333 | 6 | 5 | 5 | 250 | 1 | 0.23596 | 5 | 0.24316 | 0.34409
CLOV FPSO | 1 | 3 | 2 | 1 | 198333.3333 | 4 | 2 | 4 | 1290 | 4 | 0.80672 | 5 | 0.0079537 | 0.055556
Dalia | 1 | 4 | 2 | 1 | 287000 | 6 | 3 | 4 | 1360 | 5 | 0.83624 | 2 | 0.01072 | 0.17647
Girassol | 1 | 4 | 2 | 1 | 246666.6667 | 5 | 3 | 4 | 1350 | 1 | 0.81081 | 1 | 0.52126 | 0.12
Kizomba B | 1 | 3 | 2 | 1 | 316666.6667 | 6 | 1 | 4 | 1250 | 5 | 0.78947 | 2 | -0.14006 | 0.13333
Mondo | 1 | 4 | 1 | 2 | 115833.3333 | 3 | 1 | 4 | 728 | 3 | 0.86331 | 3 | -0.10163 | 0
Saxi-Batuque | 1 | 4 | 1 | 2 | 130000 | 3 | 1 | 4 | 720 | 3 | 0.80769 | 3 | -0.084065 | 0
Greater Plutonio | 1 | 3 | 2 | 1 | 305000 | 6 | 3 | 4 | 1350 | 2 | 0.81967 | 5 | 0.19039 | 0.85
PSVM FPSO | 1 | 5 | 2 | 2 | 197833.3333 | 4 | 5 | 4 | 2000 | 2 | 0.7936 | 1 | 0.29704 | 0.4
Baobab Ivoirien MV10 | 1 | 1 | 1 | 2 | 82500 | 2 | 1 | 4 | 970 | 3 | 0.84848 | 2 | 0.067511 | 0
Prof. John Evans Atta Mills | 1 | 4 | 1 | 2 | 108333.3333 | 3 | 1 | 4 | 1425 | 2 | 0.73846 | 5 | 0.015568 | 0
Agbami | 1 | 2 | 2 | 1 | 325000 | 6 | 2 | 4 | 1433 | 2 | 0.76923 | 2 | 0.11368 | 0.3
Akpo | 1 | 4 | 2 | 1 | 273333.3333 | 6 | 2 | 4 | 1325 | 1 | 0.67683 | 3 | 0.072141 | 1.55
Bonga | 1 | 4 | 2 | 1 | 253333.3333 | 6 | 3 | 4 | 1250 | 1 | 0.88816 | 3 | 0.70765 | 0.5
Egina FPSO | 1 | 5 | 2 | 1 | 260000 | 6 | 2 | 4 | 1600 | 3 | 0.76923 | 2 | 0.28715 | -0.09375
Erha | 1 | 4 | 2 | 1 | 266666.6667 | 6 | 2 | 4 | 1180 | 2 | 0.7875 | 2 | 0.19334 | 0.57
Kizomba A | 1 | 3 | 2 | 1 | 316666.6667 | 6 | 2 | 4 | 1250 | 3 | 0.78947 | 2 | 0.0055918 | 0.13333
Ichthys Venturer | 4 | 4 | 2 | 1 | 85000 | 2 | 5 | 4 | 250 | 2 | 1 | 5 | 0.37636 | 0.32353
Pyrenees Venture | 4 | 3 | 2 | 2 | 106000 | 3 | 4 | 4 | 200 | 4 | 0.90566 | 5 | 0.0019724 | 0.012028
Ngujima Yin | 4 | 3 | 2 | 2 | 136666.6667 | 3 | 2 | 4 | 340 | 2 | 0.87805 | 4 | 0.14665 | 0.33333
P 50 | 7 | 4 | 2 | 2 | 215000 | 5 | 1 | 4 | 1240 | 4 | 0.83721 | 1 | 0.66351 | 0.41129
P 43 | 7 | 5 | 2 | 2 | 185000 | 4 | 1 | 4 | 800 | 4 | 0.81081 | 1 | 0.43828 | 0.38462
P 48 | 7 | 5 | 2 | 2 | 185000 | 4 | 1 | 4 | 1040 | 2 | 0.81081 | 1 | 0.25516 | 0.38462
Frade | 7 | 3 | 2 | 2 | 117666.6667 | 3 | 2 | 4 | 1080 | 1 | 0.84986 | 5 | 0.20902 | 1.35
P 57 | 7 | 5 | 1 | 2 | 191833.3333 | 4 | 1 | 4 | 1300 | 4 | 0.93831 | 1 | -0.045149 | 0.0041841
Pioneiro de Libra | 7 | 5 | 1 | 2 | 73333.3333 | 2 | 1 | 4 | 2200 | 5 | 0.68182 | 1 | 0.45728 | 0.59441
P 63 | 7 | 5 | 2 | 2 | 145833.3333 | 3 | 1 | 4 | 1170 | 2 | 0.96 | 2 | 0.086768 | 0.25385
Espirito Santo | 7 | 5 | 1 | 2 | 105000 | 3 | 5 | 4 | 1780 | 1 | 0.95238 | 3 | 0.24778 | 1.32
P 54 | 7 | 5 | 2 | 2 | 215000 | 5 | 2 | 4 | 1315 | 5 | 0.83721 | 1 | 0.24468 | 0.97138
Cidade de Campos dos Goytacazes MV29 | 7 | 4 | 1 | 2 | 179500 | 4 | 2 | 4 | 765 | 4 | 0.83565 | 1 | 0.27898 | 0.0055424
Terra Nova | 3 | 2 | 2 | 1 | 175000 | 4 | 5 | 4 | 90 | 1 | 0.85714 | 2 | 0.39412 | 0.30769
Sea Rose | 3 | 3 | 2 | 1 | 125000 | 3 | 5 | 4 | 120 | 1 | 0.8 | 4 | 0.072417 | 0.2
Turritella | 6 | 1 | 2 | 2 | 62500 | 2 | 4 | 4 | 2900 | 2 | 0.96 | 5 | 0.11227 | 0.311
Asgard A | 5 | 3 | 2 | 1 | 300000 | 6 | 4 | 4 | 300 | 1 | 0.66667 | 3 | 0.20805 | 0.36
Balder | 5 | 3 | 2 | 1 | 90500 | 2 | 5 | 4 | 125 | 1 | 0.91713 | 1 | 1.9291 | 0.62
Goliat FPSO | 5 | 2 | 2 | 1 | 122500 | 3 | 5 | 4 | 400 | 1 | 0.81633 | 4 | 0.72361 | 0.52
Petrojarl Knarr | 5 | 2 | 1 | 1 | 70833.3333 | 2 | 2 | 4 | 410 | 2 | 0.88941 | 4 | 0.85656 | 0.36975
Norne | 5 | 2 | 2 | 1 | 261666.6667 | 6 | 4 | 4 | 380 | 3 | 0.84076 | 4 | -0.12519 | 0.6
Skarv | 5 | 2 | 2 | 1 | 167500 | 4 | 4 | 4 | 370 | 1 | 0.47761 | 4 | 0.73494 | 0.7
Glen Lyon | 5 | 3 | 2 | 1 | 166666.6667 | 4 | 2 | 4 | 424 | 1 | 0.78 | 4 | 0.16675 | 0.19247
Western Isles FPSO | 5 | 1 | 2 | 1 | 40000 | 1 | 3 | 4 | 165 | 2 | 1 | 3 | 0.8792 | 0.25
Belanak Natuna | 2 | 4 | 2 | 1 | 158333.3333 | 4 | 4 | 4 | 100 | 2 | 0.63158 | 4 | 0.058927 | 0.078167
Kikeh FPSO | 2 | 5 | 1 | 2 | 143500 | 3 | 2 | 4 | 1350 | 1 | 0.83624 | 4 | -0.015974 | 0.2
Song Doc Pride MV 19 | 2 | 1 | 1 | 2 | 30000 | 1 | 1 | 4 | 55 | 2 | 1 | 1 | 0.35012 | 0.04087
Thai Binh Vn | 2 | 1 | 2 | 1 | 68333.3333 | 2 | 1 | 4 | 48 | 2 | 0.95122 | 3 | 0.037643 | 0.044
Hai Yang Shi You 117 | 8 | 4 | 2 | 1 | 190000 | 4 | 1 | 4 | 27 | 1 | 1 | 3 | 0.72798 | 0.38889
Hai Yang Shi You 116 | 8 | 1 | 2 | 1 | 106000 | 3 | 1 | 4 | 125 | 1 | 1 | 1 | 0.3195 | 0.98
Unity | 1 | 4 | 2 | 1 | 125000 | 3 | 2 | 6 | 65 | 3 | 1 | 2 | 0.70092 | 0.4
Yoho | 1 | 3 | 2 | 2 | 90000 | 2 | 2 | 6 | 56 | 1 | 1 | 1 | 0.20792 | 0.083333
Yoho | 1 | 3 | 2 | 2 | 116666.6667 | 3 | 2 | 6 | 56 | 3 | 0.85714 | 2 | 0.6636 | 0.083333
Hanne Knutsen | 5 | 2 | 1 | 2 | 100000 | 3 | 2 | 6 | 115 | 1 | 1 | 2 | 0.80958 | 0.85
Ailsa FSO | 5 | 2 | 2 | 1 | 108333.3333 | 3 | 2 | 6 | 90 | 5 | 0.23077 | 5 | 0 | 0
Gagak Rimang | 2 | 5 | 2 | 2 | 165000 | 4 | 2 | 6 | 33 | 1 | 1 | 3 | 0.42973 | 1.1667
Rang Dong MV17 | 2 | 1 | 1 | 1 | 60000 | 2 | 1 | 6 | 60 | 2 | 1 | 1 | 0.10747 | 0.04087
Ichthys Explorer | 4 | 4 | 2 | 1 | 361166.6667 | 6 | 4 | 7 | 250 | 2 | 0.23535 | 5 | 0.35635 | 0.32353
P 51 | 7 | 5 | 2 | 1 | 215000 | 5 | 2 | 7 | 1250 | 5 | 0.83721 | 1 | 0.24401 | 0.25
P 56 | 7 | 5 | 2 | 1 | 135000 | 3 | 1 | 7 | 1670 | 5 | 0.74074 | 1 | 0.27379 | 0.071429
P 52 | 7 | 5 | 1 | 1 | 235000 | 5 | 2 | 7 | 1850 | 3 | 0.76596 | 1 | 0.19644 | 0.43488
Atlantis | 6 | 2 | 2 | 1 | 230000 | 5 | 2 | 7 | 2145 | 4 | 0.86957 | 1 | 0.60389 | 1.35
Delta House (Opti-Ex II) | 6 | 1 | 2 | 1 | 140000 | 3 | 2 | 7 | 1372 | 5 | 0.71429 | 2 | -0.012809 | 0
Blind Faith | 6 | 1 | 2 | 1 | 52500 | 2 | 2 | 7 | 2130 | 1 | 0.85714 | 5 | 0.28605 | 0.95
Thunder Hawk | 6 | 1 | 1 | 1 | 56666.6667 | 2 | 1 | 7 | 1847 | 4 | 0.79412 | 5 | 0.087683 | 0
Thunder Horse | 6 | 2 | 2 | 1 | 283333.3333 | 6 | 5 | 7 | 1830 | 1 | 0.88235 | 5 | 0.92623 | 2.68
Jack / St. Malo Semi | 6 | 1 | 2 | 1 | 177166.6667 | 4 | 1 | 7 | 2134 | 4 | 0.95955 | 5 | -0.005423 | 0
Asgard B | 5 | 4 | 2 | 1 | 351666.6667 | 6 | 1 | 7 | 300 | 5 | 0.38389 | 4 | 0 | 0
Gjoa | 5 | 2 | 2 | 1 | 108333.3333 | 3 | 4 | 7 | 380 | 1 | 0.46154 | 4 | 0.08898 | 0.33
Kristin | 5 | 4 | 2 | 1 | 128000 | 3 | 5 | 7 | 370 | 1 | 0.97656 | 2 | 0.023844 | 0.73684
Snorre B | 5 | 4 | 2 | 1 | 115000 | 3 | 1 | 7 | 310 | 4 | 1 | 2 | -0.064687 | 0.17
Troll B | 5 | 3 | 2 | 1 | 317000 | 6 | 5 | 7 | 320 | 2 | 0.85174 | 3 | 0.35234 | 0.14
Visund | 5 | 5 | 2 | 1 | 171333.3333 | 4 | 5 | 7 | 335 | 1 | 0.65953 | 2 | 0.3396 | 0.45
Gumusut Semi | 2 | 5 | 1 | 1 | 200000 | 5 | 2 | 7 | 1220 | 3 | 0.75 | 3 | 0.99919 | 0.25
Front Runner Spar | 6 | 2 | 2 | 1 | 78333.3333 | 2 | 3 | 3 | 1015 | 1 | 0.76596 | 1 | 0.36676 | 0.075
Tahiti Spar | 6 | 2 | 2 | 1 | 136666.6667 | 3 | 3 | 3 | 1280 | 2 | 0.91463 | 2 | 0.26747 | 1.8
Mad Dog | 6 | 1 | 2 | 1 | 66666.6667 | 2 | 2 | 3 | 1370 | 1 | 0.9 | 4 | 0.022906 | 0.1
Heidelberg Spar | 6 | 1 | 2 | 1 | 93333.3333 | 2 | 4 | 3 | 1620 | 5 | 0.85714 | 5 | -0.095816 | 0.0081542
Lucius Spar | 6 | 1 | 2 | 1 | 155000 | 4 | 4 | 3 | 2165 | 4 | 0.51613 | 5 | 0.14002 | 0.008273
Medusa Spar | 6 | 2 | 2 | 1 | 58333.3333 | 2 | 3 | 3 | 675 | 1 | 0.68571 | 1 | 0.74266 | 0.365
Gulfstar 1 | 6 | 1 | 1 | 1 | 109166.6667 | 3 | 2 | 3 | 1310 | 2 | 0.73282 | 3 | 0.12191 | 0.30435
Devil's Tower Spar | 6 | 3 | 1 | 1 | 66666.6667 | 2 | 2 | 3 | 1710 | 2 | 0.9 | 1 | 0.41949 | 0.06
Kikeh Spar | 2 | 5 | 2 | 1 | 142500 | 3 | 4 | 3 | 1330 | 1 | 0.84 | 4 | -0.015974 | 0.28571
Kizomba A Wellhead TLP | 1 | 4 | 2 | 1 | 250000 | 6 | 1 | 1 | 1175 | 3 | 1 | 2 | 0.0055918 | 0.13333
Kizomba B Wellhead TLP | 1 | 3 | 2 | 1 | 250000 | 6 | 1 | 1 | 1250 | 5 | 1 | 2 | -0.14006 | 0.13333
Okume TLP | 1 | 2 | 2 | 1 | 30000 | 1 | 1 | 1 | 500 | 4 | 0.83333 | 4 | 0.04 | 0
Oveng TLP | 1 | 2 | 2 | 1 | 30000 | 1 | 1 | 1 | 280 | 4 | 0.83333 | 4 | 0.04 | 0
P 61 Wellhead TLP | 7 | 5 | 2 | 1 | 145833.3333 | 3 | 3 | 1 | 1180 | 1 | 0.96 | 2 | 0.35051 | 0
Auger TLP | 6 | 2 | 2 | 1 | 65000 | 2 | 4 | 1 | 870 | 2 | 0.61538 | 4 | 0.044607 | 0.38947
Magnolia TLP | 6 | 1 | 2 | 1 | 75000 | 2 | 4 | 1 | 1432 | 2 | 0.66667 | 5 | 0.038462 | 0
Brutus TLP | 6 | 1 | 2 | 1 | 155000 | 4 | 2 | 1 | 910 | 4 | 0.83871 | 4 | 0.038576 | 0.078947
Stampede TLP | 6 | 1 | 2 | 1 | 86666.6667 | 2 | 1 | 1 | 1160 | 4 | 0.92308 | 5 | -0.1221 | -0.12903
Neptune TLP | 6 | 2 | 2 | 1 | 58333.3333 | 2 | 2 | 1 | 1300 | 2 | 0.85714 | 4 | 0.2345 | 0.47882
Shenzi TLP | 6 | 2 | 2 | 1 | 116666.6667 | 3 | 2 | 1 | 1333 | 2 | 0.85714 | 5 | -0.088472 | 0
Mars TLP | 6 | 1 | 2 | 1 | 230833.3333 | 5 | 2 | 1 | 896 | 4 | 0.86643 | 4 | -0.090164 | -0.054167
Olympus TLP | 6 | 1 | 2 | 1 | 116666.6667 | 3 | 2 | 1 | 945 | 5 | 0.85714 | 5 | -0.12562 | 0
Ursa TLP | 6 | 1 | 2 | 1 | 216666.6667 | 5 | 3 | 1 | 1160 | 5 | 0.69231 | 4 | -0.081731 | 0.043448
Ram Powell TLP | 6 | 1 | 2 | 1 | 93333.3333 | 2 | 3 | 1 | 990 | 5 | 0.64286 | 4 | 0.015301 | 0
Big Foot | 6 | 4 | 2 | 1 | 79166.6667 | 2 | 5 | 1 | 1580 | 1 | 0.94737 | 5 | 0.94899 | 0.275
Heidrun TLP | 5 | 1 | 2 | 1 | 283333.3333 | 6 | 2 | 1 | 350 | 2 | 0.88235 | 5 | 0.039406 | 0.076923
Malikai TLP | 2 | 5 | 2 | 1 | 68333.3333 | 2 | 2 | 1 | 470 | 3 | 0.87805 | 5 | 0.36796 | 0.077973

## Cost
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun
Bohai Ming Zhu | 8 | 5 | 2 | 2 | 1 | 4350 | 3 | 259 | 0.4 | 1 | 40000 | 1 | 2 | 4 | 30 | 1 | 1 | 1 | 0.47104 | 0.25
Petrojarl Varg | 5 | 1 | 1 | 1 | 1 | 2240 | 3 | 816 | 0.46 | 1 | 65833.3333 | 2 | 2 | 4 | 84 | 1 | 0.86582 | 2 | 0.28676 | 0.24
Stybarrow Venture MV16 | 4 | 3 | 3 | 1 | 3 | 5922 | 3 | 702 | 0.59843 | 1 | 87500 | 2 | 3 | 4 | 825 | 2 | 0.91429 | 4 | -0.14387 | 0.27
Alima FPU | 1 | 2 | 3 | 2 | 1 | 5720 | 3 | 994 | 1.133 | 1 | 100000 | 3 | 1 | 2 | 600 | 3 | 0.9 | 4 | -0.022133 | 0.35
Jangkrik | 2 | 4 | 1 | 2 | 1 | 8824 | 3 | 1052 | 2.6765 | 1 | 79400 | 2 | 2 | 2 | 120 | 2 | 0.055416 | 3 | 0.11407 | 0.17
Prelude | 4 | 3 | 3 | 2 | 1 | 7814 | 3 | 2229 | 11.16 | 1 | 148333.3333 | 6 | 5 | 5 | 250 | 1 | 0.23596 | 5 | 0.24316 | 0.34409
CLOV FPSO | 1 | 3 | 3 | 2 | 1 | 7534 | 3 | 1383 | 1.8 | 1 | 198333.3333 | 4 | 2 | 4 | 1290 | 4 | 0.80672 | 5 | 0.0079537 | 0.055556
Dalia | 1 | 4 | 3 | 2 | 1 | 4872 | 3 | 1306 | 3.4 | 1 | 287000 | 6 | 3 | 4 | 1360 | 5 | 0.83624 | 2 | 0.01072 | 0.17647
Girassol | 1 | 4 | 3 | 2 | 1 | 3103 | 3 | 823 | 2.5 | 1 | 246666.6667 | 5 | 3 | 4 | 1350 | 1 | 0.81081 | 1 | 0.52126 | 0.12
Kizomba B | 1 | 3 | 3 | 2 | 1 | 4756 | 3 | 1071 | 0.76 | 1 | 316666.6667 | 6 | 1 | 4 | 1250 | 5 | 0.78947 | 2 | -0.14006 | 0.13333
Mondo | 1 | 4 | 3 | 1 | 1 | 5866 | 3 | 797 | 0.75 | 2 | 115833.3333 | 3 | 1 | 4 | 728 | 3 | 0.86331 | 3 | -0.10163 | 0
Saxi-Batuque | 1 | 4 | 3 | 1 | 3 | 5866 | 3 | 797 | 0.75 | 2 | 130000 | 3 | 1 | 4 | 720 | 3 | 0.80769 | 3 | -0.084065 | 0
Greater Plutonio | 1 | 3 | 3 | 2 | 1 | 5144 | 3 | 1124 | 1.73 | 1 | 305000 | 6 | 3 | 4 | 1350 | 2 | 0.81967 | 5 | 0.19039 | 0.85
PSVM FPSO | 1 | 5 | 3 | 2 | 1 | 6755 | 3 | 1249 | 10 | 2 | 197833.3333 | 4 | 5 | 4 | 2000 | 2 | 0.7936 | 1 | 0.29704 | 0.4
Baobab Ivoirien MV10 | 1 | 1 | 1 | 1 | 3 | 4949 | 3 | 711 | 1.5 | 2 | 82500 | 2 | 1 | 4 | 970 | 3 | 0.84848 | 2 | 0.067511 | 0
Prof. John Evans Atta Mills | 1 | 4 | 3 | 1 | 3 | 8617 | 3 | 1092 | 5 | 2 | 108333.3333 | 3 | 1 | 4 | 1425 | 2 | 0.73846 | 5 | 0.015568 | 0
Agbami | 1 | 2 | 3 | 2 | 2 | 5539 | 3 | 1126 | 4.1538 | 1 | 325000 | 6 | 2 | 4 | 1433 | 2 | 0.76923 | 2 | 0.11368 | 0.3
Akpo | 1 | 4 | 3 | 2 | 1 | 5606 | 4 | 1303 | 2.345 | 1 | 273333.3333 | 6 | 2 | 4 | 1325 | 1 | 0.67683 | 3 | 0.072141 | 1.55
Bonga | 1 | 4 | 3 | 2 | 1 | 4049 | 3 | 1033 | 2.4 | 1 | 253333.3333 | 6 | 3 | 4 | 1250 | 1 | 0.88816 | 3 | 0.70765 | 0.5
Egina FPSO | 1 | 5 | 3 | 2 | 1 | 8540 | 3 | 1595 | 16 | 1 | 260000 | 6 | 2 | 4 | 1600 | 3 | 0.76923 | 2 | 0.28715 | -0.09375
Erha | 1 | 4 | 3 | 2 | 1 | 4671 | 3 | 1081 | 2.6 | 1 | 266666.6667 | 6 | 2 | 4 | 1180 | 2 | 0.7875 | 2 | 0.19334 | 0.57
Kizomba A | 1 | 3 | 3 | 2 | 1 | 4253 | 3 | 1073 | 0.77 | 1 | 316666.6667 | 6 | 2 | 4 | 1250 | 3 | 0.78947 | 2 | 0.0055918 | 0.13333
Ichthys Venturer | 4 | 4 | 3 | 2 | 1 | 8102 | 3 | 1743 | 2 | 1 | 85000 | 2 | 5 | 4 | 250 | 2 | 1 | 5 | 0.37636 | 0.32353
Pyrenees Venture | 4 | 3 | 3 | 2 | 2 | 6379 | 3 | 1014 | 1.66 | 2 | 106000 | 3 | 4 | 4 | 200 | 4 | 0.90566 | 5 | 0.0019724 | 0.012028
Ngujima Yin | 4 | 3 | 3 | 2 | 1 | 5993 | 3 | 716 | 0.72 | 2 | 136666.6667 | 3 | 2 | 4 | 340 | 2 | 0.87805 | 4 | 0.14665 | 0.33333
P 50 | 7 | 4 | 2 | 2 | 1 | 4557 | 2 | 844 | 0.496 | 2 | 215000 | 5 | 1 | 4 | 1240 | 4 | 0.83721 | 1 | 0.66351 | 0.41129
P 43 | 7 | 5 | 2 | 2 | 1 | 4199 | 4 | 883 | 1.3 | 2 | 185000 | 4 | 1 | 4 | 800 | 4 | 0.81081 | 1 | 0.43828 | 0.38462
P 48 | 7 | 5 | 2 | 2 | 1 | 4199 | 4 | 1066 | 1.3 | 2 | 185000 | 4 | 1 | 4 | 1040 | 2 | 0.81081 | 1 | 0.25516 | 0.38462
Frade | 7 | 3 | 3 | 2 | 1 | 6014 | 3 | 909 | 2 | 2 | 117666.6667 | 3 | 2 | 4 | 1080 | 1 | 0.84986 | 5 | 0.20902 | 1.35
P 57 | 7 | 5 | 2 | 1 | 2 | 6622 | 3 | 1041 | 1.195 | 2 | 191833.3333 | 4 | 1 | 4 | 1300 | 4 | 0.93831 | 1 | -0.045149 | 0.0041841
Pioneiro de Libra | 7 | 5 | 2 | 1 | 3 | 8984 | 1 | 831 | 1 | 2 | 73333.3333 | 2 | 1 | 4 | 2200 | 5 | 0.68182 | 1 | 0.45728 | 0.59441
P 63 | 7 | 5 | 2 | 2 | 1 | 7213 | 3 | 1383 | 1.3 | 2 | 145833.3333 | 3 | 1 | 4 | 1170 | 2 | 0.96 | 2 | 0.086768 | 0.25385
Espirito Santo | 7 | 5 | 3 | 1 | 3 | 6153 | 3 | 787 | 1.5086 | 2 | 105000 | 3 | 5 | 4 | 1780 | 1 | 0.95238 | 3 | 0.24778 | 1.32
P 54 | 7 | 5 | 2 | 2 | 1 | 5272 | 3 | 1034 | 0.629 | 2 | 215000 | 5 | 2 | 4 | 1315 | 5 | 0.83721 | 1 | 0.24468 | 0.97138
Cidade de Campos dos Goytacazes MV29 | 7 | 4 | 2 | 1 | 3 | 9101 | 3 | 1018 | 1.263 | 2 | 179500 | 4 | 2 | 4 | 765 | 4 | 0.83565 | 1 | 0.27898 | 0.0055424
Terra Nova | 3 | 2 | 1 | 2 | 1 | 2800 | 3 | 1157 | 1.3 | 1 | 175000 | 4 | 5 | 4 | 90 | 1 | 0.85714 | 2 | 0.39412 | 0.30769
Sea Rose | 3 | 3 | 1 | 2 | 1 | 4476 | 3 | 1229 | 0.49 | 1 | 125000 | 3 | 5 | 4 | 120 | 1 | 0.8 | 4 | 0.072417 | 0.2
Turritella | 6 | 1 | 1 | 2 | 1 | 8528 | 3 | 1149 | 1 | 2 | 62500 | 2 | 4 | 4 | 2900 | 2 | 0.96 | 5 | 0.11227 | 0.311
Asgard A | 5 | 3 | 1 | 2 | 1 | 2356 | 4 | 870 | 5.2941 | 1 | 300000 | 6 | 4 | 4 | 300 | 1 | 0.66667 | 3 | 0.20805 | 0.36
Balder | 5 | 3 | 3 | 2 | 1 | 1826 | 4 | 592 | 0.35 | 1 | 90500 | 2 | 5 | 4 | 125 | 1 | 0.91713 | 1 | 1.9291 | 0.62
Goliat FPSO | 5 | 2 | 1 | 2 | 1 | 7218 | 3 | 1364 | 3.9 | 1 | 122500 | 3 | 5 | 4 | 400 | 1 | 0.81633 | 4 | 0.72361 | 0.52
Petrojarl Knarr | 5 | 2 | 1 | 1 | 3 | 7850 | 3 | 732 | 1.6119 | 1 | 70833.3333 | 2 | 2 | 4 | 410 | 2 | 0.88941 | 4 | 0.85656 | 0.36975
Norne | 5 | 2 | 1 | 2 | 1 | 1551 | 3 | 1334 | 4.7 | 1 | 261666.6667 | 6 | 4 | 4 | 380 | 3 | 0.84076 | 4 | -0.12519 | 0.6
Skarv | 5 | 2 | 3 | 2 | 1 | 6240 | 3 | 1245 | 5 | 1 | 167500 | 4 | 4 | 4 | 370 | 1 | 0.47761 | 4 | 0.73494 | 0.7
Glen Lyon | 5 | 3 | 3 | 2 | 1 | 7729 | 3 | 1949 | 4.78 | 1 | 166666.6667 | 4 | 2 | 4 | 424 | 1 | 0.78 | 4 | 0.16675 | 0.19247
Western Isles FPSO | 5 | 1 | 1 | 2 | 1 | 8391 | 3 | 952 | 1.6 | 1 | 40000 | 1 | 3 | 4 | 165 | 2 | 1 | 3 | 0.8792 | 0.25
Belanak Natuna | 2 | 4 | 3 | 2 | 1 | 4250 | 4 | 1137 | 1.6 | 1 | 158333.3333 | 4 | 4 | 4 | 100 | 2 | 0.63158 | 4 | 0.058927 | 0.078167
Kikeh FPSO | 2 | 5 | 1 | 1 | 3 | 5513 | 3 | 939 | 0.8 | 2 | 143500 | 3 | 2 | 4 | 1350 | 1 | 0.83624 | 4 | -0.015974 | 0.2
Song Doc Pride MV 19 | 2 | 1 | 2 | 1 | 1 | 6339 | 3 | 417 | 0.25 | 2 | 30000 | 1 | 1 | 4 | 55 | 2 | 1 | 1 | 0.35012 | 0.04087
Thai Binh Vn | 2 | 1 | 2 | 2 | 1 | 4446 | 3 | 611 | 0.714 | 1 | 68333.3333 | 2 | 1 | 4 | 48 | 2 | 0.95122 | 3 | 0.037643 | 0.044
Hai Yang Shi You 117 | 8 | 4 | 2 | 2 | 1 | 5524 | 3 | 897 | 1.8 | 1 | 190000 | 4 | 1 | 4 | 27 | 1 | 1 | 3 | 0.72798 | 0.38889
Hai Yang Shi You 116 | 8 | 1 | 2 | 2 | 1 | 5804 | 3 | 723 | 1.2 | 1 | 106000 | 3 | 1 | 4 | 125 | 1 | 1 | 1 | 0.3195 | 0.98
Unity | 1 | 4 | 3 | 2 | 1 | 4018 | 3 | 545 | 1 | 1 | 125000 | 3 | 2 | 6 | 65 | 3 | 1 | 2 | 0.70092 | 0.4
Yoho | 1 | 3 | 3 | 2 | 1 | 4196 | 3 | 505 | 1.2 | 2 | 90000 | 2 | 2 | 6 | 56 | 1 | 1 | 1 | 0.20792 | 0.083333
Yoho | 1 | 3 | 3 | 2 | 1 | 4623 | 3 | 761 | 1.2 | 2 | 116666.6667 | 3 | 2 | 6 | 56 | 3 | 0.85714 | 2 | 0.6636 | 0.083333
Hanne Knutsen | 5 | 2 | 3 | 1 | 3 | 8124 | 3 | 1691 | 2.8649 | 2 | 100000 | 3 | 2 | 6 | 115 | 1 | 1 | 2 | 0.80958 | 0.85
Ailsa FSO | 5 | 2 | 3 | 2 | 1 | 9389 | 3 | 1364 | 4.7 | 1 | 108333.3333 | 3 | 2 | 6 | 90 | 5 | 0.23077 | 5 | 0 | 0
Gagak Rimang | 2 | 5 | 3 | 2 | 1 | 7891 | 3 | 1110 | 1.2 | 2 | 165000 | 4 | 2 | 6 | 33 | 1 | 1 | 3 | 0.42973 | 1.1667
Rang Dong MV17 | 2 | 1 | 2 | 1 | 3 | 6038 | 3 | 763 | 0.5 | 1 | 60000 | 2 | 1 | 6 | 60 | 2 | 1 | 1 | 0.10747 | 0.04087
Ichthys Explorer | 4 | 4 | 1 | 2 | 1 | 8046 | 3 | 1810 | 3 | 1 | 361166.6667 | 6 | 4 | 7 | 250 | 2 | 0.23535 | 5 | 0.35635 | 0.32353
P 51 | 7 | 5 | 2 | 2 | 1 | 5201 | 3 | 1418 | 0.83 | 1 | 215000 | 5 | 2 | 7 | 1250 | 5 | 0.83721 | 1 | 0.24401 | 0.25
P 56 | 7 | 5 | 2 | 2 | 1 | 6478 | 3 | 1114 | 1.4 | 1 | 135000 | 3 | 1 | 7 | 1670 | 5 | 0.74074 | 1 | 0.27379 | 0.071429
P 52 | 7 | 5 | 2 | 1 | 3 | 5060 | 3 | 1237 | 0.906 | 1 | 235000 | 5 | 2 | 7 | 1850 | 3 | 0.76596 | 1 | 0.19644 | 0.43488
Atlantis | 6 | 2 | 3 | 2 | 1 | 4533 | 3 | 1492 | 2.5 | 1 | 230000 | 5 | 2 | 7 | 2145 | 4 | 0.86957 | 1 | 0.60389 | 1.35
Delta House (Opti-Ex II) | 6 | 1 | 1 | 2 | 1 | 8158 | 3 | 1093 | 2 | 1 | 140000 | 3 | 2 | 7 | 1372 | 5 | 0.71429 | 2 | -0.012809 | 0
Blind Faith | 6 | 1 | 3 | 2 | 1 | 5802 | 3 | 846 | 1.151 | 1 | 52500 | 2 | 2 | 7 | 2130 | 1 | 0.85714 | 5 | 0.28605 | 0.95
Thunder Hawk | 6 | 1 | 1 | 1 | 3 | 6086 | 3 | 958 | 0.8 | 1 | 56666.6667 | 2 | 1 | 7 | 1847 | 4 | 0.79412 | 5 | 0.087683 | 0
Thunder Horse | 6 | 2 | 3 | 2 | 1 | 4624 | 3 | 1098 | 5 | 1 | 283333.3333 | 6 | 5 | 7 | 1830 | 1 | 0.88235 | 5 | 0.92623 | 2.68
Jack / St. Malo Semi | 6 | 1 | 3 | 2 | 1 | 7270 | 3 | 1844 | 7.5 | 1 | 177166.6667 | 4 | 1 | 7 | 2134 | 4 | 0.95955 | 5 | -0.005423 | 0
Asgard B | 5 | 4 | 1 | 2 | 1 | 2356 | 4 | 1570 | 1.3 | 1 | 351666.6667 | 6 | 1 | 7 | 300 | 5 | 0.38389 | 4 | 0 | 0
Gjoa | 5 | 2 | 1 | 2 | 1 | 6025 | 2 | 1461 | 4.4361 | 1 | 108333.3333 | 3 | 4 | 7 | 380 | 1 | 0.46154 | 4 | 0.08898 | 0.33
Kristin | 5 | 4 | 1 | 2 | 1 | 4368 | 3 | 1384 | 1.9 | 1 | 128000 | 3 | 5 | 7 | 370 | 1 | 0.97656 | 2 | 0.023844 | 0.73684
Snorre B | 5 | 4 | 1 | 2 | 1 | 3256 | 3 | 943 | 1.2821 | 1 | 115000 | 3 | 1 | 7 | 310 | 4 | 1 | 2 | -0.064687 | 0.17
Troll B | 5 | 3 | 1 | 2 | 1 | 379 | 3 | 1263 | 2.9 | 1 | 317000 | 6 | 5 | 7 | 320 | 2 | 0.85174 | 3 | 0.35234 | 0.14
Visund | 5 | 5 | 1 | 2 | 1 | 2251 | 4 | 851 | 0.7 | 1 | 171333.3333 | 4 | 5 | 7 | 335 | 1 | 0.65953 | 2 | 0.3396 | 0.45
Gumusut Semi | 2 | 5 | 3 | 1 | 3 | 6588 | 3 | 1233 | 1.6 | 1 | 200000 | 5 | 2 | 7 | 1220 | 3 | 0.75 | 3 | 0.99919 | 0.25
Front Runner Spar | 6 | 2 | 1 | 2 | 1 | 4459 | 4 | 728 | 0.2 | 1 | 78333.3333 | 2 | 3 | 3 | 1015 | 1 | 0.76596 | 1 | 0.36676 | 0.075
Tahiti Spar | 6 | 2 | 3 | 2 | 1 | 5597 | 3 | 1159 | 3.5 | 1 | 136666.6667 | 3 | 3 | 3 | 1280 | 2 | 0.91463 | 2 | 0.26747 | 1.8
Mad Dog | 6 | 1 | 3 | 2 | 1 | 4070 | 3 | 1397 | 1.82 | 1 | 66666.6667 | 2 | 2 | 3 | 1370 | 1 | 0.9 | 4 | 0.022906 | 0.1
Heidelberg Spar | 6 | 1 | 1 | 2 | 1 | 8018 | 3 | 1649 | 6.745 | 1 | 93333.3333 | 2 | 4 | 3 | 1620 | 5 | 0.85714 | 5 | -0.095816 | 0.0081542
Lucius Spar | 6 | 1 | 1 | 2 | 1 | 8002 | 3 | 1007 | 7.736 | 1 | 155000 | 4 | 4 | 3 | 2165 | 4 | 0.51613 | 5 | 0.14002 | 0.008273
Medusa Spar | 6 | 2 | 1 | 2 | 1 | 4077 | 4 | 579 | 0.2 | 1 | 58333.3333 | 2 | 3 | 3 | 675 | 1 | 0.68571 | 1 | 0.74266 | 0.365
Gulfstar 1 | 6 | 1 | 3 | 1 | 3 | 7813 | 3 | 1132 | 2.3 | 1 | 109166.6667 | 3 | 2 | 3 | 1310 | 2 | 0.73282 | 3 | 0.12191 | 0.30435
Devil's Tower Spar | 6 | 3 | 1 | 1 | 3 | 4189 | 4 | 739 | 0.2 | 1 | 66666.6667 | 2 | 2 | 3 | 1710 | 2 | 0.9 | 1 | 0.41949 | 0.06
Kikeh Spar | 2 | 5 | 1 | 2 | 1 | 5513 | 3 | 939 | 0.5 | 1 | 142500 | 3 | 4 | 3 | 1330 | 1 | 0.84 | 4 | -0.015974 | 0.28571
Kizomba A Wellhead TLP | 1 | 4 | 3 | 2 | 1 | 4253 | 3 | 1073 | 0.65 | 1 | 250000 | 6 | 1 | 1 | 1175 | 3 | 1 | 2 | 0.0055918 | 0.13333
Kizomba B Wellhead TLP | 1 | 3 | 3 | 2 | 1 | 4756 | 3 | 1071 | 0.6 | 1 | 250000 | 6 | 1 | 1 | 1250 | 5 | 1 | 2 | -0.14006 | 0.13333
Okume TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.1425 | 1 | 30000 | 1 | 1 | 1 | 500 | 4 | 0.83333 | 4 | 0.04 | 0
Oveng TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.1425 | 1 | 30000 | 1 | 1 | 1 | 280 | 4 | 0.83333 | 4 | 0.04 | 0
P 61 Wellhead TLP | 7 | 5 | 2 | 2 | 1 | 7213 | 3 | 1475 | 1.07 | 1 | 145833.3333 | 3 | 3 | 1 | 1180 | 1 | 0.96 | 2 | 0.35051 | 0
Auger TLP | 6 | 2 | 3 | 2 | 1 | 287 | 3 | 1233 | 0.86364 | 1 | 65000 | 2 | 4 | 1 | 870 | 2 | 0.61538 | 4 | 0.044607 | 0.38947
Magnolia TLP | 6 | 1 | 3 | 2 | 1 | 4392 | 3 | 1040 | 0.6 | 1 | 75000 | 2 | 4 | 1 | 1432 | 2 | 0.66667 | 5 | 0.038462 | 0
Brutus TLP | 6 | 1 | 3 | 2 | 1 | 3570 | 3 | 674 | 0.76 | 1 | 155000 | 4 | 2 | 1 | 910 | 4 | 0.83871 | 4 | 0.038576 | 0.078947
Stampede TLP | 6 | 1 | 1 | 2 | 1 | 8523 | 3 | 1982 | 6.2 | 1 | 86666.6667 | 2 | 1 | 1 | 1160 | 4 | 0.92308 | 5 | -0.1221 | -0.12903
Neptune TLP | 6 | 2 | 1 | 2 | 1 | 5670 | 3 | 887 | 0.85 | 1 | 58333.3333 | 2 | 2 | 1 | 1300 | 2 | 0.85714 | 4 | 0.2345 | 0.47882
Shenzi TLP | 6 | 2 | 1 | 2 | 1 | 6001 | 3 | 1119 | 4.41 | 1 | 116666.6667 | 3 | 2 | 1 | 1333 | 2 | 0.85714 | 5 | -0.088472 | 0
Mars TLP | 6 | 1 | 3 | 2 | 1 | 1381 | 3 | 1098 | 1.2 | 1 | 230833.3333 | 5 | 2 | 1 | 896 | 4 | 0.86643 | 4 | -0.090164 | -0.054167
Olympus TLP | 6 | 1 | 3 | 2 | 1 | 7729 | 3 | 1202 | 3 | 1 | 116666.6667 | 3 | 2 | 1 | 945 | 5 | 0.85714 | 5 | -0.12562 | 0
Ursa TLP | 6 | 1 | 3 | 2 | 1 | 2398 | 3 | 1040 | 1.45 | 1 | 216666.6667 | 5 | 3 | 1 | 1160 | 5 | 0.69231 | 4 | -0.081731 | 0.043448
Ram Powell TLP | 6 | 1 | 3 | 2 | 1 | 1885 | 3 | 915 | 1 | 1 | 93333.3333 | 2 | 3 | 1 | 990 | 5 | 0.64286 | 4 | 0.015301 | 0
Big Foot | 6 | 4 | 3 | 2 | 1 | 7571 | 3 | 1529 | 4 | 1 | 79166.6667 | 2 | 5 | 1 | 1580 | 1 | 0.94737 | 5 | 0.94899 | 0.275
Heidrun TLP | 5 | 1 | 1 | 2 | 1 | 504 | 3 | 1548 | 3.9 | 1 | 283333.3333 | 6 | 2 | 1 | 350 | 2 | 0.88235 | 5 | 0.039406 | 0.076923
Malikai TLP | 2 | 5 | 3 | 2 | 1 | 8439 | 3 | 1030 | 1.2825 | 1 | 68333.3333 | 2 | 2 | 1 | 470 | 3 | 0.87805 | 5 | 0.36796 | 0.077973

## Cost_T1
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun | 18 | 11 | 7 | Error(18) | Error(11) | Error(7)
Bohai Ming Zhu | 8 | 5 | 2 | 2 | 1 | 4350 | 3 | 259 | 0.4 | 1 | 40000 | 1 | 2 | 1 | 30 | 1 | 1 | 1 | 0.47104 | 25% | 31.71% | 35.27% | 37.46% | -26.84% | -41.09% | -49.84%
Petrojarl Varg | 5 | 1 | 1 | 1 | 1 | 2240 | 3 | 816 | 0.46 | 1 | 65833 | 2 | 2 | 1 | 84 | 1 | 0.8658 | 2 | 0.28676 | 24% | 31.19% | 21.19% | 26.46% | -29.97% | 11.71% | -10.26%
Stybarrow Venture MV16 | 4 | 3 | 3 | 1 | 3 | 5922 | 3 | 702 | 0.6 | 1 | 87500 | 2 | 3 | 1 | 825 | 2 | 0.9143 | 4 | -0.14387 | 27% | 30.61% | 17.37% | 14.14% | -13.39% | 35.66% | 47.62%
Alima FPU | 1 | 2 | 3 | 2 | 1 | 5720 | 3 | 994 | 1.13 | 1 | 100000 | 3 | 1 | 2 | 600 | 3 | 0.9 | 4 | -0.022133 | 35% | 30.67% | 10.46% | 9.701% | 12.38% | 70.1% | 72.28%
Jangkrik | 2 | 4 | 1 | 2 | 1 | 8824 | 3 | 1052 | 2.68 | 1 | 79400 | 2 | 2 | 2 | 120 | 2 | 0.0554 | 3 | 0.11407 | 17% | 30.67% | 17.55% | 25.08% | -80.39% | -3.233% | -47.5%
Prelude | 4 | 3 | 3 | 2 | 1 | 7814 | 3 | 2229 | 11.16 | 1 | 148333 | 6 | 5 | 6 | 250 | 1 | 0.236 | 5 | 0.24316 | 34.41% | 29.54% | 34.04% | 49.99% | 14.14% | 1.057% | -45.28%
CLOV FPSO | 1 | 3 | 3 | 2 | 1 | 7534 | 3 | 1383 | 1.8 | 1 | 198333 | 4 | 2 | 1 | 1290 | 4 | 0.8067 | 5 | 0.0079537 | 5.556% | 30.02% | 8.107% | 6.486% | -440.3% | -45.93% | -16.74%
Dalia | 1 | 4 | 3 | 2 | 1 | 4872 | 3 | 1306 | 3.4 | 1 | 287000 | 6 | 3 | 1 | 1360 | 5 | 0.8362 | 2 | 0.01072 | 17.65% | 29.74% | 7.906% | 6.066% | -68.52% | 55.2% | 65.63%
Girassol | 1 | 4 | 3 | 2 | 1 | 3103 | 3 | 823 | 2.5 | 1 | 246667 | 5 | 3 | 1 | 1350 | 1 | 0.8108 | 1 | 0.52126 | 12% | 30.57% | 31.31% | 23.23% | -154.8% | -160.9% | -93.62%
Kizomba B | 1 | 3 | 3 | 2 | 1 | 4756 | 3 | 1071 | 0.76 | 1 | 316667 | 6 | 1 | 1 | 1250 | 5 | 0.7895 | 2 | -0.14006 | 13.33% | 29.74% | 6.544% | 6.577% | -123% | 50.92% | 50.67%
Mondo | 1 | 4 | 3 | 1 | 1 | 5866 | 3 | 797 | 0.75 | 2 | 115833 | 3 | 1 | 1 | 728 | 3 | 0.8633 | 3 | -0.10163 | 0% | 30.39% | 8.882% | 6.173% | -30.39% | -8.882% | -6.173%
Saxi-Batuque | 1 | 4 | 3 | 1 | 3 | 5866 | 3 | 797 | 0.75 | 2 | 130000 | 3 | 1 | 1 | 720 | 3 | 0.8077 | 3 | -0.084065 | 0% | 30.56% | 8.927% | 6.173% | -30.56% | -8.927% | -6.173%
Greater Plutonio | 1 | 3 | 3 | 2 | 1 | 5144 | 3 | 1124 | 1.73 | 1 | 305000 | 6 | 3 | 1 | 1350 | 2 | 0.8197 | 5 | 0.19039 | 85% | 29.8% | 20.27% | 17.99% | 64.94% | 76.16% | 78.83%
PSVM FPSO | 1 | 5 | 3 | 2 | 1 | 6755 | 3 | 1249 | 10 | 2 | 197833 | 4 | 5 | 1 | 2000 | 2 | 0.7936 | 1 | 0.29704 | 40% | 30.57% | 34.35% | 10.1% | 23.57% | 14.12% | 74.75%
Baobab Ivoirien MV10 | 1 | 1 | 1 | 1 | 3 | 4949 | 3 | 711 | 1.5 | 2 | 82500 | 2 | 1 | 1 | 970 | 3 | 0.8485 | 2 | 0.067511 | 0% | 31.16% | 9.099% | 9.827% | -31.16% | -9.099% | -9.827%
Prof. John Evans Atta Mills | 1 | 4 | 3 | 1 | 3 | 8617 | 3 | 1092 | 5 | 2 | 108333 | 3 | 1 | 1 | 1425 | 2 | 0.7385 | 5 | 0.015568 | 0% | 30.35% | 9.395% | 8.773% | -30.35% | -9.395% | -8.773%
Agbami | 1 | 2 | 3 | 2 | 2 | 5539 | 3 | 1126 | 4.15 | 1 | 325000 | 6 | 2 | 1 | 1433 | 2 | 0.7692 | 2 | 0.11368 | 30% | 30% | 17.77% | 21.27% | 0.008341% | 40.78% | 29.11%
Akpo | 1 | 4 | 3 | 2 | 1 | 5606 | 4 | 1303 | 2.35 | 1 | 273333 | 6 | 2 | 1 | 1325 | 1 | 0.6768 | 3 | 0.072141 | 155% | 30.07% | 27.26% | 28.52% | 80.6% | 82.41% | 81.6%
Bonga | 1 | 4 | 3 | 2 | 1 | 4049 | 3 | 1033 | 2.4 | 1 | 253333 | 6 | 3 | 1 | 1250 | 1 | 0.8882 | 3 | 0.70765 | 50% | 30.22% | 31.46% | 25.92% | 39.56% | 37.09% | 48.15%
Egina FPSO | 1 | 5 | 3 | 2 | 1 | 8540 | 3 | 1595 | 16 | 1 | 260000 | 6 | 2 | 1 | 1600 | 3 | 0.7692 | 2 | 0.28715 | -9.375% | 29.61% | 8.902% | 12.76% | -29.61% | -8.902% | -12.76%
Erha | 1 | 4 | 3 | 2 | 1 | 4671 | 3 | 1081 | 2.6 | 1 | 266667 | 6 | 2 | 1 | 1180 | 2 | 0.7875 | 2 | 0.19334 | 57% | 30.11% | 20.48% | 19.67% | 47.18% | 64.06% | 65.49%
Kizomba A | 1 | 3 | 3 | 2 | 1 | 4253 | 3 | 1073 | 0.77 | 1 | 316667 | 6 | 2 | 1 | 1250 | 3 | 0.7895 | 2 | 0.0055918 | 13.33% | 29.96% | 14.85% | 15.24% | -124.7% | -11.39% | -14.27%
Ichthys Venturer | 4 | 4 | 3 | 2 | 1 | 8102 | 3 | 1743 | 2 | 1 | 85000 | 2 | 5 | 1 | 250 | 2 | 1 | 5 | 0.37636 | 32.35% | 30.7% | 22.7% | 18.56% | 5.097% | 29.82% | 42.63%
Pyrenees Venture | 4 | 3 | 3 | 2 | 2 | 6379 | 3 | 1014 | 1.66 | 2 | 106000 | 3 | 4 | 1 | 200 | 4 | 0.9057 | 5 | 0.0019724 | 1.203% | 30.67% | 12.12% | 8.764% | -2450% | -907.5% | -628.6%
Ngujima Yin | 4 | 3 | 3 | 2 | 1 | 5993 | 3 | 716 | 0.72 | 2 | 136667 | 3 | 2 | 1 | 340 | 2 | 0.878 | 4 | 0.14665 | 33.33% | 30.85% | 24.25% | 19.76% | 7.448% | 27.26% | 40.72%
P 50 | 7 | 4 | 2 | 2 | 1 | 4557 | 2 | 844 | 0.5 | 2 | 215000 | 5 | 1 | 1 | 1240 | 4 | 0.8372 | 1 | 0.66351 | 41.13% | 30.59% | 25.84% | 24.8% | 25.62% | 37.18% | 39.7%
P 43 | 7 | 5 | 2 | 2 | 1 | 4199 | 4 | 883 | 1.3 | 2 | 185000 | 4 | 1 | 1 | 800 | 4 | 0.8108 | 1 | 0.43828 | 38.46% | 30.76% | 24.57% | 26.7% | 20.02% | 36.11% | 30.57%
P 48 | 7 | 5 | 2 | 2 | 1 | 4199 | 4 | 1066 | 1.3 | 2 | 185000 | 4 | 1 | 1 | 1040 | 2 | 0.8108 | 1 | 0.25516 | 38.46% | 31.03% | 42.21% | 36.97% | 19.31% | -9.75% | 3.871%
Frade | 7 | 3 | 3 | 2 | 1 | 6014 | 3 | 909 | 2 | 2 | 117667 | 3 | 2 | 1 | 1080 | 1 | 0.8499 | 5 | 0.20902 | 135% | 30.97% | 37.01% | 27.19% | 77.06% | 72.58% | 79.86%
P 57 | 7 | 5 | 2 | 1 | 2 | 6622 | 3 | 1041 | 1.2 | 2 | 191833 | 4 | 1 | 1 | 1300 | 4 | 0.9383 | 1 | -0.045149 | 0.4184% | 30.25% | 16.07% | 17.74% | -7130% | -3741% | -4140%
Pioneiro de Libra | 7 | 5 | 2 | 1 | 3 | 8984 | 1 | 831 | 1 | 2 | 73333 | 2 | 1 | 1 | 2200 | 5 | 0.6818 | 1 | 0.45728 | 59.44% | 30.73% | 12.86% | 11.84% | 48.3% | 78.37% | 80.08%
P 63 | 7 | 5 | 2 | 2 | 1 | 7213 | 3 | 1383 | 1.3 | 2 | 145833 | 3 | 1 | 1 | 1170 | 2 | 0.96 | 2 | 0.086768 | 25.38% | 31.09% | 39.41% | 33.59% | -22.49% | -55.27% | -32.32%
Espirito Santo | 7 | 5 | 3 | 1 | 3 | 6153 | 3 | 787 | 1.51 | 2 | 105000 | 3 | 5 | 1 | 1780 | 1 | 0.9524 | 3 | 0.24778 | 132% | 30.8% | 48.68% | 17.35% | 76.67% | 63.12% | 86.86%
P 54 | 7 | 5 | 2 | 2 | 1 | 5272 | 3 | 1034 | 0.63 | 2 | 215000 | 5 | 2 | 1 | 1315 | 5 | 0.8372 | 1 | 0.24468 | 97.14% | 30.4% | 21.77% | 19.63% | 68.71% | 77.59% | 79.79%
Cidade de Campos dos Goytacazes MV29 | 7 | 4 | 2 | 1 | 3 | 9101 | 3 | 1018 | 1.26 | 2 | 179500 | 4 | 2 | 1 | 765 | 4 | 0.8357 | 1 | 0.27898 | 0.5542% | 30.12% | 17.23% | 17.38% | -5335% | -3009% | -3037%
Terra Nova | 3 | 2 | 1 | 2 | 1 | 2800 | 3 | 1157 | 1.3 | 1 | 175000 | 4 | 5 | 1 | 90 | 1 | 0.8571 | 2 | 0.39412 | 30.77% | 30.97% | 33.81% | 28.02% | -0.6647% | -9.88% | 8.924%
Sea Rose | 3 | 3 | 1 | 2 | 1 | 4476 | 3 | 1229 | 0.49 | 1 | 125000 | 3 | 5 | 1 | 120 | 1 | 0.8 | 4 | 0.072417 | 20% | 30.97% | 30.88% | 26.28% | -54.85% | -54.38% | -31.42%
Turritella | 6 | 1 | 1 | 2 | 1 | 8528 | 3 | 1149 | 1 | 2 | 62500 | 2 | 4 | 1 | 2900 | 2 | 0.96 | 5 | 0.11227 | 31.1% | 31.33% | 34.29% | 17.03% | -0.7391% | -10.25% | 45.23%
Asgard A | 5 | 3 | 1 | 2 | 1 | 2356 | 4 | 870 | 5.29 | 1 | 300000 | 6 | 4 | 1 | 300 | 1 | 0.6667 | 3 | 0.20805 | 36% | 30.14% | 29.01% | 32.51% | 16.27% | 19.4% | 9.706%
Balder | 5 | 3 | 3 | 2 | 1 | 1826 | 4 | 592 | 0.35 | 1 | 90500 | 2 | 5 | 1 | 125 | 1 | 0.9171 | 1 | 1.9291 | 62% | 31.5% | 40.17% | 30.21% | 49.19% | 35.21% | 51.28%
Goliat FPSO | 5 | 2 | 1 | 2 | 1 | 7218 | 3 | 1364 | 3.9 | 1 | 122500 | 3 | 5 | 1 | 400 | 1 | 0.8163 | 4 | 0.72361 | 52% | 30.77% | 28.57% | 30.05% | 40.83% | 45.07% | 42.22%
Petrojarl Knarr | 5 | 2 | 1 | 1 | 3 | 7850 | 3 | 732 | 1.61 | 1 | 70833 | 2 | 2 | 1 | 410 | 2 | 0.8894 | 4 | 0.85656 | 36.97% | 30.63% | 11.73% | 15.98% | 17.16% | 68.27% | 56.79%
Norne | 5 | 2 | 1 | 2 | 1 | 1551 | 3 | 1334 | 4.7 | 1 | 261667 | 6 | 4 | 1 | 380 | 3 | 0.8408 | 4 | -0.12519 | 60% | 30.14% | 12.9% | 12.99% | 49.76% | 78.5% | 78.35%
Skarv | 5 | 2 | 3 | 2 | 1 | 6240 | 3 | 1245 | 5 | 1 | 167500 | 4 | 4 | 1 | 370 | 1 | 0.4776 | 4 | 0.73494 | 70% | 30.34% | 25% | 28.82% | 56.65% | 64.29% | 58.82%
Glen Lyon | 5 | 3 | 3 | 2 | 1 | 7729 | 3 | 1949 | 4.78 | 1 | 166667 | 4 | 2 | 1 | 424 | 1 | 0.78 | 4 | 0.16675 | 19.25% | 30.45% | 20.82% | 28.71% | -58.19% | -8.191% | -49.15%
Western Isles FPSO | 5 | 1 | 1 | 2 | 1 | 8391 | 3 | 952 | 1.6 | 1 | 40000 | 1 | 3 | 1 | 165 | 2 | 1 | 3 | 0.8792 | 25% | 31.32% | 20.18% | 18.41% | -25.26% | 19.27% | 26.37%
Belanak Natuna | 2 | 4 | 3 | 2 | 1 | 4250 | 4 | 1137 | 1.6 | 1 | 158333 | 4 | 4 | 1 | 100 | 2 | 0.6316 | 4 | 0.058927 | 7.817% | 30.44% | 19.55% | 17.21% | -289.5% | -150.1% | -120.1%
Kikeh FPSO | 2 | 5 | 1 | 1 | 3 | 5513 | 3 | 939 | 0.8 | 2 | 143500 | 3 | 2 | 1 | 1350 | 1 | 0.8362 | 4 | -0.015974 | 20% | 30.82% | 22.84% | 14.1% | -54.08% | -14.21% | 29.48%
Song Doc Pride MV 19 | 2 | 1 | 2 | 1 | 1 | 6339 | 3 | 417 | 0.25 | 2 | 30000 | 1 | 1 | 1 | 55 | 2 | 1 | 1 | 0.35012 | 4.087% | 31.27% | 16.39% | 19.11% | -665.2% | -301% | -367.5%
Thai Binh Vn | 2 | 1 | 2 | 2 | 1 | 4446 | 3 | 611 | 0.71 | 1 | 68333 | 2 | 1 | 1 | 48 | 2 | 0.9512 | 3 | 0.037643 | 4.4% | 31.32% | 13.48% | 17.54% | -611.9% | -206.4% | -298.7%
Hai Yang Shi You 117 | 8 | 4 | 2 | 2 | 1 | 5524 | 3 | 897 | 1.8 | 1 | 190000 | 4 | 1 | 1 | 27 | 1 | 1 | 3 | 0.72798 | 38.89% | 30.66% | 29.08% | 33.18% | 21.16% | 25.23% | 14.67%
Hai Yang Shi You 116 | 8 | 1 | 2 | 2 | 1 | 5804 | 3 | 723 | 1.2 | 1 | 106000 | 3 | 1 | 1 | 125 | 1 | 1 | 1 | 0.3195 | 98% | 31.26% | 34.31% | 38.82% | 68.1% | 64.99% | 60.39%
Unity | 1 | 4 | 3 | 2 | 1 | 4018 | 3 | 545 | 1 | 1 | 125000 | 3 | 2 | 8 | 65 | 3 | 1 | 2 | 0.70092 | 40% | 30.41% | 23.84% | 29.37% | 23.98% | 40.4% | 26.57%
Yoho | 1 | 3 | 3 | 2 | 1 | 4196 | 3 | 505 | 1.2 | 2 | 0 | 1 | 2 | 8 | 56 | 1 | 1 | 1 | 0.20792 | 8.333% | 31.6% | 49.26% | 40.99% | -279.2% | -491.1% | -391.9%
Yoho | 1 | 3 | 3 | 2 | 1 | 4623 | 3 | 761 | 1.2 | 2 | 116667 | 3 | 2 | 8 | 56 | 3 | 0.8571 | 2 | 0.6636 | 8.333% | 30.6% | 35.56% | 26.97% | -267.2% | -326.7% | -223.6%
Hanne Knutsen | 5 | 2 | 3 | 1 | 3 | 8124 | 3 | 1691 | 2.86 | 2 | 100000 | 3 | 2 | 8 | 115 | 1 | 1 | 2 | 0.80958 | 85% | 30.36% | 43.93% | 46.22% | 64.29% | 48.32% | 45.63%
Ailsa FSO | 5 | 2 | 3 | 2 | 1 | 9389 | 3 | 1364 | 4.7 | 1 | 108333 | 3 | 2 | 8 | 90 | 5 | 0.2308 | 5 | 0 | 0% | 29.56% | 9.009% | 7.811% | -29.56% | -9.009% | -7.811%
Gagak Rimang | 2 | 5 | 3 | 2 | 1 | 7891 | 3 | 1110 | 1.2 | 2 | 0 | 1 | 2 | 8 | 33 | 1 | 1 | 3 | 0.42973 | 116.7% | 31.16% | 50.21% | 58.47% | 73.29% | 56.97% | 49.88%
Rang Dong MV17 | 2 | 1 | 2 | 1 | 3 | 6038 | 3 | 763 | 0.5 | 1 | 0 | 1 | 1 | 8 | 60 | 2 | 1 | 1 | 0.10747 | 4.087% | 30.84% | 22.47% | 26.44% | -654.6% | -449.9% | -547%
Ichthys Explorer | 4 | 4 | 1 | 2 | 1 | 8046 | 3 | 1810 | 3 | 1 | 361167 | 6 | 4 | 5 | 250 | 2 | 0.2353 | 5 | 0.35635 | 32.35% | 29.19% | 28.39% | 35.35% | 9.773% | 12.25% | -9.27%
P 51 | 7 | 5 | 2 | 2 | 1 | 5201 | 3 | 1418 | 0.83 | 1 | 215000 | 5 | 2 | 5 | 1250 | 5 | 0.8372 | 1 | 0.24401 | 25% | 29.95% | 18.44% | 27.13% | -19.81% | 26.25% | -8.506%
P 56 | 7 | 5 | 2 | 2 | 1 | 6478 | 3 | 1114 | 1.4 | 1 | 135000 | 3 | 1 | 5 | 1670 | 5 | 0.7407 | 1 | 0.27379 | 7.143% | 30.36% | 16.37% | 25.08% | -325% | -129.2% | -251.1%
P 52 | 7 | 5 | 2 | 1 | 3 | 5060 | 3 | 1237 | 0.91 | 1 | 235000 | 5 | 2 | 5 | 1850 | 3 | 0.766 | 1 | 0.19644 | 43.49% | 29.75% | 24.78% | 34.67% | 31.58% | 43.01% | 20.29%
Atlantis | 6 | 2 | 3 | 2 | 1 | 4533 | 3 | 1492 | 2.5 | 1 | 230000 | 5 | 2 | 5 | 2145 | 4 | 0.8696 | 1 | 0.60389 | 135% | 30.1% | 25.72% | 24.15% | 77.7% | 80.95% | 82.11%
Delta House (Opti-Ex II) | 6 | 1 | 1 | 2 | 1 | 8158 | 3 | 1093 | 2 | 1 | 140000 | 3 | 2 | 5 | 1372 | 5 | 0.7143 | 2 | -0.012809 | 0% | 30.24% | 14.35% | 13.07% | -30.24% | -14.35% | -13.07%
Blind Faith | 6 | 1 | 3 | 2 | 1 | 5802 | 3 | 846 | 1.15 | 1 | 52500 | 2 | 2 | 5 | 2130 | 1 | 0.8571 | 5 | 0.28605 | 95% | 30.96% | 38.64% | 36.06% | 67.41% | 59.33% | 62.04%
Thunder Hawk | 6 | 1 | 1 | 1 | 3 | 6086 | 3 | 958 | 0.8 | 1 | 56667 | 2 | 1 | 5 | 1847 | 4 | 0.7941 | 5 | 0.087683 | 0% | 30.34% | 7.917% | 7.189% | -30.34% | -7.917% | -7.189%
Thunder Horse | 6 | 2 | 3 | 2 | 1 | 4624 | 3 | 1098 | 5 | 1 | 283333 | 6 | 5 | 5 | 1830 | 1 | 0.8824 | 5 | 0.92623 | 268% | 29.67% | 42.53% | 42.95% | 88.93% | 84.13% | 83.97%
Jack / St. Malo Semi | 6 | 1 | 3 | 2 | 1 | 7270 | 3 | 1844 | 7.5 | 1 | 177167 | 4 | 1 | 5 | 2134 | 4 | 0.9595 | 5 | -0.005423 | 0% | 29.97% | 8.657% | 8.059% | -29.97% | -8.657% | -8.059%
Asgard B | 5 | 4 | 1 | 2 | 1 | 2356 | 4 | 1570 | 1.3 | 1 | 351667 | 6 | 1 | 5 | 300 | 5 | 0.3839 | 4 | 0 | 0% | 29.41% | 8.077% | 8.19% | -29.41% | -8.077% | -8.19%
Gjoa | 5 | 2 | 1 | 2 | 1 | 6025 | 2 | 1461 | 4.44 | 1 | 108333 | 3 | 4 | 5 | 380 | 1 | 0.4615 | 4 | 0.08898 | 33% | 30.6% | 40.16% | 43.18% | 7.278% | -21.69% | -30.85%
Kristin | 5 | 4 | 1 | 2 | 1 | 4368 | 3 | 1384 | 1.9 | 1 | 128000 | 3 | 5 | 5 | 370 | 1 | 0.9766 | 2 | 0.023844 | 73.68% | 30.9% | 47.49% | 49.13% | 58.07% | 35.55% | 33.32%
Snorre B | 5 | 4 | 1 | 2 | 1 | 3256 | 3 | 943 | 1.28 | 1 | 115000 | 3 | 1 | 5 | 310 | 4 | 1 | 2 | -0.064687 | 17% | 30.74% | 14.45% | 21.41% | -80.81% | 15.02% | -25.92%
Troll B | 5 | 3 | 1 | 2 | 1 | 379 | 3 | 1263 | 2.9 | 1 | 317000 | 6 | 5 | 5 | 320 | 2 | 0.8517 | 3 | 0.35234 | 14% | 29.99% | 40.16% | 36.79% | -114.2% | -186.8% | -162.8%
Visund | 5 | 5 | 1 | 2 | 1 | 2251 | 4 | 851 | 0.7 | 1 | 171333 | 4 | 5 | 5 | 335 | 1 | 0.6595 | 2 | 0.3396 | 45% | 30.62% | 48.49% | 42.79% | 31.95% | -7.747% | 4.918%
Gumusut Semi | 2 | 5 | 3 | 1 | 3 | 6588 | 3 | 1233 | 1.6 | 1 | 200000 | 5 | 2 | 5 | 1220 | 3 | 0.75 | 3 | 0.99919 | 25% | 29.54% | 17.24% | 9.776% | -18.17% | 31.05% | 60.9%
Front Runner Spar | 6 | 2 | 1 | 2 | 1 | 4459 | 4 | 728 | 0.2 | 1 | 78333 | 2 | 3 | 4 | 1015 | 1 | 0.766 | 1 | 0.36676 | 7.5% | 31.37% | 46.23% | 39.53% | -318.2% | -516.4% | -427.1%
Tahiti Spar | 6 | 2 | 3 | 2 | 1 | 5597 | 3 | 1159 | 3.5 | 1 | 136667 | 3 | 3 | 4 | 1280 | 2 | 0.9146 | 2 | 0.26747 | 180% | 30.68% | 36.1% | 29.76% | 82.96% | 79.94% | 83.47%
Mad Dog | 6 | 1 | 3 | 2 | 1 | 4070 | 3 | 1397 | 1.82 | 1 | 66667 | 2 | 2 | 4 | 1370 | 1 | 0.9 | 4 | 0.022906 | 10% | 31.24% | 36.7% | 33.88% | -212.4% | -267% | -238.8%
Heidelberg Spar | 6 | 1 | 1 | 2 | 1 | 8018 | 3 | 1649 | 6.75 | 1 | 93333 | 2 | 4 | 4 | 1620 | 5 | 0.8571 | 5 | -0.095816 | 0.8154% | 30.35% | 8.291% | 6.864% | -3622% | -916.8% | -741.8%
Lucius Spar | 6 | 1 | 1 | 2 | 1 | 8002 | 3 | 1007 | 7.74 | 1 | 155000 | 4 | 4 | 4 | 2165 | 4 | 0.5161 | 5 | 0.14002 | 0.8273% | 29.86% | 13.14% | 10.82% | -3509% | -1488% | -1208%
Medusa Spar | 6 | 2 | 1 | 2 | 1 | 4077 | 4 | 579 | 0.2 | 1 | 58333 | 2 | 3 | 4 | 675 | 1 | 0.6857 | 1 | 0.74266 | 36.5% | 31.39% | 45.84% | 39.53% | 13.99% | -25.59% | -8.298%
Gulfstar 1 | 6 | 1 | 3 | 1 | 3 | 7813 | 3 | 1132 | 2.3 | 1 | 109167 | 3 | 2 | 4 | 1310 | 2 | 0.7328 | 3 | 0.12191 | 30.43% | 30.15% | 21.23% | 21.46% | 0.9393% | 30.25% | 29.49%
Devil's Tower Spar | 6 | 3 | 1 | 1 | 3 | 4189 | 4 | 739 | 0.2 | 1 | 66667 | 2 | 2 | 4 | 1710 | 2 | 0.9 | 1 | 0.41949 | 6% | 30.96% | 29.25% | 36.68% | -416% | -387.5% | -511.3%
Kikeh Spar | 2 | 5 | 1 | 2 | 1 | 5513 | 3 | 939 | 0.5 | 1 | 0 | 1 | 4 | 4 | 1330 | 1 | 1 | 4 | -0.015974 | 28.57% | 31.43% | 45.11% | 36.88% | -10.01% | -57.89% | -29.08%
Kizomba A Wellhead TLP | 1 | 4 | 3 | 2 | 1 | 4253 | 3 | 1073 | 0.65 | 1 | 250000 | 6 | 1 | 3 | 1175 | 3 | 1 | 2 | 0.0055918 | 13.33% | 30.05% | 17.45% | 18.48% | -125.4% | -30.86% | -38.62%
Kizomba B Wellhead TLP | 1 | 3 | 3 | 2 | 1 | 4756 | 3 | 1071 | 0.6 | 1 | 250000 | 6 | 1 | 3 | 1250 | 5 | 1 | 2 | -0.14006 | 13.33% | 29.81% | 7.57% | 7.4% | -123.6% | 43.22% | 44.5%
Okume TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.14 | 1 | 30000 | 1 | 1 | 3 | 500 | 4 | 0.8333 | 4 | 0.04 | 0% | 31.1% | 7.89% | 6.006% | -31.1% | -7.89% | -6.006%
Oveng TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.14 | 1 | 30000 | 1 | 1 | 3 | 280 | 4 | 0.8333 | 4 | 0.04 | 0% | 31.09% | 7.6% | 6.006% | -31.09% | -7.6% | -6.006%
P 61 Wellhead TLP | 7 | 5 | 2 | 2 | 1 | 7213 | 3 | 1475 | 1.07 | 1 | 145833 | 3 | 3 | 3 | 1180 | 1 | 0.96 | 2 | 0.35051 | 0% | 30.81% | 42.04% | 36.72% | -30.81% | -42.04% | -36.72%
Auger TLP | 6 | 2 | 3 | 2 | 1 | 287 | 3 | 1233 | 0.86 | 1 | 65000 | 2 | 4 | 3 | 870 | 2 | 0.6154 | 4 | 0.044607 | 38.95% | 31.28% | 31.06% | 25.07% | 19.68% | 20.24% | 35.64%
Magnolia TLP | 6 | 1 | 3 | 2 | 1 | 4392 | 3 | 1040 | 0.6 | 1 | 75000 | 2 | 4 | 3 | 1432 | 2 | 0.6667 | 5 | 0.038462 | 0% | 30.9% | 27.68% | 21.95% | -30.9% | -27.68% | -21.95%
Brutus TLP | 6 | 1 | 3 | 2 | 1 | 3570 | 3 | 674 | 0.76 | 1 | 155000 | 4 | 2 | 3 | 910 | 4 | 0.8387 | 4 | 0.038576 | 7.895% | 30.3% | 11.15% | 8.927% | -283.8% | -41.21% | -13.08%
Stampede TLP | 6 | 1 | 1 | 2 | 1 | 8523 | 3 | 1982 | 6.2 | 1 | 86667 | 2 | 1 | 3 | 1160 | 4 | 0.9231 | 5 | -0.1221 | -12.9% | 30.65% | 6.624% | 6.435% | -30.65% | -6.624% | -6.435%
Neptune TLP | 6 | 2 | 1 | 2 | 1 | 5670 | 3 | 887 | 0.85 | 1 | 58333 | 2 | 2 | 3 | 1300 | 2 | 0.8571 | 4 | 0.2345 | 47.88% | 31.13% | 26.25% | 22.92% | 34.98% | 45.18% | 52.13%
Shenzi TLP | 6 | 2 | 1 | 2 | 1 | 6001 | 3 | 1119 | 4.41 | 1 | 116667 | 3 | 2 | 3 | 1333 | 2 | 0.8571 | 5 | -0.088472 | 0% | 30.69% | 19.31% | 21.27% | -30.69% | -19.31% | -21.27%
Mars TLP | 6 | 1 | 3 | 2 | 1 | 1381 | 3 | 1098 | 1.2 | 1 | 230833 | 5 | 2 | 3 | 896 | 4 | 0.8664 | 4 | -0.090164 | -5.417% | 30.17% | 10.85% | 8.927% | -30.17% | -10.85% | -8.927%
Olympus TLP | 6 | 1 | 3 | 2 | 1 | 7729 | 3 | 1202 | 3 | 1 | 116667 | 3 | 2 | 3 | 945 | 5 | 0.8571 | 5 | -0.12562 | 0% | 30.11% | 6.066% | 4.563% | -30.11% | -6.066% | -4.563%
Ursa TLP | 6 | 1 | 3 | 2 | 1 | 2398 | 3 | 1040 | 1.45 | 1 | 216667 | 5 | 3 | 3 | 1160 | 5 | 0.6923 | 4 | -0.081731 | 4.345% | 29.95% | 9.118% | 6.357% | -589.2% | -109.9% | -46.31%
Ram Powell TLP | 6 | 1 | 3 | 2 | 1 | 1885 | 3 | 915 | 1 | 1 | 93333 | 2 | 3 | 3 | 990 | 5 | 0.6429 | 4 | 0.015301 | 0% | 30.74% | 9.165% | 6.357% | -30.74% | -9.165% | -6.357%
Big Foot | 6 | 4 | 3 | 2 | 1 | 7571 | 3 | 1529 | 4 | 1 | 79167 | 2 | 5 | 3 | 1580 | 1 | 0.9474 | 5 | 0.94899 | 27.5% | 30.73% | 38.24% | 40.74% | -11.74% | -39.04% | -48.15%
Heidrun TLP | 5 | 1 | 1 | 2 | 1 | 504 | 3 | 1548 | 3.9 | 1 | 283333 | 6 | 2 | 3 | 350 | 2 | 0.8824 | 5 | 0.039406 | 7.692% | 30.22% | 14.9% | 19.63% | -292.8% | -93.71% | -155.2%
Malikai TLP | 2 | 5 | 3 | 2 | 1 | 8439 | 3 | 1030 | 1.28 | 1 | 68333 | 2 | 2 | 3 | 470 | 3 | 0.878 | 5 | 0.36796 | 7.797% | 30.46% | 13.9% | 15.64% | -290.7% | -78.22% | -100.6%

## Coding
| H | High | 5 |  | H | 5
| M | Medium | 4
| A | Average | 3
| L | Low | 2
| N | Negligible | 1
Schedule | OC | National Oil Company | 1 | Cost | OC | National Oil Company | 1
| IOC | International Oil Company | 2 |  | NOC | International Oil Company | 2
| NOC | Oil Company | 3 |  | IOC | Oil Company | 3
| EPC | Engineering, Procurement, Construction | 3
| TK | Turnkey | 4
| CL | Client as Integrator | 2
| PS | Production Sharing | 1
| BARGE | 1 |  |  | BARGE | 2
| FLNG | 4 |  |  | FLNG | 5
| FPSO | 5 |  |  | FPSO | 4
| FSO | 7 |  |  | FSO | 6
| SEMI | 6 |  |  | SEMI | 7
| SPAR | 3 |  |  | SPAR | 3
| TLP | 2 |  |  | TLP | 1
| FSO (LNG) | 8 |  |  | FSO (LNG) | 8
| MOPU | 9 |  |  | MOPU | 9
Schedule | AFRICA | 1 | Cost | AFRICA | 1
| SEA | 2 |  | SEA | 2
| GOM | 3 |  | CAN | 3
| AUST/NZ | 4 |  | AUST/NZ | 4
| CAN | 5 |  | NE | 5
| BRAZ | 6 |  | GOM | 6
| NE | 7 |  | BRAZ | 7
| SEA CH | 8 |  | SEA CH | 8
| Lease | 1
| Own | 2
H 1 = FOO & FOM – Field Operator Owned FPSO & Field Operator Managed FPSO
Schedule | 1 | H 2 = FOO & CM – Field Operator Owned & Contractor Managed FPSO
| 2 | H 3 = CO & CM – Contractor Owned FPSO & Contractor Managed FPSO
| 3 | H 4 = CO & FOM – Contractor Owned FPSO & Field Operator Managed FPSO
4
| NEW | 1
| CONV | 2
| VS | Very Small | 1
| S | Small | 2
| M | Medium | 3
| L | Large | 4
| VL | Very Large | 5
| UL | Ultra Large | 6

## Hydro
Schedule_Overrun | Cost_Overrun
402% | 416%
32% | 11%
33% | 63%
6% | 2%
21% | -7%
26% | -18%
0% | 50%
68% | 87%
58% | 101%
-29% | -3%
116% | 21%
21% | -2%
31% | -3%
10% | 12%
27% | 15%
60% | -20%
100% | 23%
49% | 200%
-22% | -51%
130% | 26%
56% | -17%
3% | 143%
-2% | -6%
325% | 513%
38% | 353%
32% | 88%
98% | -16%
147% | 402%

## Nuclear
Schedule_Overrun | Cost_Overrun
-0.15 | 0.81623
-0.083333 | 0.32827
0.78333 | 1.0097
1.25 | 2.0199
0.16667 | 0.044919
0.91667 | 1.5123
0.18333 | 2.1207
0.18333 | 0.92665
0 | 0.034501
0.35417 | 0.022218
0.35417 | 0.022218
0.35417 | 0.066663
0.35417 | 0.088881
0.18 | 0.96735
0 | 2.2701
0 | 0.10632
1.0167 | 1.7095
1.0333 | 4.3533
0.61667 | 1.4803
1.4 | 4.0992
0 | 0.29511
0.016667 | 0.74884

## Solar
Schedule_Overrun | Cost_Overrun
3% | -9%
-8% | 0%
0% | 31%
-3% | -2%
-10% | -19%
0% | -16%
-2% | 13%
0% | 5%
0% | 12%
-4% | 0%
0% | 13%
-4% | 8%
25% | -3%

## Thermal
Schedule_Overrun | Cost_Overrun
15% | 10%
-3% | -14%
0% | 120%
50% | 0%
0% | 4%
17% | 75%
46% | 75%
23% | 57%
17% | 31%
10% | 9%
9% | 9%
0% | 11%
0% | 9%
13% | 69%
0% | -17%
67% | -9%
-7% | -31%
-11% | -42%
0% | 15%
4% | 1%
0% | -50%
0% | 13%
0% | 14%
0% | 3%

## Wind
Schedule_Overrun | Cost_Overrun
0.1 | -0.0083871
0 | 0.35713
0.25 | 0.10088
0 | -0.0056899
-0.083333 | 0
0 | 0
0.6 | 0.21359
-0.19048 | 0
0.15 | 0.17699
-0.125 | 0.017319
0.5 | 0.064516
-0.052632 | 0
-0.1 | 0
0 | 0.0041494
0.2 | -0.021033
0.33333 | 0.065097
-0.15 | -0.0082372
0.28571 | -0.033708

## Transmission
Schedule_Overrun | Cost_Overrun
0% | 15%
0% | 21%
0% | 14%
0% | 18%
0% | 33%
0% | 33%
0% | 11%
0% | 0%
0% | -33%
0% | 13%
0% | -4%
0% | 71%
0% | 4%
0% | -11%
0% | -21%