## Cost_Sch1
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned Duration | Planned Cost billion USD | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED Detail (H,M,A,L,N) | Schedule overun | Cost Overrun
Lingshui Semi | SEA CH | H | NOC | Own | 1 | 10439 | EPC | 700 | 3.1 | NEW | 67166.6667 | S | L | SEMI | 980 | L | 0.14888 | M | 0.76 | Not Availible
Bohai Ming Zhu | SEA CH | H | NOC | Own | 1 | 4350 | EPC | 259 | 0.4 | NEW | 40000 | VS | L | FPSO | 30 | N | 1 | N | 0.47104 | 0.25
Petrojarl Varg | NE | N | OC | Lease | 1 | 2240 | EPC | 816 | 0.46 | NEW | 65833.3333 | S | L | FPSO | 84 | N | 0.86582 | L | 0.28676 | 0.24
Stybarrow Venture MV16 | AUST/NZ | A | IOC | Lease | 3 | 5922 | EPC | 702 | 0.59843 | NEW | 87500 | S | A | FPSO | 825 | L | 0.91429 | M | -0.14387 | 0.27
Alima FPU | AFRICA | L | IOC | Own | 1 | 5720 | EPC | 994 | 1.133 | NEW | 100000 | M | N | BARGE | 600 | A | 0.9 | M | -0.022133 | 0.35
Jangkrik | SEA | M | OC | Own | 1 | 8824 | EPC | 1052 | 2.6765 | NEW | 79400 | S | L | BARGE | 120 | L | 0.055416 | A | 0.11407 | 0.17
Prelude | AUST/NZ | A | IOC | Own | 1 | 7814 | EPC | 2229 | 11.16 | NEW | 148333.3333 | UL | H | FLNG | 250 | N | 0.23596 | H | 0.24316 | 0.34409
CLOV FPSO | AFRICA | A | IOC | Own | 1 | 7534 | EPC | 1383 | 7 | NEW | 198333.3333 | L | L | FPSO | 1290 | M | 0.80672 | H | 0.0079537 | 0.14286
Dalia | AFRICA | M | IOC | Own | 1 | 4872 | EPC | 1306 | 3.4 | NEW | 287000 | UL | A | FPSO | 1360 | H | 0.83624 | L | 0.01072 | 0.17647
Girassol | AFRICA | M | IOC | Own | 1 | 3103 | EPC | 823 | 2.5 | NEW | 246666.6667 | VL | A | FPSO | 1350 | N | 0.81081 | N | 0.52126 | 0.12
Kaombo Norte | AFRICA | H | IOC | Own | 1 | 8871 | EPC | 1081 | 1.5 | CONV | 131666.6667 | M | L | FPSO | 1600 | L | 0.87342 | A | 0.44773 | Not Availible
Kaombo Sul | AFRICA | H | IOC | Own | 1 | 8871 | EPC | 1173 | 1.5 | CONV | 131666.6667 | M | L | FPSO | 1600 | L | 0.87342 | A | 0.54646 | Not Availible
Kizomba B | AFRICA | A | IOC | Own | 1 | 4756 | EPC | 1071 | 0.76 | NEW | 316666.6667 | UL | N | FPSO | 1250 | H | 0.78947 | L | -0.14006 | 0.13333
Mondo | AFRICA | M | IOC | Lease | 1 | 5866 | EPC | 797 | 0.75 | CONV | 115833.3333 | M | N | FPSO | 728 | A | 0.86331 | A | -0.10163 | 0
Saxi-Batuque | AFRICA | M | IOC | Lease | 3 | 5866 | EPC | 797 | 0.75 | CONV | 130000 | M | N | FPSO | 720 | A | 0.80769 | A | -0.084065 | 0
Greater Plutonio | AFRICA | A | IOC | Own | 1 | 5144 | EPC | 1124 | 1.73 | NEW | 305000 | UL | A | FPSO | 1350 | L | 0.81967 | M | 0.19039 | 0.85
PSVM FPSO | AFRICA | H | IOC | Own | 1 | 6755 | EPC | 1249 | 10 | CONV | 197833.3333 | L | H | FPSO | 2000 | L | 0.7936 | N | 0.29704 | 0.4
Sanha LPG | AFRICA | N | IOC | Own | 1 | 4687 | EPC | 821 | 1.9 | NEW | 37405.31 | L | A | FPSO | 58 | N | 0.99906 | A | 0.036541 | Not Availible
Baobab Ivoirien MV10 | AFRICA | N | OC | Lease | 3 | 4949 | EPC | 711 | 1.5 | CONV | 82500 | S | N | FPSO | 970 | A | 0.84848 | L | 0.067511 | 0
Prof. John Evans Atta Mills | AFRICA | M | IOC | Lease | 3 | 8617 | EPC | 1092 | 4.5 | CONV | 108333.3333 | M | N | FPSO | 1425 | L | 0.73846 | H | 0.015568 | 0.088889
Agbami | AFRICA | L | IOC | Own | 2 | 5539 | EPC | 1126 | 4.1538 | NEW | 325000 | UL | L | FPSO | 1433 | L | 0.76923 | L | 0.11368 | 0.3
Akpo | AFRICA | M | IOC | Own | 1 | 5606 | TK | 1303 | 2.345 | NEW | 273333.3333 | UL | M | FPSO | 1325 | N | 0.67683 | L | 0.072141 | 1.55
Bonga | AFRICA | M | IOC | Own | 1 | 4049 | EPC | 1033 | 2.4 | NEW | 253333.3333 | UL | A | FPSO | 1250 | N | 0.88816 | A | 0.70765 | 0.5
Egina FPSO | AFRICA | H | IOC | Own | 1 | 8540 | EPC | 1595 | 15 | NEW | 260000 | UL | L | FPSO | 1600 | A | 0.76923 | L | 0.28715 | -0.033333
Erha | AFRICA | M | IOC | Own | 1 | 4671 | EPC | 1081 | 2.6 | NEW | 266666.6667 | UL | L | FPSO | 1180 | L | 0.7875 | L | 0.19334 | 0.57
Kizomba A | AFRICA | A | IOC | Own | 1 | 4253 | EPC | 1073 | 0.77 | NEW | 316666.6667 | UL | L | FPSO | 1250 | A | 0.78947 | L | 0.0055918 | 0.13333
Ichthys Venturer | AUST/NZ | M | IOC | Own | 1 | 8102 | EPC | 1743 | 2 | NEW | 85000 | S | H | FPSO | 250 | L | 1 | H | 0.37636 | 0.32353
Pyrenees Venture | AUST/NZ | A | IOC | Own | 2 | 6379 | EPC | 1014 | 1.66 | CONV | 106000 | M | M | FPSO | 200 | M | 0.90566 | H | 0.0019724 | 0.012028
Ngujima Yin | AUST/NZ | A | IOC | Own | 1 | 5993 | EPC | 716 | 0.72 | CONV | 136666.6667 | M | L | FPSO | 340 | L | 0.87805 | A | 0.14665 | 0.33333
P 50 | BRAZ | M | NOC | Own | 1 | 4557 | CL | 844 | 0.496 | CONV | 215000 | VL | M | FPSO | 1240 | N | 0.83721 | N | 0.66351 | 0.41129
P 43 | BRAZ | H | NOC | Own | 1 | 4199 | TK | 883 | 1.3 | CONV | 185000 | L | A | FPSO | 800 | N | 0.81081 | N | 0.43828 | 0.38462
P 74 | BRAZ | H | NOC | Own | 1 | 8110 | CL | 1630 | 1.1658 | CONV | 191166.6667 | L | N | FPSO | 2190 | M | 0.78466 | N | 0.36748 | Not Availible
P 75 | BRAZ | H | NOC | Own | 1 | 8110 | CL | 1721 | 1.22 | CONV | 191166.6667 | L | N | FPSO | 1875 | M | 0.78466 | N | 0.52992 | Not Availible
P 76 | BRAZ | H | NOC | Own | 1 | 8110 | CL | 1995 | 1.3242 | CONV | 191166.6667 | L | N | FPSO | 2030 | M | 0.78466 | N | 0.36491 | Not Availible
P 77 | BRAZ | H | NOC | Own | 1 | 8110 | CL | 2086 | 1.22 | CONV | 191166.6667 | L | N | FPSO | 1875 | M | 0.78466 | N | 0.30537 | Not Availible
P 48 | BRAZ | H | NOC | Own | 1 | 4199 | TK | 1066 | 1.3 | CONV | 185000 | L | N | FPSO | 1040 | L | 0.81081 | N | 0.25516 | 0.38462
Frade | BRAZ | A | IOC | Own | 1 | 6014 | EPC | 909 | 2 | CONV | 117666.6667 | M | L | FPSO | 1080 | N | 0.84986 | M | 0.20902 | 1.35
P 68 | BRAZ | H | NOC | Own | 1 | 7486 | CL | 2557 | 1.4 | NEW | 187000 | L | N | FPSO | 2165 | M | 0.80214 | N | 0.33907 | Not Availible
P 70 | BRAZ | H | NOC | Own | 1 | 7486 | EPC | 2557 | 1.4 | NEW | 185333.3333 | L | N | FPSO | 2240 | M | 0.80935 | N | 0.42785 | Not Availible
Cidade de Itaguai MV26 | BRAZ | M | NOC | Lease | 3 | 8352 | EPC | 838 | 1.17 | CONV | 196666.6667 | L | N | FPSO | 2240 | A | 0.76271 | N | 0.18138 | 0
Cidade de Mangaratiba MV24 | BRAZ | A | NOC | Lease | 3 | 7971 | EPC | 1021 | 1.1 | CONV | 197166.6667 | L | N | FPSO | 2200 | A | 0.76078 | N | 0.059745 | Not Availible
P 57 | BRAZ | H | NOC | Lease | 2 | 6622 | EPC | 1041 | 1.195 | CONV | 191833.3333 | L | N | FPSO | 1300 | M | 0.93831 | N | -0.045149 | 0.0041841
Pioneiro de Libra | BRAZ | H | NOC | Lease | 3 | 8984 | PS | 831 | 1 | CONV | 73333.3333 | S | N | FPSO | 2200 | N | 0.68182 | N | 0.45728 | 0.27553
Cidade de Marica | BRAZ | H | NOC | Lease | 3 | 8481 | EPC | 1075 | 1.75 | CONV | 185000 | L | N | FPSO | 2120 | H | 0.81081 | L | -0.042791 | Not Availible
Cidade de Saquarema | BRAZ | H | NOC | Lease | 3 | 8460 | EPC | 1127 | 1.75 | CONV | 185000 | L | N | FPSO | 2200 | H | 0.81081 | L | -0.015084 | Not Availible
P 69 | BRAZ | M | NOC | Own | 1 | 7486 | CL | 2557 | 1.4 | NEW | 185333.3333 | L | N | FPSO | 2165 | M | 0.80935 | N | 0.18772 | Not Availible
P 67 | BRAZ | M | NOC | Own | 1 | 7486 | CL | 2084 | 1.4 | NEW | 179500 | L | N | FPSO | 2165 | M | 0.83565 | N | 0.50432 | Not Availible
P 66 | BRAZ | H | NOC | Own | 1 | 7486 | CL | 2024 | 1.4 | NEW | 191166.6667 | L | A | FPSO | 2165 | M | 0.78466 | N | 0.2332 | Not Availible
P 53 | BRAZ | M | NOC | Own | 2 | 5826 | EPC | 779 | 0.758 | CONV | 215000 | VL | L | FPSO | 1080 | L | 0.83721 | L | 0.38896 | Not Availible
P 63 | BRAZ | H | NOC | Own | 1 | 7213 | EPC | 1383 | 1.3 | CONV | 145833.3333 | M | N | FPSO | 1170 | L | 0.96 | L | 0.086768 | 0.25385
P 58 | BRAZ | H | NOC | Own | 1 | 7268 | EPC | 1481 | 1.03 | CONV | 215333.3333 | VL | N | FPSO | 1400 | M | 0.83591 | N | 0.39095 | Not Availible
Espirito Santo | BRAZ | H | IOC | Lease | 3 | 6153 | EPC | 787 | 1.5086 | CONV | 105000 | M | H | FPSO | 1780 | N | 0.95238 | L | 0.24778 | 1.32
P 54 | BRAZ | H | NOC | Own | 1 | 5272 | EPC | 1034 | 0.629 | CONV | 215000 | VL | A | FPSO | 1315 | A | 0.83721 | N | 0.24468 | 0.97138
P 62 | BRAZ | H | NOC | Own | 1 | 7336 | CL | 1413 | 1.01 | CONV | 215333.3333 | VL | N | FPSO | 1600 | M | 0.83591 | N | 0.22647 | Not Availible
Cidade de Ilhabela | BRAZ | M | NOC | Lease | 3 | 7851 | EPC | 1172 | 1.5 | CONV | 185333.3333 | L | N | FPSO | 2100 | L | 0.80935 | L | 0.052048 | Not Availible
Cidade de Campos dos Goytacazes MV29 | BRAZ | M | NOC | Lease | 3 | 9101 | EPC | 1018 | 1.263 | CONV | 179500 | L | L | FPSO | 765 | M | 0.83565 | N | 0.27898 | 0.0055424
Terra Nova | CAN | L | OC | Own | 1 | 2800 | EPC | 1157 | 1.3 | NEW | 175000 | L | H | FPSO | 90 | N | 0.85714 | L | 0.39412 | 0.30769
Sea Rose | CAN | A | OC | Own | 1 | 4476 | EPC | 1229 | 0.49 | NEW | 125000 | M | H | FPSO | 120 | N | 0.8 | M | 0.072417 | 0.2
Turritella | GOM | N | OC | Own | 1 | 8528 | EPC | 1149 | 1 | Conv | 62500 | S | M | FPSO | 2900 | L | 0.96 | H | 0.11227 | 0.311
Asgard A | NE | A | OC | Own | 1 | 2356 | TK | 870 | 5.2941 | NEW | 300000 | UL | M | FPSO | 300 | N | 0.66667 | A | 0.20805 | 0.36
Balder | NE | A | IOC | Own | 1 | 1826 | TK | 592 | 0.35 | NEW | 90500 | S | H | FPSO | 125 | N | 0.91713 | N | 1.9291 | 0.62
Goliat FPSO | NE | L | OC | Own | 1 | 7218 | EPC | 1364 | 3.9 | NEW | 122500 | M | H | FPSO | 400 | N | 0.81633 | A | 0.72361 | 0.94872
Petrojarl Knarr | NE | L | OC | Lease | 3 | 7850 | EPC | 732 | 1.6119 | NEW | 70833.3333 | S | L | FPSO | 410 | L | 0.88941 | M | 0.85656 | 0.36975
Norne | NE | A | OC | Own | 1 | 1551 | EPC | 1334 | 4.7 | NEW | 261666.6667 | UL | M | FPSO | 380 | A | 0.84076 | L | -0.12519 | 0.6
Skarv | NE | L | IOC | Own | 1 | 6240 | EPC | 1245 | 5 | NEW | 167500 | L | M | FPSO | 370 | N | 0.47761 | A | 0.73494 | 0.7
Armada Kraken | NE | N | OC | Lease | 0 | 8719 | EPC | 1136 | 2.5 | CONV | 83333.3333 | S | N | FPSO | 116 | N | 0.96 | M | 0.16285 | 0
Glen Lyon | NE | A | IOC | Own | 1 | 7729 | EPC | 1949 | 4.78 | NEW | 166666.6667 | L | L | FPSO | 424 | N | 0.78 | M | 0.16675 | 0.19247
Western Isles FPSO | NE | N | OC | Own | 1 | 8391 | EPC | 952 | 1.6 | NEW | 40000 | VS | A | FPSO | 165 | L | 1 | A | 0.8792 | 0.25
Belanak Natuna | SEA | M | IOC | Own | 1 | 4250 | TK | 1137 | 1.6 | NEW | 158333.3333 | L | M | FPSO | 100 | L | 0.63158 | M | 0.058927 | 0.078167
Kikeh FPSO | SEA | H | OC | Lease | 3 | 5513 | EPC | 939 | 0.8 | CONV | 143500 | M | L | FPSO | 1350 | N | 0.83624 | M | -0.015974 | 0.2
Song Doc Pride MV 19 | SEA | N | NOC | Lease | 1 | 6339 | EPC | 417 | 0.25 | CONV | 30000 | VS | N | FPSO | 55 | L | 1 | N | 0.35012 | 0.04087
Thai Binh Vn | SEA | N | NOC | Own | 1 | 4446 | EPC | 611 | 0.714 | NEW | 68333.3333 | S | N | FPSO | 48 | L | 0.95122 | A | 0.037643 | 0.044
Hai Yang Shi You 117 | SEA CH | M | NOC | Own | 1 | 5524 | EPC | 897 | 1.8 | NEW | 190000 | L | N | FPSO | 27 | N | 1 | A | 0.72798 | 0.38889
Hai Yang Shi You 116 | SEA CH | M | NOC | Own | 1 | 5804 | EPC | 723 | 1.2 | NEW | 106000 | M | L | FPSO | 125 | N | 1 | N | 0.3195 | 0.98
Unity | AFRICA | M | IOC | Own | 1 | 4018 | EPC | 545 | 1 | NEW | 125000 | M | L | FSO | 65 | A | 1 | L | 0.70092 | 0.4
Yoho | AFRICA | A | IOC | Own | 1 | 4196 | EPC | 505 | 1.2 | CONV | 90000 | S | L | FSO | 56 | N | 1 | N | 0.20792 | 0.083333
Yoho | AFRICA | A | IOC | Own | 1 | 4623 | EPC | 761 | 1.2 | CONV | 116666.6667 | M | L | FSO | 56 | A | 0.85714 | L | 0.6636 | 0.083333
Randgrid | NE | L | OC | Lease | 0 | 8521 | EPC | 1386 | 3.7 | CONV | 0 | VS | N | FSO | 116 | L | 1 | A | 0.097403 | 0
Hanne Knutsen | NE | L | IOC | Lease | 3 | 8124 | EPC | 1691 | 2.8649 | CONV | 100000 | M | A | FSO | 115 | N | 1 | L | 0.80958 | 0.85
Ailsa FSO | NE | L | IOC | Own | 1 | 9389 | EPC | 1364 | 4.7 | NEW | 108333.3333 | M | L | FSO | 90 | H | 0.23077 | H | 0 | 0
Gagak Rimang | SEA | H | IOC | Own | 1 | 7891 | EPC | 1110 | 1.2 | CONV | 165000 | L | L | FSO | 33 | N | 1 | L | 0.42973 | 1.1667
Rang Dong MV17 | SEA | N | NOC | Lease | 3 | 6038 | EPC | 763 | 0.5 | NEW | 60000 | S | N | FSO | 60 | L | 1 | N | 0.10747 | 0.04087
Ichthys Explorer | AUST/NZ | M | OC | Own | 1 | 8046 | EPC | 1810 | 3 | NEW | 361166.6667 | UL | M | SEMI | 250 | L | 0.23535 | H | 0.35635 | 0.32353
P 51 | BRAZ | H | NOC | Own | 1 | 5201 | EPC | 1418 | 0.83 | NEW | 215000 | VL | L | SEMI | 1250 | H | 0.83721 | N | 0.24401 | 0.25
P 56 | BRAZ | H | NOC | Own | 1 | 6478 | EPC | 1114 | 1.4 | NEW | 135000 | M | N | SEMI | 1670 | H | 0.74074 | N | 0.27379 | 0.071429
P 52 | BRAZ | H | NOC | Lease | 3 | 5060 | EPC | 1237 | 0.906 | NEW | 235000 | VL | L | SEMI | 1850 | A | 0.76596 | N | 0.19644 | 0.43488
P 55 | BRAZ | H | NOC | Own | 1 | 6517 | EPC | 1518 | 1.65 | NEW | 215333.3333 | VL | L | SEMI | 1790 | A | 0.83591 | N | 0.49144 | Not Availible
Atlantis | GOM | A | IOC | Own | 1 | 4533 | EPC | 1492 | 2.5 | NEW | 230000 | VL | A | SEMI | 2145 | A | 0.86957 | N | 0.60389 | 1.35
Delta House (Opti-Ex II) | GOM | N | OC | Own | 1 | 8158 | EPC | 1093 | 2 | NEW | 140000 | M | L | SEMI | 1372 | H | 0.71429 | L | -0.012809 | 0
Blind Faith | GOM | L | IOC | Own | 1 | 5802 | EPC | 846 | 1.151 | NEW | 52500 | S | M | SEMI | 2130 | N | 0.85714 | H | 0.28605 | 0.95
Thunder Hawk | GOM | N | OC | Lease | 3 | 6086 | EPC | 958 | 0.8 | NEW | 56666.6667 | S | N | SEMI | 1847 | M | 0.79412 | H | 0.087683 | 0
Thunder Horse | GOM | A | IOC | Own | 1 | 4624 | EPC | 1098 | 5 | NEW | 283333.3333 | UL | H | SEMI | 1830 | N | 0.88235 | M | 0.92623 | 2.68
Jack / St. Malo Semi | GOM | N | IOC | Own | 1 | 7270 | EPC | 1844 | 7.5 | NEW | 177166.6667 | L | N | SEMI | 2134 | M | 0.95955 | H | -0.005423 | 0
Asgard B | NE | M | OC | Own | 1 | 2356 | TK | 1570 | 1.3 | New | 351666.6667 | UL | N | SEMI | 300 | H | 0.38389 | M | 0 | 0
Gjoa | NE | L | OC | Own | 1 | 6025 | CL | 1461 | 4.4361 | NEW | 108333.3333 | M | M | SEMI | 380 | N | 0.46154 | A | 0.08898 | 0.33
Kristin | NE | M | OC | Own | 1 | 4368 | EPC | 1384 | 1.9 | New | 128000 | M | H | SEMI | 370 | N | 0.97656 | L | 0.023844 | 0.73684
Snorre B | NE | M | OC | Own | 1 | 3256 | EPC | 943 | 1.2821 | NEW | 115000 | M | N | SEMI | 310 | M | 1 | L | -0.064687 | 0.17
Troll C | NE | A | OC | Own | 1 | 2647 | EPC | 821 | 4.5 | NEW | 243333.3333 | VL | H | SEMI | 340 | M | 0.78082 | A | 0.18636 | Not Availible
Troll B | NE | A | OC | Own | 1 | 379 | EPC | 1263 | 2.9 | NEW | 317000 | UL | H | SEMI | 320 | L | 0.85174 | A | 0.35234 | 0.14
Visund | NE | H | OC | Own | 1 | 2251 | TK | 851 | 0.7 | NEW | 171333.3333 | L | H | SEMI | 335 | N | 0.65953 | L | 0.3396 | 0.45
Gumusut Semi | SEA | H | IOC | Lease | 3 | 6588 | EPC | 1233 | 1.6 | NEW | 200000 | VL | L | SEMI | 1220 | L | 0.75 | A | 0.99919 | 0.25
Perdido Spar | GOM | L | IOC | Own | 1 | 6025 | EPC | 974 | 3 | NEW | 133333.3333 | M | H | SPAR | 2440 | N | 0.75 | A | 0.40554 | Not Availible
Front Runner Spar | GOM | L | OC | Own | 1 | 4459 | TK | 728 | 0.2 | NEW | 78333.3333 | S | A | SPAR | 1015 | N | 0.76596 | N | 0.36676 | 0.075
Tahiti Spar | GOM | L | IOC | Own | 1 | 5597 | EPC | 1159 | 3.5 | NEW | 136666.6667 | M | A | SPAR | 1280 | L | 0.91463 | L | 0.26747 | 1.8
Holstein | GOM | N | IOC | Own | 1 | 4070 | EPC | 859 | 1 | NEW | 135000 | M | M | SPAR | 1345 | L | 0.81481 | A | 0.6135 | Not Availible
Mad Dog | GOM | N | IOC | Own | 1 | 4070 | EPC | 1397 | 1.82 | NEW | 66666.6667 | S | L | SPAR | 1370 | N | 0.9 | M | 0.022906 | 0.1
Heidelberg Spar | GOM | N | OC | Own | 1 | 8018 | EPC | 1649 | 6.745 | NEW | 93333.3333 | S | M | SPAR | 1620 | H | 0.85714 | H | -0.095816 | 0.0081542
Lucius Spar | GOM | N | OC | Own | 1 | 8002 | EPC | 1007 | 7.736 | NEW | 155000 | L | M | SPAR | 2165 | M | 0.51613 | H | 0.14002 | 0.008273
Medusa Spar | GOM | L | OC | Own | 1 | 4077 | TK | 579 | 0.2 | NEW | 58333.3333 | S | A | SPAR | 675 | N | 0.68571 | N | 0.74266 | 0.365
Gulfstar 1 | GOM | N | IOC | Lease | 3 | 7813 | EPC | 1132 | 2.3 | NEW | 109166.6667 | M | L | SPAR | 1310 | L | 0.73282 | A | 0.12191 | 0.47826
Devil's Tower Spar | GOM | A | OC | Lease | 3 | 4189 | TK | 739 | 0.2 | NEW | 66666.6667 | S | L | SPAR | 1710 | L | 0.9 | N | 0.41949 | 0.06
Kikeh Spar | SEA | H | OC | Own | 1 | 5513 | EPC | 939 | 0.5 | NEW | 142500 | M | M | SPAR | 1330 | N | 0.84211 | M | -0.015974 | 0.28571
Kizomba A Wellhead TLP | AFRICA | M | IOC | Own | 1 | 4253 | EPC | 1073 | 0.65 | NEW | 250000 | UL | N | TLP | 1175 | A | 1 | L | 0.0055918 | 0.13333
Kizomba B Wellhead TLP | AFRICA | A | IOC | Own | 1 | 4756 | EPC | 1071 | 0.6 | NEW | 250000 | UL | N | TLP | 1250 | H | 1 | L | -0.14006 | 0.13333
Okume TLP | AFRICA | L | OC | Own | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | VS | N | TLP | 500 | M | 0.83333 | M | 0.04 | 0
Oveng TLP | AFRICA | L | OC | Own | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | VS | N | TLP | 280 | M | 0.83333 | M | 0.04 | 0
P 61 Wellhead TLP | BRAZ | H | NOC | Own | 1 | 7213 | EPC | 1475 | 1.07 | NEW | 145833.3333 | M | A | TLP | 1180 | N | 0.96 | L | 0.35051 | 0
Auger TLP | GOM | L | IOC | Own | 1 | 287 | EPC | 1233 | 0.86364 | NEW | 65000 | S | M | TLP | 870 | L | 0.61538 | M | 0.044607 | 0.38947
Magnolia TLP | GOM | N | IOC | Own | 1 | 4392 | EPC | 1040 | 0.6 | NEW | 75000 | S | M | TLP | 1432 | L | 0.66667 | H | 0.038462 | 0
Brutus TLP | GOM | N | IOC | Own | 1 | 3570 | EPC | 674 | 0.76 | NEW | 155000 | L | L | TLP | 910 | M | 0.83871 | M | 0.038576 | 0.078947
Stampede TLP | GOM | N | OC | Own | 1 | 8523 | EPC | 1982 | 6.2 | NEW | 86666.6667 | S | N | TLP | 1160 | M | 0.92308 | H | -0.1221 | -0.12903
Neptune TLP | GOM | L | OC | Own | 1 | 5670 | EPC | 887 | 0.85 | NEW | 58333.3333 | S | L | TLP | 1300 | L | 0.85714 | A | 0.2345 | 0.47882
Shenzi TLP | GOM | L | OC | Own | 1 | 6001 | EPC | 1119 | 4.41 | NEW | 116666.6667 | M | L | TLP | 1333 | L | 0.85714 | H | -0.088472 | 0
Mars TLP | GOM | N | IOC | Own | 1 | 1381 | EPC | 1098 | 1.2 | NEW | 230833.3333 | VL | L | TLP | 896 | M | 0.86643 | M | -0.090164 | -0.054167
Olympus TLP | GOM | N | IOC | Own | 1 | 7729 | EPC | 1202 | 3 | NEW | 116666.6667 | M | L | TLP | 945 | H | 0.85714 | H | -0.12562 | 0
Ursa TLP | GOM | N | IOC | Own | 1 | 2398 | EPC | 1040 | 1.45 | NEW | 216666.6667 | VL | A | TLP | 1160 | H | 0.69231 | M | -0.081731 | 0.043448
Ram Powell TLP | GOM | N | IOC | Own | 1 | 1885 | EPC | 915 | 1 | NEW | 93333.3333 | S | A | TLP | 990 | H | 0.64286 | M | 0.015301 | 0
Big Foot | GOM | A | IOC | Own | 1 | 7571 | EPC | 1529 | 4 | NEW | 79166.6667 | S | H | TLP | 1580 | N | 0.94737 | M | 0.94899 | 0.375
Heidrun TLP | NE | N | OC | Own | 1 | 504 | EPC | 1548 | 3.9 | NEW | 283333.3333 | UL | L | TLP | 350 | L | 0.88235 | H | 0.039406 | 0.076923
Malikai TLP | SEA | H | IOC | Own | 1 | 8439 | EPC | 1030 | 1.2825 | NEW | 68333.3333 | S | L | TLP | 470 | A | 0.87805 | H | 0.36796 | 0.077973

## Schedule
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun
Lingshui Semi | 8 | 5 | 3 | 2 | 1 | 10439 | 3 | 700 | 3.1 | 1 | 67166.6667 | 2 | 2 | 6 | 980 | 2 | 0.14888 | 4 | 0.76 | Not Availible
Bohai Ming Zhu | 8 | 5 | 3 | 2 | 1 | 4350 | 3 | 259 | 0.4 | 1 | 40000 | 1 | 2 | 5 | 30 | 1 | 1 | 1 | 0.47104 | 0.25
Petrojarl Varg | 7 | 1 | 1 | 1 | 1 | 2240 | 3 | 816 | 0.46 | 1 | 65833.3333 | 2 | 2 | 5 | 84 | 1 | 0.86582 | 2 | 0.28676 | 0.24
Stybarrow Venture MV16 | 4 | 3 | 2 | 1 | 3 | 5922 | 3 | 702 | 0.59843 | 1 | 87500 | 2 | 3 | 5 | 825 | 2 | 0.91429 | 4 | -0.14387 | 0.27
Alima FPU | 1 | 2 | 2 | 2 | 1 | 5720 | 3 | 994 | 1.133 | 1 | 100000 | 3 | 1 | 1 | 600 | 3 | 0.9 | 4 | -0.022133 | 0.35
Jangkrik | 2 | 4 | 1 | 2 | 1 | 8824 | 3 | 1052 | 2.6765 | 1 | 79400 | 2 | 2 | 1 | 120 | 2 | 0.055416 | 3 | 0.11407 | 0.17
Prelude | 4 | 3 | 2 | 2 | 1 | 7814 | 3 | 2229 | 11.16 | 1 | 148333.3333 | 6 | 5 | 4 | 250 | 1 | 0.23596 | 5 | 0.24316 | 0.34409
CLOV FPSO | 1 | 3 | 2 | 2 | 1 | 7534 | 3 | 1383 | 7 | 1 | 198333.3333 | 4 | 2 | 5 | 1290 | 4 | 0.80672 | 5 | 0.0079537 | 0.14286
Dalia | 1 | 4 | 2 | 2 | 1 | 4872 | 3 | 1306 | 3.4 | 1 | 287000 | 6 | 3 | 5 | 1360 | 5 | 0.83624 | 2 | 0.01072 | 0.17647
Girassol | 1 | 4 | 2 | 2 | 1 | 3103 | 3 | 823 | 2.5 | 1 | 246666.6667 | 5 | 3 | 5 | 1350 | 1 | 0.81081 | 1 | 0.52126 | 0.12
Kaombo Norte | 1 | 5 | 2 | 2 | 1 | 8871 | 3 | 1081 | 1.5 | 2 | 131666.6667 | 3 | 2 | 5 | 1600 | 2 | 0.87342 | 3 | 0.44773 | Not Availible
Kaombo Sul | 1 | 5 | 2 | 2 | 1 | 8871 | 3 | 1173 | 1.5 | 2 | 131666.6667 | 3 | 2 | 5 | 1600 | 2 | 0.87342 | 3 | 0.54646 | Not Availible
Kizomba B | 1 | 3 | 2 | 2 | 1 | 4756 | 3 | 1071 | 0.76 | 1 | 316666.6667 | 6 | 1 | 5 | 1250 | 5 | 0.78947 | 2 | -0.14006 | 0.13333
Mondo | 1 | 4 | 2 | 1 | 1 | 5866 | 3 | 797 | 0.75 | 2 | 115833.3333 | 3 | 1 | 5 | 728 | 3 | 0.86331 | 3 | -0.10163 | 0
Saxi-Batuque | 1 | 4 | 2 | 1 | 3 | 5866 | 3 | 797 | 0.75 | 2 | 130000 | 3 | 1 | 5 | 720 | 3 | 0.80769 | 3 | -0.084065 | 0
Greater Plutonio | 1 | 3 | 2 | 2 | 1 | 5144 | 3 | 1124 | 1.73 | 1 | 305000 | 6 | 3 | 5 | 1350 | 2 | 0.81967 | 4 | 0.19039 | 0.85
PSVM FPSO | 1 | 5 | 2 | 2 | 1 | 6755 | 3 | 1249 | 10 | 2 | 197833.3333 | 4 | 5 | 5 | 2000 | 2 | 0.7936 | 1 | 0.29704 | 0.4
Sanha LPG | 1 | 1 | 2 | 2 | 1 | 4687 | 3 | 821 | 1.9 | 1 | 37405.31 | 4 | 3 | 5 | 58 | 1 | 0.99906 | 3 | 0.036541 | Not Availible
Baobab Ivoirien MV10 | 1 | 1 | 1 | 1 | 3 | 4949 | 3 | 711 | 1.5 | 2 | 82500 | 2 | 1 | 5 | 970 | 3 | 0.84848 | 2 | 0.067511 | 0
Prof. John Evans Atta Mills | 1 | 4 | 2 | 1 | 3 | 8617 | 3 | 1092 | 4.5 | 2 | 108333.3333 | 3 | 1 | 5 | 1425 | 2 | 0.73846 | 5 | 0.015568 | 0.088889
Agbami | 1 | 2 | 2 | 2 | 2 | 5539 | 3 | 1126 | 4.1538 | 1 | 325000 | 6 | 2 | 5 | 1433 | 2 | 0.76923 | 2 | 0.11368 | 0.3
Akpo | 1 | 4 | 2 | 2 | 1 | 5606 | 4 | 1303 | 2.345 | 1 | 273333.3333 | 6 | 4 | 5 | 1325 | 1 | 0.67683 | 2 | 0.072141 | 1.55
Bonga | 1 | 4 | 2 | 2 | 1 | 4049 | 3 | 1033 | 2.4 | 1 | 253333.3333 | 6 | 3 | 5 | 1250 | 1 | 0.88816 | 3 | 0.70765 | 0.5
Egina FPSO | 1 | 5 | 2 | 2 | 1 | 8540 | 3 | 1595 | 15 | 1 | 260000 | 6 | 2 | 5 | 1600 | 3 | 0.76923 | 2 | 0.28715 | -0.033333
Erha | 1 | 4 | 2 | 2 | 1 | 4671 | 3 | 1081 | 2.6 | 1 | 266666.6667 | 6 | 2 | 5 | 1180 | 2 | 0.7875 | 2 | 0.19334 | 0.57
Kizomba A | 1 | 3 | 2 | 2 | 1 | 4253 | 3 | 1073 | 0.77 | 1 | 316666.6667 | 6 | 2 | 5 | 1250 | 3 | 0.78947 | 2 | 0.0055918 | 0.13333
Ichthys Venturer | 4 | 4 | 2 | 2 | 1 | 8102 | 3 | 1743 | 2 | 1 | 85000 | 2 | 5 | 5 | 250 | 2 | 1 | 5 | 0.37636 | 0.32353
Pyrenees Venture | 4 | 3 | 2 | 2 | 2 | 6379 | 3 | 1014 | 1.66 | 2 | 106000 | 3 | 4 | 5 | 200 | 4 | 0.90566 | 5 | 0.0019724 | 0.012028
Ngujima Yin | 4 | 3 | 2 | 2 | 1 | 5993 | 3 | 716 | 0.72 | 2 | 136666.6667 | 3 | 2 | 5 | 340 | 2 | 0.87805 | 3 | 0.14665 | 0.33333
P 50 | 6 | 4 | 3 | 2 | 1 | 4557 | 2 | 844 | 0.496 | 2 | 215000 | 5 | 4 | 5 | 1240 | 1 | 0.83721 | 1 | 0.66351 | 0.41129
P 43 | 6 | 5 | 3 | 2 | 1 | 4199 | 4 | 883 | 1.3 | 2 | 185000 | 4 | 3 | 5 | 800 | 1 | 0.81081 | 1 | 0.43828 | 0.38462
P 74 | 6 | 5 | 3 | 2 | 1 | 8110 | 2 | 1630 | 1.1658 | 2 | 191166.6667 | 4 | 1 | 5 | 2190 | 4 | 0.78466 | 1 | 0.36748 | Not Availible
P 75 | 6 | 5 | 3 | 2 | 1 | 8110 | 2 | 1721 | 1.22 | 2 | 191166.6667 | 4 | 1 | 5 | 1875 | 4 | 0.78466 | 1 | 0.52992 | Not Availible
P 76 | 6 | 5 | 3 | 2 | 1 | 8110 | 2 | 1995 | 1.3242 | 2 | 191166.6667 | 4 | 1 | 5 | 2030 | 4 | 0.78466 | 1 | 0.36491 | Not Availible
P 77 | 6 | 5 | 3 | 2 | 1 | 8110 | 2 | 2086 | 1.22 | 2 | 191166.6667 | 4 | 1 | 5 | 1875 | 4 | 0.78466 | 1 | 0.30537 | Not Availible
P 48 | 6 | 5 | 3 | 2 | 1 | 4199 | 4 | 1066 | 1.3 | 2 | 185000 | 4 | 1 | 5 | 1040 | 2 | 0.81081 | 1 | 0.25516 | 0.38462
Frade | 6 | 3 | 2 | 2 | 1 | 6014 | 3 | 909 | 2 | 2 | 117666.6667 | 3 | 2 | 5 | 1080 | 1 | 0.84986 | 4 | 0.20902 | 1.35
P 68 | 6 | 5 | 3 | 2 | 1 | 7486 | 2 | 2557 | 1.4 | 1 | 187000 | 4 | 1 | 5 | 2165 | 4 | 0.80214 | 1 | 0.33907 | Not Availible
P 70 | 6 | 5 | 3 | 2 | 1 | 7486 | 3 | 2557 | 1.4 | 1 | 185333.3333 | 4 | 1 | 5 | 2240 | 4 | 0.80935 | 1 | 0.42785 | Not Availible
Cidade de Itaguai MV26 | 6 | 4 | 3 | 1 | 3 | 8352 | 3 | 838 | 1.17 | 2 | 196666.6667 | 4 | 1 | 5 | 2240 | 3 | 0.76271 | 1 | 0.18138 | 0
Cidade de Mangaratiba MV24 | 6 | 3 | 3 | 1 | 3 | 7971 | 3 | 1021 | 1.1 | 2 | 197166.6667 | 4 | 1 | 5 | 2200 | 3 | 0.76078 | 1 | 0.059745 | Not Availible
P 57 | 6 | 5 | 3 | 1 | 2 | 6622 | 3 | 1041 | 1.195 | 2 | 191833.3333 | 4 | 1 | 5 | 1300 | 4 | 0.93831 | 1 | -0.045149 | 0.0041841
Pioneiro de Libra | 6 | 5 | 3 | 1 | 3 | 8984 | 1 | 831 | 1 | 2 | 73333.3333 | 2 | 1 | 5 | 2200 | 1 | 0.68182 | 1 | 0.45728 | 0.27553
Cidade de Marica | 6 | 5 | 3 | 1 | 3 | 8481 | 3 | 1075 | 1.75 | 2 | 185000 | 4 | 1 | 5 | 2120 | 5 | 0.81081 | 2 | -0.042791 | Not Availible
Cidade de Saquarema | 6 | 5 | 3 | 1 | 3 | 8460 | 3 | 1127 | 1.75 | 2 | 185000 | 4 | 1 | 5 | 2200 | 5 | 0.81081 | 2 | -0.015084 | Not Availible
P 69 | 6 | 4 | 3 | 2 | 1 | 7486 | 2 | 2557 | 1.4 | 1 | 185333.3333 | 4 | 1 | 5 | 2165 | 4 | 0.80935 | 1 | 0.18772 | Not Availible
P 67 | 6 | 4 | 3 | 2 | 1 | 7486 | 2 | 2084 | 1.4 | 1 | 179500 | 4 | 1 | 5 | 2165 | 4 | 0.83565 | 1 | 0.50432 | Not Availible
P 66 | 6 | 5 | 3 | 2 | 1 | 7486 | 2 | 2024 | 1.4 | 1 | 191166.6667 | 4 | 3 | 5 | 2165 | 4 | 0.78466 | 1 | 0.2332 | Not Availible
P 53 | 6 | 4 | 3 | 2 | 2 | 5826 | 3 | 779 | 0.758 | 2 | 215000 | 5 | 2 | 5 | 1080 | 2 | 0.83721 | 2 | 0.38896 | Not Availible
P 63 | 6 | 5 | 3 | 2 | 1 | 7213 | 3 | 1383 | 1.3 | 2 | 145833.3333 | 3 | 1 | 5 | 1170 | 2 | 0.96 | 2 | 0.086768 | 0.25385
P 58 | 6 | 5 | 3 | 2 | 1 | 7268 | 3 | 1481 | 1.03 | 2 | 215333.3333 | 5 | 1 | 5 | 1400 | 4 | 0.83591 | 1 | 0.39095 | Not Availible
Espirito Santo | 6 | 5 | 2 | 1 | 3 | 6153 | 3 | 787 | 1.5086 | 2 | 105000 | 3 | 5 | 5 | 1780 | 1 | 0.95238 | 2 | 0.24778 | 1.32
P 54 | 6 | 5 | 3 | 2 | 1 | 5272 | 3 | 1034 | 0.629 | 2 | 215000 | 5 | 3 | 5 | 1315 | 3 | 0.83721 | 1 | 0.24468 | 0.97138
P 62 | 6 | 5 | 3 | 2 | 1 | 7336 | 2 | 1413 | 1.01 | 2 | 215333.3333 | 5 | 1 | 5 | 1600 | 4 | 0.83591 | 1 | 0.22647 | Not Availible
Cidade de Ilhabela | 6 | 4 | 3 | 1 | 3 | 7851 | 3 | 1172 | 1.5 | 2 | 185333.3333 | 4 | 1 | 5 | 2100 | 2 | 0.80935 | 2 | 0.052048 | Not Availible
Cidade de Campos dos Goytacazes MV29 | 6 | 4 | 3 | 1 | 3 | 9101 | 3 | 1018 | 1.263 | 2 | 179500 | 4 | 2 | 5 | 765 | 4 | 0.83565 | 1 | 0.27898 | 0.0055424
Terra Nova | 5 | 2 | 1 | 2 | 1 | 2800 | 3 | 1157 | 1.3 | 1 | 175000 | 4 | 5 | 5 | 90 | 1 | 0.85714 | 2 | 0.39412 | 0.30769
Sea Rose | 5 | 3 | 1 | 2 | 1 | 4476 | 3 | 1229 | 0.49 | 1 | 125000 | 3 | 5 | 5 | 120 | 1 | 0.8 | 4 | 0.072417 | 0.2
Turritella | 3 | 1 | 1 | 2 | 1 | 8528 | 3 | 1149 | 1 | 2 | 62500 | 2 | 4 | 5 | 2900 | 2 | 0.96 | 5 | 0.11227 | 0.311
Asgard A | 7 | 3 | 1 | 2 | 1 | 2356 | 4 | 870 | 5.2941 | 1 | 300000 | 6 | 4 | 5 | 300 | 1 | 0.66667 | 3 | 0.20805 | 0.36
Balder | 7 | 3 | 2 | 2 | 1 | 1826 | 4 | 592 | 0.35 | 1 | 90500 | 2 | 5 | 5 | 125 | 1 | 0.91713 | 1 | 1.9291 | 0.62
Goliat FPSO | 7 | 2 | 1 | 2 | 1 | 7218 | 3 | 1364 | 3.9 | 1 | 122500 | 3 | 5 | 5 | 400 | 1 | 0.81633 | 3 | 0.72361 | 0.94872
Petrojarl Knarr | 7 | 2 | 1 | 1 | 3 | 7850 | 3 | 732 | 1.6119 | 1 | 70833.3333 | 2 | 2 | 5 | 410 | 2 | 0.88941 | 4 | 0.85656 | 0.36975
Norne | 7 | 3 | 1 | 2 | 1 | 1551 | 3 | 1334 | 4.7 | 1 | 261666.6667 | 6 | 4 | 5 | 380 | 3 | 0.84076 | 2 | -0.12519 | 0.6
Skarv | 7 | 2 | 2 | 2 | 1 | 6240 | 3 | 1245 | 5 | 1 | 167500 | 4 | 4 | 5 | 370 | 1 | 0.47761 | 3 | 0.73494 | 0.7
Armada Kraken | 7 | 1 | 1 | 1 | 0 | 8719 | 3 | 1136 | 2.5 | 2 | 83333.3333 | 2 | 1 | 5 | 116 | 1 | 0.96 | 4 | 0.16285 | 0
Glen Lyon | 7 | 3 | 2 | 2 | 1 | 7729 | 3 | 1949 | 4.78 | 1 | 166666.6667 | 4 | 2 | 5 | 424 | 1 | 0.78 | 4 | 0.16675 | 0.19247
Western Isles FPSO | 7 | 1 | 1 | 2 | 1 | 8391 | 3 | 952 | 1.6 | 1 | 40000 | 1 | 3 | 5 | 165 | 2 | 1 | 3 | 0.8792 | 0.25
Belanak Natuna | 2 | 4 | 2 | 2 | 1 | 4250 | 4 | 1137 | 1.6 | 1 | 158333.3333 | 4 | 4 | 5 | 100 | 2 | 0.63158 | 4 | 0.058927 | 0.078167
Kikeh FPSO | 2 | 5 | 1 | 1 | 3 | 5513 | 3 | 939 | 0.8 | 2 | 143500 | 3 | 2 | 5 | 1350 | 1 | 0.83624 | 4 | -0.015974 | 0.2
Song Doc Pride MV 19 | 2 | 1 | 3 | 1 | 1 | 6339 | 3 | 417 | 0.25 | 2 | 30000 | 1 | 1 | 5 | 55 | 2 | 1 | 1 | 0.35012 | 0.04087
Thai Binh Vn | 2 | 1 | 3 | 2 | 1 | 4446 | 3 | 611 | 0.714 | 1 | 68333.3333 | 2 | 1 | 5 | 48 | 2 | 0.95122 | 3 | 0.037643 | 0.044
Hai Yang Shi You 117 | 8 | 4 | 3 | 2 | 1 | 5524 | 3 | 897 | 1.8 | 1 | 190000 | 4 | 1 | 5 | 27 | 1 | 1 | 3 | 0.72798 | 0.38889
Hai Yang Shi You 116 | 8 | 4 | 3 | 2 | 1 | 5804 | 3 | 723 | 1.2 | 1 | 106000 | 3 | 2 | 5 | 125 | 1 | 1 | 1 | 0.3195 | 0.98
Unity | 1 | 4 | 2 | 2 | 1 | 4018 | 3 | 545 | 1 | 1 | 125000 | 3 | 2 | 7 | 65 | 3 | 1 | 2 | 0.70092 | 0.4
Yoho | 1 | 3 | 2 | 2 | 1 | 4196 | 3 | 505 | 1.2 | 2 | 90000 | 2 | 2 | 7 | 56 | 1 | 1 | 1 | 0.20792 | 0.083333
Yoho | 1 | 3 | 2 | 2 | 1 | 4623 | 3 | 761 | 1.2 | 2 | 116666.6667 | 3 | 2 | 7 | 56 | 3 | 0.85714 | 2 | 0.6636 | 0.083333
Randgrid | 7 | 2 | 1 | 1 | 0 | 8521 | 3 | 1386 | 3.7 | 2 | 0 | 1 | 1 | 7 | 116 | 2 | 1 | 3 | 0.097403 | 0
Hanne Knutsen | 7 | 2 | 2 | 1 | 3 | 8124 | 3 | 1691 | 2.8649 | 2 | 100000 | 3 | 3 | 7 | 115 | 1 | 1 | 2 | 0.80958 | 0.85
Ailsa FSO | 7 | 2 | 2 | 2 | 1 | 9389 | 3 | 1364 | 4.7 | 1 | 108333.3333 | 3 | 2 | 7 | 90 | 5 | 0.23077 | 5 | 0 | 0
Gagak Rimang | 2 | 5 | 2 | 2 | 1 | 7891 | 3 | 1110 | 1.2 | 2 | 165000 | 4 | 2 | 7 | 33 | 1 | 1 | 2 | 0.42973 | 1.1667
Rang Dong MV17 | 2 | 1 | 3 | 1 | 3 | 6038 | 3 | 763 | 0.5 | 1 | 60000 | 2 | 1 | 7 | 60 | 2 | 1 | 1 | 0.10747 | 0.04087
Ichthys Explorer | 4 | 4 | 1 | 2 | 1 | 8046 | 3 | 1810 | 3 | 1 | 361166.6667 | 6 | 4 | 6 | 250 | 2 | 0.23535 | 5 | 0.35635 | 0.32353
P 51 | 6 | 5 | 3 | 2 | 1 | 5201 | 3 | 1418 | 0.83 | 1 | 215000 | 5 | 2 | 6 | 1250 | 5 | 0.83721 | 1 | 0.24401 | 0.25
P 56 | 6 | 5 | 3 | 2 | 1 | 6478 | 3 | 1114 | 1.4 | 1 | 135000 | 3 | 1 | 6 | 1670 | 5 | 0.74074 | 1 | 0.27379 | 0.071429
P 52 | 6 | 5 | 3 | 1 | 3 | 5060 | 3 | 1237 | 0.906 | 1 | 235000 | 5 | 2 | 6 | 1850 | 3 | 0.76596 | 1 | 0.19644 | 0.43488
P 55 | 6 | 5 | 3 | 2 | 1 | 6517 | 3 | 1518 | 1.65 | 1 | 215333.3333 | 5 | 2 | 6 | 1790 | 3 | 0.83591 | 1 | 0.49144 | Not Availible
Atlantis | 3 | 3 | 2 | 2 | 1 | 4533 | 3 | 1492 | 2.5 | 1 | 230000 | 5 | 3 | 6 | 2145 | 3 | 0.86957 | 1 | 0.60389 | 1.35
Delta House (Opti-Ex II) | 3 | 1 | 1 | 2 | 1 | 8158 | 3 | 1093 | 2 | 1 | 140000 | 3 | 2 | 6 | 1372 | 5 | 0.71429 | 2 | -0.012809 | 0
Blind Faith | 3 | 2 | 2 | 2 | 1 | 5802 | 3 | 846 | 1.151 | 1 | 52500 | 2 | 4 | 6 | 2130 | 1 | 0.85714 | 5 | 0.28605 | 0.95
Thunder Hawk | 3 | 1 | 1 | 1 | 3 | 6086 | 3 | 958 | 0.8 | 1 | 56666.6667 | 2 | 1 | 6 | 1847 | 4 | 0.79412 | 5 | 0.087683 | 0
Thunder Horse | 3 | 3 | 2 | 2 | 1 | 4624 | 3 | 1098 | 5 | 1 | 283333.3333 | 6 | 5 | 6 | 1830 | 1 | 0.88235 | 4 | 0.92623 | 2.68
Jack / St. Malo Semi | 3 | 1 | 2 | 2 | 1 | 7270 | 3 | 1844 | 7.5 | 1 | 177166.6667 | 4 | 1 | 6 | 2134 | 4 | 0.95955 | 5 | -0.005423 | 0
Asgard B | 7 | 4 | 1 | 2 | 1 | 2356 | 4 | 1570 | 1.3 | 1 | 351666.6667 | 6 | 1 | 6 | 300 | 5 | 0.38389 | 4 | 0 | 0
Gjoa | 7 | 2 | 1 | 2 | 1 | 6025 | 2 | 1461 | 4.4361 | 1 | 108333.3333 | 3 | 4 | 6 | 380 | 1 | 0.46154 | 3 | 0.08898 | 0.33
Kristin | 7 | 4 | 1 | 2 | 1 | 4368 | 3 | 1384 | 1.9 | 1 | 128000 | 3 | 5 | 6 | 370 | 1 | 0.97656 | 2 | 0.023844 | 0.73684
Snorre B | 7 | 4 | 1 | 2 | 1 | 3256 | 3 | 943 | 1.2821 | 1 | 115000 | 3 | 1 | 6 | 310 | 4 | 1 | 2 | -0.064687 | 0.17
Troll C | 7 | 3 | 1 | 2 | 1 | 2647 | 3 | 821 | 4.5 | 1 | 243333.3333 | 5 | 5 | 6 | 340 | 4 | 0.78082 | 3 | 0.18636 | Not Availible
Troll B | 7 | 3 | 1 | 2 | 1 | 379 | 3 | 1263 | 2.9 | 1 | 317000 | 6 | 5 | 6 | 320 | 2 | 0.85174 | 3 | 0.35234 | 0.14
Visund | 7 | 5 | 1 | 2 | 1 | 2251 | 4 | 851 | 0.7 | 1 | 171333.3333 | 4 | 5 | 6 | 335 | 1 | 0.65953 | 2 | 0.3396 | 0.45
Gumusut Semi | 2 | 5 | 2 | 1 | 3 | 6588 | 3 | 1233 | 1.6 | 1 | 200000 | 5 | 2 | 6 | 1220 | 2 | 0.75 | 3 | 0.99919 | 0.25
Perdido Spar | 3 | 2 | 2 | 2 | 1 | 6025 | 3 | 974 | 3 | 1 | 133333.3333 | 3 | 5 | 3 | 2440 | 1 | 0.75 | 3 | 0.40554 | Not Availible
Front Runner Spar | 3 | 2 | 1 | 2 | 1 | 4459 | 4 | 728 | 0.2 | 1 | 78333.3333 | 2 | 3 | 3 | 1015 | 1 | 0.76596 | 1 | 0.36676 | 0.075
Tahiti Spar | 3 | 2 | 2 | 2 | 1 | 5597 | 3 | 1159 | 3.5 | 1 | 136666.6667 | 3 | 3 | 3 | 1280 | 2 | 0.91463 | 2 | 0.26747 | 1.8
Holstein | 3 | 1 | 2 | 2 | 1 | 4070 | 3 | 859 | 1 | 1 | 135000 | 3 | 4 | 3 | 1345 | 2 | 0.81481 | 3 | 0.6135 | Not Availible
Mad Dog | 3 | 1 | 2 | 2 | 1 | 4070 | 3 | 1397 | 1.82 | 1 | 66666.6667 | 2 | 2 | 3 | 1370 | 1 | 0.9 | 4 | 0.022906 | 0.1
Heidelberg Spar | 3 | 1 | 1 | 2 | 1 | 8018 | 3 | 1649 | 6.745 | 1 | 93333.3333 | 2 | 4 | 3 | 1620 | 5 | 0.85714 | 5 | -0.095816 | 0.0081542
Lucius Spar | 3 | 1 | 1 | 2 | 1 | 8002 | 3 | 1007 | 7.736 | 1 | 155000 | 4 | 4 | 3 | 2165 | 4 | 0.51613 | 5 | 0.14002 | 0.008273
Medusa Spar | 3 | 2 | 1 | 2 | 1 | 4077 | 4 | 579 | 0.2 | 1 | 58333.3333 | 2 | 3 | 3 | 675 | 1 | 0.68571 | 1 | 0.74266 | 0.365
Gulfstar 1 | 3 | 1 | 2 | 1 | 3 | 7813 | 3 | 1132 | 2.3 | 1 | 109166.6667 | 3 | 2 | 3 | 1310 | 2 | 0.73282 | 3 | 0.12191 | 0.47826
Devil's Tower Spar | 3 | 3 | 1 | 1 | 3 | 4189 | 4 | 739 | 0.2 | 1 | 66666.6667 | 2 | 2 | 3 | 1710 | 2 | 0.9 | 1 | 0.41949 | 0.06
Kikeh Spar | 2 | 5 | 1 | 2 | 1 | 5513 | 3 | 939 | 0.5 | 1 | 142500 | 3 | 4 | 3 | 1330 | 1 | 0.84211 | 4 | -0.015974 | 0.28571
Kizomba A Wellhead TLP | 1 | 4 | 2 | 2 | 1 | 4253 | 3 | 1073 | 0.65 | 1 | 250000 | 6 | 1 | 2 | 1175 | 3 | 1 | 2 | 0.0055918 | 0.13333
Kizomba B Wellhead TLP | 1 | 3 | 2 | 2 | 1 | 4756 | 3 | 1071 | 0.6 | 1 | 250000 | 6 | 1 | 2 | 1250 | 5 | 1 | 2 | -0.14006 | 0.13333
Okume TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.1425 | 1 | 30000 | 1 | 1 | 2 | 500 | 4 | 0.83333 | 4 | 0.04 | 0
Oveng TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.1425 | 1 | 30000 | 1 | 1 | 2 | 280 | 4 | 0.83333 | 4 | 0.04 | 0
P 61 Wellhead TLP | 6 | 5 | 3 | 2 | 1 | 7213 | 3 | 1475 | 1.07 | 1 | 145833.3333 | 3 | 3 | 2 | 1180 | 1 | 0.96 | 2 | 0.35051 | 0
Auger TLP | 3 | 2 | 2 | 2 | 1 | 287 | 3 | 1233 | 0.86364 | 1 | 65000 | 2 | 4 | 2 | 870 | 2 | 0.61538 | 4 | 0.044607 | 0.38947
Magnolia TLP | 3 | 1 | 2 | 2 | 1 | 4392 | 3 | 1040 | 0.6 | 1 | 75000 | 2 | 4 | 2 | 1432 | 2 | 0.66667 | 5 | 0.038462 | 0
Brutus TLP | 3 | 1 | 2 | 2 | 1 | 3570 | 3 | 674 | 0.76 | 1 | 155000 | 4 | 2 | 2 | 910 | 4 | 0.83871 | 4 | 0.038576 | 0.078947
Stampede TLP | 3 | 1 | 1 | 2 | 1 | 8523 | 3 | 1982 | 6.2 | 1 | 86666.6667 | 2 | 1 | 2 | 1160 | 4 | 0.92308 | 5 | -0.1221 | -0.12903
Neptune TLP | 3 | 2 | 1 | 2 | 1 | 5670 | 3 | 887 | 0.85 | 1 | 58333.3333 | 2 | 2 | 2 | 1300 | 2 | 0.85714 | 3 | 0.2345 | 0.47882
Shenzi TLP | 3 | 2 | 1 | 2 | 1 | 6001 | 3 | 1119 | 4.41 | 1 | 116666.6667 | 3 | 2 | 2 | 1333 | 2 | 0.85714 | 5 | -0.088472 | 0
Mars TLP | 3 | 1 | 2 | 2 | 1 | 1381 | 3 | 1098 | 1.2 | 1 | 230833.3333 | 5 | 2 | 2 | 896 | 4 | 0.86643 | 4 | -0.090164 | -0.054167
Olympus TLP | 3 | 1 | 2 | 2 | 1 | 7729 | 3 | 1202 | 3 | 1 | 116666.6667 | 3 | 2 | 2 | 945 | 5 | 0.85714 | 5 | -0.12562 | 0
Ursa TLP | 3 | 1 | 2 | 2 | 1 | 2398 | 3 | 1040 | 1.45 | 1 | 216666.6667 | 5 | 3 | 2 | 1160 | 5 | 0.69231 | 4 | -0.081731 | 0.043448
Ram Powell TLP | 3 | 1 | 2 | 2 | 1 | 1885 | 3 | 915 | 1 | 1 | 93333.3333 | 2 | 3 | 2 | 990 | 5 | 0.64286 | 4 | 0.015301 | 0

## Sch_2
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun
Lingshui Semi | SEA CH | 5 | NOC | 2 | 1 | 10439 | EPC | 700 | 3.1 | 1 | 67166.6667 | 2 | 2 | SEMI | 980 | 2 | 0.14888 | 4 | 0.76
Bohai Ming Zhu | SEA CH | 5 | NOC | 2 | 1 | 4350 | EPC | 259 | 0.4 | 1 | 40000 | 1 | 2 | FPSO | 30 | 1 | 1 | 1 | 0.47104
Petrojarl Varg | NE | 1 | OC | 1 | 1 | 2240 | EPC | 816 | 0.46 | 1 | 65833.3333 | 2 | 2 | FPSO | 84 | 1 | 0.86582 | 2 | 0.28676
Stybarrow Venture MV16 | AUST/NZ | 3 | IOC | 1 | 3 | 5922 | EPC | 702 | 0.59843 | 1 | 87500 | 2 | 3 | FPSO | 825 | 2 | 0.91429 | 4 | -0.14387
Alima FPU | AFRICA | 2 | IOC | 2 | 1 | 5720 | EPC | 994 | 1.133 | 1 | 100000 | 3 | 1 | BARGE | 600 | 3 | 0.9 | 4 | -0.022133
Jangkrik | SEA | 4 | OC | 2 | 1 | 8824 | EPC | 1052 | 2.6765 | 1 | 79400 | 2 | 2 | BARGE | 120 | 2 | 0.055416 | 3 | 0.11407
Prelude | AUST/NZ | 3 | IOC | 2 | 1 | 7814 | EPC | 2229 | 11.16 | 1 | 148333.3333 | 6 | 5 | FLNG | 250 | 1 | 0.23596 | 5 | 0.24316
CLOV FPSO | AFRICA | 3 | IOC | 2 | 1 | 7534 | EPC | 1383 | 7 | 1 | 198333.3333 | 4 | 2 | FPSO | 1290 | 4 | 0.80672 | 5 | 0.0079537
Dalia | AFRICA | 4 | IOC | 2 | 1 | 4872 | EPC | 1306 | 3.4 | 1 | 287000 | 6 | 3 | FPSO | 1360 | 5 | 0.83624 | 2 | 0.01072
Girassol | AFRICA | 4 | IOC | 2 | 1 | 3103 | EPC | 823 | 2.5 | 1 | 246666.6667 | 5 | 3 | FPSO | 1350 | 1 | 0.81081 | 1 | 0.52126
Kaombo Norte | AFRICA | 5 | IOC | 2 | 1 | 8871 | EPC | 1081 | 1.5 | 2 | 131666.6667 | 3 | 2 | FPSO | 1600 | 2 | 0.87342 | 3 | 0.44773
Kaombo Sul | AFRICA | 5 | IOC | 2 | 1 | 8871 | EPC | 1173 | 1.5 | 2 | 131666.6667 | 3 | 2 | FPSO | 1600 | 2 | 0.87342 | 3 | 0.54646
Kizomba B | AFRICA | 3 | IOC | 2 | 1 | 4756 | EPC | 1071 | 0.76 | 1 | 316666.6667 | 6 | 1 | FPSO | 1250 | 5 | 0.78947 | 2 | -0.14006
Mondo | AFRICA | 4 | IOC | 1 | 1 | 5866 | EPC | 797 | 0.75 | 2 | 115833.3333 | 3 | 1 | FPSO | 728 | 3 | 0.86331 | 3 | -0.10163
Saxi-Batuque | AFRICA | 4 | IOC | 1 | 3 | 5866 | EPC | 797 | 0.75 | 2 | 130000 | 3 | 1 | FPSO | 720 | 3 | 0.80769 | 3 | -0.084065
Greater Plutonio | AFRICA | 3 | IOC | 2 | 1 | 5144 | EPC | 1124 | 1.73 | 1 | 305000 | 6 | 3 | FPSO | 1350 | 2 | 0.81967 | 4 | 0.19039
PSVM FPSO | AFRICA | 5 | IOC | 2 | 1 | 6755 | EPC | 1249 | 10 | 2 | 197833.3333 | 4 | 5 | FPSO | 2000 | 2 | 0.7936 | 1 | 0.29704
Sanha LPG | AFRICA | 1 | IOC | 2 | 1 | 4687 | EPC | 821 | 1.9 | 1 | 37405.31 | 4 | 3 | FPSO | 58 | 1 | 0.99906 | 3 | 0.036541
Baobab Ivoirien MV10 | AFRICA | 1 | OC | 1 | 3 | 4949 | EPC | 711 | 1.5 | 2 | 82500 | 2 | 1 | FPSO | 970 | 3 | 0.84848 | 2 | 0.067511
Prof. John Evans Atta Mills | AFRICA | 4 | IOC | 1 | 3 | 8617 | EPC | 1092 | 4.5 | 2 | 108333.3333 | 3 | 1 | FPSO | 1425 | 2 | 0.73846 | 5 | 0.015568
Agbami | AFRICA | 2 | IOC | 2 | 2 | 5539 | EPC | 1126 | 4.1538 | 1 | 325000 | 6 | 2 | FPSO | 1433 | 2 | 0.76923 | 2 | 0.11368
Akpo | AFRICA | 4 | IOC | 2 | 1 | 5606 | TK | 1303 | 2.345 | 1 | 273333.3333 | 6 | 4 | FPSO | 1325 | 1 | 0.67683 | 2 | 0.072141
Bonga | AFRICA | 4 | IOC | 2 | 1 | 4049 | EPC | 1033 | 2.4 | 1 | 253333.3333 | 6 | 3 | FPSO | 1250 | 1 | 0.88816 | 3 | 0.70765
Egina FPSO | AFRICA | 5 | IOC | 2 | 1 | 8540 | EPC | 1595 | 15 | 1 | 260000 | 6 | 2 | FPSO | 1600 | 3 | 0.76923 | 2 | 0.28715
Erha | AFRICA | 4 | IOC | 2 | 1 | 4671 | EPC | 1081 | 2.6 | 1 | 266666.6667 | 6 | 2 | FPSO | 1180 | 2 | 0.7875 | 2 | 0.19334
Kizomba A | AFRICA | 3 | IOC | 2 | 1 | 4253 | EPC | 1073 | 0.77 | 1 | 316666.6667 | 6 | 2 | FPSO | 1250 | 3 | 0.78947 | 2 | 0.0055918
Ichthys Venturer | AUST/NZ | 4 | IOC | 2 | 1 | 8102 | EPC | 1743 | 2 | 1 | 85000 | 2 | 5 | FPSO | 250 | 2 | 1 | 5 | 0.37636
Pyrenees Venture | AUST/NZ | 3 | IOC | 2 | 2 | 6379 | EPC | 1014 | 1.66 | 2 | 106000 | 3 | 4 | FPSO | 200 | 4 | 0.90566 | 5 | 0.0019724
Ngujima Yin | AUST/NZ | 3 | IOC | 2 | 1 | 5993 | EPC | 716 | 0.72 | 2 | 136666.6667 | 3 | 2 | FPSO | 340 | 2 | 0.87805 | 3 | 0.14665
P 50 | BRAZ | 4 | NOC | 2 | 1 | 4557 | CL | 844 | 0.496 | 2 | 215000 | 5 | 4 | FPSO | 1240 | 1 | 0.83721 | 1 | 0.66351
P 43 | BRAZ | 5 | NOC | 2 | 1 | 4199 | TK | 883 | 1.3 | 2 | 185000 | 4 | 3 | FPSO | 800 | 1 | 0.81081 | 1 | 0.43828
P 74 | BRAZ | 5 | NOC | 2 | 1 | 8110 | CL | 1630 | 1.1658 | 2 | 191166.6667 | 4 | 1 | FPSO | 2190 | 4 | 0.78466 | 1 | 0.36748
P 75 | BRAZ | 5 | NOC | 2 | 1 | 8110 | CL | 1721 | 1.22 | 2 | 191166.6667 | 4 | 1 | FPSO | 1875 | 4 | 0.78466 | 1 | 0.52992
P 76 | BRAZ | 5 | NOC | 2 | 1 | 8110 | CL | 1995 | 1.3242 | 2 | 191166.6667 | 4 | 1 | FPSO | 2030 | 4 | 0.78466 | 1 | 0.36491
P 77 | BRAZ | 5 | NOC | 2 | 1 | 8110 | CL | 2086 | 1.22 | 2 | 191166.6667 | 4 | 1 | FPSO | 1875 | 4 | 0.78466 | 1 | 0.30537
P 48 | BRAZ | 5 | NOC | 2 | 1 | 4199 | TK | 1066 | 1.3 | 2 | 185000 | 4 | 1 | FPSO | 1040 | 2 | 0.81081 | 1 | 0.25516
Frade | BRAZ | 3 | IOC | 2 | 1 | 6014 | EPC | 909 | 2 | 2 | 117666.6667 | 3 | 2 | FPSO | 1080 | 1 | 0.84986 | 4 | 0.20902
P 68 | BRAZ | 5 | NOC | 2 | 1 | 7486 | CL | 2557 | 1.4 | 1 | 187000 | 4 | 1 | FPSO | 2165 | 4 | 0.80214 | 1 | 0.33907
P 70 | BRAZ | 5 | NOC | 2 | 1 | 7486 | EPC | 2557 | 1.4 | 1 | 185333.3333 | 4 | 1 | FPSO | 2240 | 4 | 0.80935 | 1 | 0.42785
Cidade de Itaguai MV26 | BRAZ | 4 | NOC | 1 | 3 | 8352 | EPC | 838 | 1.17 | 2 | 196666.6667 | 4 | 1 | FPSO | 2240 | 3 | 0.76271 | 1 | 0.18138
Cidade de Mangaratiba MV24 | BRAZ | 3 | NOC | 1 | 3 | 7971 | EPC | 1021 | 1.1 | 2 | 197166.6667 | 4 | 1 | FPSO | 2200 | 3 | 0.76078 | 1 | 0.059745
P 57 | BRAZ | 5 | NOC | 1 | 2 | 6622 | EPC | 1041 | 1.195 | 2 | 191833.3333 | 4 | 1 | FPSO | 1300 | 4 | 0.93831 | 1 | -0.045149
Pioneiro de Libra | BRAZ | 5 | NOC | 1 | 3 | 8984 | PS | 831 | 1 | 2 | 73333.3333 | 2 | 1 | FPSO | 2200 | 1 | 0.68182 | 1 | 0.45728
Cidade de Marica | BRAZ | 5 | NOC | 1 | 3 | 8481 | EPC | 1075 | 1.75 | 2 | 185000 | 4 | 1 | FPSO | 2120 | 5 | 0.81081 | 2 | -0.042791
Cidade de Saquarema | BRAZ | 5 | NOC | 1 | 3 | 8460 | EPC | 1127 | 1.75 | 2 | 185000 | 4 | 1 | FPSO | 2200 | 5 | 0.81081 | 2 | -0.015084
P 69 | BRAZ | 4 | NOC | 2 | 1 | 7486 | CL | 2557 | 1.4 | 1 | 185333.3333 | 4 | 1 | FPSO | 2165 | 4 | 0.80935 | 1 | 0.18772
P 67 | BRAZ | 4 | NOC | 2 | 1 | 7486 | CL | 2084 | 1.4 | 1 | 179500 | 4 | 1 | FPSO | 2165 | 4 | 0.83565 | 1 | 0.50432
P 66 | BRAZ | 5 | NOC | 2 | 1 | 7486 | CL | 2024 | 1.4 | 1 | 191166.6667 | 4 | 3 | FPSO | 2165 | 4 | 0.78466 | 1 | 0.2332
P 53 | BRAZ | 4 | NOC | 2 | 2 | 5826 | EPC | 779 | 0.758 | 2 | 215000 | 5 | 2 | FPSO | 1080 | 2 | 0.83721 | 2 | 0.38896
P 63 | BRAZ | 5 | NOC | 2 | 1 | 7213 | EPC | 1383 | 1.3 | 2 | 145833.3333 | 3 | 1 | FPSO | 1170 | 2 | 0.96 | 2 | 0.086768
P 58 | BRAZ | 5 | NOC | 2 | 1 | 7268 | EPC | 1481 | 1.03 | 2 | 215333.3333 | 5 | 1 | FPSO | 1400 | 4 | 0.83591 | 1 | 0.39095
Espirito Santo | BRAZ | 5 | IOC | 1 | 3 | 6153 | EPC | 787 | 1.5086 | 2 | 105000 | 3 | 5 | FPSO | 1780 | 1 | 0.95238 | 2 | 0.24778
P 54 | BRAZ | 5 | NOC | 2 | 1 | 5272 | EPC | 1034 | 0.629 | 2 | 215000 | 5 | 3 | FPSO | 1315 | 3 | 0.83721 | 1 | 0.24468
P 62 | BRAZ | 5 | NOC | 2 | 1 | 7336 | CL | 1413 | 1.01 | 2 | 215333.3333 | 5 | 1 | FPSO | 1600 | 4 | 0.83591 | 1 | 0.22647
Cidade de Ilhabela | BRAZ | 4 | NOC | 1 | 3 | 7851 | EPC | 1172 | 1.5 | 2 | 185333.3333 | 4 | 1 | FPSO | 2100 | 2 | 0.80935 | 2 | 0.052048
Cidade de Campos dos Goytacazes MV29 | BRAZ | 4 | NOC | 1 | 3 | 9101 | EPC | 1018 | 1.263 | 2 | 179500 | 4 | 2 | FPSO | 765 | 4 | 0.83565 | 1 | 0.27898
Terra Nova | CAN | 2 | OC | 2 | 1 | 2800 | EPC | 1157 | 1.3 | 1 | 175000 | 4 | 5 | FPSO | 90 | 1 | 0.85714 | 2 | 0.39412
Sea Rose | CAN | 3 | OC | 2 | 1 | 4476 | EPC | 1229 | 0.49 | 1 | 125000 | 3 | 5 | FPSO | 120 | 1 | 0.8 | 4 | 0.072417
Turritella | GOM | 1 | OC | 2 | 1 | 8528 | EPC | 1149 | 1 | 2 | 62500 | 2 | 4 | FPSO | 2900 | 2 | 0.96 | 5 | 0.11227
Asgard A | NE | 3 | OC | 2 | 1 | 2356 | TK | 870 | 5.2941 | 1 | 300000 | 6 | 4 | FPSO | 300 | 1 | 0.66667 | 3 | 0.20805
Balder | NE | 3 | IOC | 2 | 1 | 1826 | TK | 592 | 0.35 | 1 | 90500 | 2 | 5 | FPSO | 125 | 1 | 0.91713 | 1 | 1.9291
Goliat FPSO | NE | 2 | OC | 2 | 1 | 7218 | EPC | 1364 | 3.9 | 1 | 122500 | 3 | 5 | FPSO | 400 | 1 | 0.81633 | 3 | 0.72361
Petrojarl Knarr | NE | 2 | OC | 1 | 3 | 7850 | EPC | 732 | 1.6119 | 1 | 70833.3333 | 2 | 2 | FPSO | 410 | 2 | 0.88941 | 4 | 0.85656
Norne | NE | 3 | OC | 2 | 1 | 1551 | EPC | 1334 | 4.7 | 1 | 261666.6667 | 6 | 4 | FPSO | 380 | 3 | 0.84076 | 2 | -0.12519
Skarv | NE | 2 | IOC | 2 | 1 | 6240 | EPC | 1245 | 5 | 1 | 167500 | 4 | 4 | FPSO | 370 | 1 | 0.47761 | 3 | 0.73494
Armada Kraken | NE | 1 | OC | 1 | 0 | 8719 | EPC | 1136 | 2.5 | 2 | 83333.3333 | 2 | 1 | FPSO | 116 | 1 | 0.96 | 4 | 0.16285
Glen Lyon | NE | 3 | IOC | 2 | 1 | 7729 | EPC | 1949 | 4.78 | 1 | 166666.6667 | 4 | 2 | FPSO | 424 | 1 | 0.78 | 4 | 0.16675
Western Isles FPSO | NE | 1 | OC | 2 | 1 | 8391 | EPC | 952 | 1.6 | 1 | 40000 | 1 | 3 | FPSO | 165 | 2 | 1 | 3 | 0.8792
Belanak Natuna | SEA | 4 | IOC | 2 | 1 | 4250 | TK | 1137 | 1.6 | 1 | 158333.3333 | 4 | 4 | FPSO | 100 | 2 | 0.63158 | 4 | 0.058927
Kikeh FPSO | SEA | 5 | OC | 1 | 3 | 5513 | EPC | 939 | 0.8 | 2 | 143500 | 3 | 2 | FPSO | 1350 | 1 | 0.83624 | 4 | -0.015974
Song Doc Pride MV 19 | SEA | 1 | NOC | 1 | 1 | 6339 | EPC | 417 | 0.25 | 2 | 30000 | 1 | 1 | FPSO | 55 | 2 | 1 | 1 | 0.35012
Thai Binh Vn | SEA | 1 | NOC | 2 | 1 | 4446 | EPC | 611 | 0.714 | 1 | 68333.3333 | 2 | 1 | FPSO | 48 | 2 | 0.95122 | 3 | 0.037643
Hai Yang Shi You 117 | SEA CH | 4 | NOC | 2 | 1 | 5524 | EPC | 897 | 1.8 | 1 | 190000 | 4 | 1 | FPSO | 27 | 1 | 1 | 3 | 0.72798
Hai Yang Shi You 116 | SEA CH | 4 | NOC | 2 | 1 | 5804 | EPC | 723 | 1.2 | 1 | 106000 | 3 | 2 | FPSO | 125 | 1 | 1 | 1 | 0.3195
Unity | AFRICA | 4 | IOC | 2 | 1 | 4018 | EPC | 545 | 1 | 1 | 125000 | 3 | 2 | FSO | 65 | 3 | 1 | 2 | 0.70092
Yoho | AFRICA | 3 | IOC | 2 | 1 | 4196 | EPC | 505 | 1.2 | 2 | 90000 | 2 | 2 | FSO | 56 | 1 | 1 | 1 | 0.20792
Yoho | AFRICA | 3 | IOC | 2 | 1 | 4623 | EPC | 761 | 1.2 | 2 | 116666.6667 | 3 | 2 | FSO | 56 | 3 | 0.85714 | 2 | 0.6636
Randgrid | NE | 2 | OC | 1 | 0 | 8521 | EPC | 1386 | 3.7 | 2 | 0 | 1 | 1 | FSO | 116 | 2 | 1 | 3 | 0.097403
Hanne Knutsen | NE | 2 | IOC | 1 | 3 | 8124 | EPC | 1691 | 2.8649 | 2 | 100000 | 3 | 3 | FSO | 115 | 1 | 1 | 2 | 0.80958
Ailsa FSO | NE | 2 | IOC | 2 | 1 | 9389 | EPC | 1364 | 4.7 | 1 | 108333.3333 | 3 | 2 | FSO | 90 | 5 | 0.23077 | 5 | 0
Gagak Rimang | SEA | 5 | IOC | 2 | 1 | 7891 | EPC | 1110 | 1.2 | 2 | 165000 | 4 | 2 | FSO | 33 | 1 | 1 | 2 | 0.42973
Rang Dong MV17 | SEA | 1 | NOC | 1 | 3 | 6038 | EPC | 763 | 0.5 | 1 | 60000 | 2 | 1 | FSO | 60 | 2 | 1 | 1 | 0.10747
Ichthys Explorer | AUST/NZ | 4 | OC | 2 | 1 | 8046 | EPC | 1810 | 3 | 1 | 361166.6667 | 6 | 4 | SEMI | 250 | 2 | 0.23535 | 5 | 0.35635
P 51 | BRAZ | 5 | NOC | 2 | 1 | 5201 | EPC | 1418 | 0.83 | 1 | 215000 | 5 | 2 | SEMI | 1250 | 5 | 0.83721 | 1 | 0.24401
P 56 | BRAZ | 5 | NOC | 2 | 1 | 6478 | EPC | 1114 | 1.4 | 1 | 135000 | 3 | 1 | SEMI | 1670 | 5 | 0.74074 | 1 | 0.27379
P 52 | BRAZ | 5 | NOC | 1 | 3 | 5060 | EPC | 1237 | 0.906 | 1 | 235000 | 5 | 2 | SEMI | 1850 | 3 | 0.76596 | 1 | 0.19644
P 55 | BRAZ | 5 | NOC | 2 | 1 | 6517 | EPC | 1518 | 1.65 | 1 | 215333.3333 | 5 | 2 | SEMI | 1790 | 3 | 0.83591 | 1 | 0.49144
Atlantis | GOM | 3 | IOC | 2 | 1 | 4533 | EPC | 1492 | 2.5 | 1 | 230000 | 5 | 3 | SEMI | 2145 | 3 | 0.86957 | 1 | 0.60389
Delta House (Opti-Ex II) | GOM | 1 | OC | 2 | 1 | 8158 | EPC | 1093 | 2 | 1 | 140000 | 3 | 2 | SEMI | 1372 | 5 | 0.71429 | 2 | -0.012809
Blind Faith | GOM | 2 | IOC | 2 | 1 | 5802 | EPC | 846 | 1.151 | 1 | 52500 | 2 | 4 | SEMI | 2130 | 1 | 0.85714 | 5 | 0.28605
Thunder Hawk | GOM | 1 | OC | 1 | 3 | 6086 | EPC | 958 | 0.8 | 1 | 56666.6667 | 2 | 1 | SEMI | 1847 | 4 | 0.79412 | 5 | 0.087683
Thunder Horse | GOM | 3 | IOC | 2 | 1 | 4624 | EPC | 1098 | 5 | 1 | 283333.3333 | 6 | 5 | SEMI | 1830 | 1 | 0.88235 | 4 | 0.92623
Jack / St. Malo Semi | GOM | 1 | IOC | 2 | 1 | 7270 | EPC | 1844 | 7.5 | 1 | 177166.6667 | 4 | 1 | SEMI | 2134 | 4 | 0.95955 | 5 | -0.005423
Asgard B | NE | 4 | OC | 2 | 1 | 2356 | TK | 1570 | 1.3 | 1 | 351666.6667 | 6 | 1 | SEMI | 300 | 5 | 0.38389 | 4 | 0
Gjoa | NE | 2 | OC | 2 | 1 | 6025 | CL | 1461 | 4.4361 | 1 | 108333.3333 | 3 | 4 | SEMI | 380 | 1 | 0.46154 | 3 | 0.08898
Kristin | NE | 4 | OC | 2 | 1 | 4368 | EPC | 1384 | 1.9 | 1 | 128000 | 3 | 5 | SEMI | 370 | 1 | 0.97656 | 2 | 0.023844
Snorre B | NE | 4 | OC | 2 | 1 | 3256 | EPC | 943 | 1.2821 | 1 | 115000 | 3 | 1 | SEMI | 310 | 4 | 1 | 2 | -0.064687
Troll C | NE | 3 | OC | 2 | 1 | 2647 | EPC | 821 | 4.5 | 1 | 243333.3333 | 5 | 5 | SEMI | 340 | 4 | 0.78082 | 3 | 0.18636
Troll B | NE | 3 | OC | 2 | 1 | 379 | EPC | 1263 | 2.9 | 1 | 317000 | 6 | 5 | SEMI | 320 | 2 | 0.85174 | 3 | 0.35234
Visund | NE | 5 | OC | 2 | 1 | 2251 | TK | 851 | 0.7 | 1 | 171333.3333 | 4 | 5 | SEMI | 335 | 1 | 0.65953 | 2 | 0.3396
Gumusut Semi | SEA | 5 | IOC | 1 | 3 | 6588 | EPC | 1233 | 1.6 | 1 | 200000 | 5 | 2 | SEMI | 1220 | 2 | 0.75 | 3 | 0.99919
Perdido Spar | GOM | 2 | IOC | 2 | 1 | 6025 | EPC | 974 | 3 | 1 | 133333.3333 | 3 | 5 | SPAR | 2440 | 1 | 0.75 | 3 | 0.40554
Front Runner Spar | GOM | 2 | OC | 2 | 1 | 4459 | TK | 728 | 0.2 | 1 | 78333.3333 | 2 | 3 | SPAR | 1015 | 1 | 0.76596 | 1 | 0.36676
Tahiti Spar | GOM | 2 | IOC | 2 | 1 | 5597 | EPC | 1159 | 3.5 | 1 | 136666.6667 | 3 | 3 | SPAR | 1280 | 2 | 0.91463 | 2 | 0.26747
Holstein | GOM | 1 | IOC | 2 | 1 | 4070 | EPC | 859 | 1 | 1 | 135000 | 3 | 4 | SPAR | 1345 | 2 | 0.81481 | 3 | 0.6135
Mad Dog | GOM | 1 | IOC | 2 | 1 | 4070 | EPC | 1397 | 1.82 | 1 | 66666.6667 | 2 | 2 | SPAR | 1370 | 1 | 0.9 | 4 | 0.022906
Heidelberg Spar | GOM | 1 | OC | 2 | 1 | 8018 | EPC | 1649 | 6.745 | 1 | 93333.3333 | 2 | 4 | SPAR | 1620 | 5 | 0.85714 | 5 | -0.095816
Lucius Spar | GOM | 1 | OC | 2 | 1 | 8002 | EPC | 1007 | 7.736 | 1 | 155000 | 4 | 4 | SPAR | 2165 | 4 | 0.51613 | 5 | 0.14002
Medusa Spar | GOM | 2 | OC | 2 | 1 | 4077 | TK | 579 | 0.2 | 1 | 58333.3333 | 2 | 3 | SPAR | 675 | 1 | 0.68571 | 1 | 0.74266
Gulfstar 1 | GOM | 1 | IOC | 1 | 3 | 7813 | EPC | 1132 | 2.3 | 1 | 109166.6667 | 3 | 2 | SPAR | 1310 | 2 | 0.73282 | 3 | 0.12191
Devil's Tower Spar | GOM | 3 | OC | 1 | 3 | 4189 | TK | 739 | 0.2 | 1 | 66666.6667 | 2 | 2 | SPAR | 1710 | 2 | 0.9 | 1 | 0.41949
Kikeh Spar | SEA | 5 | OC | 2 | 1 | 5513 | EPC | 939 | 0.5 | 1 | 142500 | 3 | 4 | SPAR | 1330 | 1 | 0.84211 | 4 | -0.015974
Kizomba A Wellhead TLP | AFRICA | 4 | IOC | 2 | 1 | 4253 | EPC | 1073 | 0.65 | 1 | 250000 | 6 | 1 | TLP | 1175 | 3 | 1 | 2 | 0.0055918
Kizomba B Wellhead TLP | AFRICA | 3 | IOC | 2 | 1 | 4756 | EPC | 1071 | 0.6 | 1 | 250000 | 6 | 1 | TLP | 1250 | 5 | 1 | 2 | -0.14006
Okume TLP | AFRICA | 2 | OC | 2 | 1 | 5414 | EPC | 550 | 0.1425 | 1 | 30000 | 1 | 1 | TLP | 500 | 4 | 0.83333 | 4 | 0.04
Oveng TLP | AFRICA | 2 | OC | 2 | 1 | 5414 | EPC | 550 | 0.1425 | 1 | 30000 | 1 | 1 | TLP | 280 | 4 | 0.83333 | 4 | 0.04
P 61 Wellhead TLP | BRAZ | 5 | NOC | 2 | 1 | 7213 | EPC | 1475 | 1.07 | 1 | 145833.3333 | 3 | 3 | TLP | 1180 | 1 | 0.96 | 2 | 0.35051
Auger TLP | GOM | 2 | IOC | 2 | 1 | 287 | EPC | 1233 | 0.86364 | 1 | 65000 | 2 | 4 | TLP | 870 | 2 | 0.61538 | 4 | 0.044607
Magnolia TLP | GOM | 1 | IOC | 2 | 1 | 4392 | EPC | 1040 | 0.6 | 1 | 75000 | 2 | 4 | TLP | 1432 | 2 | 0.66667 | 5 | 0.038462
Brutus TLP | GOM | 1 | IOC | 2 | 1 | 3570 | EPC | 674 | 0.76 | 1 | 155000 | 4 | 2 | TLP | 910 | 4 | 0.83871 | 4 | 0.038576
Stampede TLP | GOM | 1 | OC | 2 | 1 | 8523 | EPC | 1982 | 6.2 | 1 | 86666.6667 | 2 | 1 | TLP | 1160 | 4 | 0.92308 | 5 | -0.1221
Neptune TLP | GOM | 2 | OC | 2 | 1 | 5670 | EPC | 887 | 0.85 | 1 | 58333.3333 | 2 | 2 | TLP | 1300 | 2 | 0.85714 | 3 | 0.2345
Shenzi TLP | GOM | 2 | OC | 2 | 1 | 6001 | EPC | 1119 | 4.41 | 1 | 116666.6667 | 3 | 2 | TLP | 1333 | 2 | 0.85714 | 5 | -0.088472
Mars TLP | GOM | 1 | IOC | 2 | 1 | 1381 | EPC | 1098 | 1.2 | 1 | 230833.3333 | 5 | 2 | TLP | 896 | 4 | 0.86643 | 4 | -0.090164
Olympus TLP | GOM | 1 | IOC | 2 | 1 | 7729 | EPC | 1202 | 3 | 1 | 116666.6667 | 3 | 2 | TLP | 945 | 5 | 0.85714 | 5 | -0.12562
Ursa TLP | GOM | 1 | IOC | 2 | 1 | 2398 | EPC | 1040 | 1.45 | 1 | 216666.6667 | 5 | 3 | TLP | 1160 | 5 | 0.69231 | 4 | -0.081731
Ram Powell TLP | GOM | 1 | IOC | 2 | 1 | 1885 | EPC | 915 | 1 | 1 | 93333.3333 | 2 | 3 | TLP | 990 | 5 | 0.64286 | 4 | 0.015301

## Sch_T2
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun
Lingshui Semi | SEA CH | 5 | NOC | 2 | 1 | 10439 | EPC | 700 | 3.1 | 1 | 67166.6667 | 2 | 2 | SEMI | 980 | 2 | 0.14888 | 4 | 0.76
Bohai Ming Zhu | SEA CH | 5 | NOC | 2 | 1 | 4350 | EPC | 259 | 0.4 | 1 | 40000 | 1 | 2 | FPSO | 30 | 1 | 1 | 1 | 0.47104
Petrojarl Varg | NE | 1 | OC | 1 | 1 | 2240 | EPC | 816 | 0.46 | 1 | 65833.3333 | 2 | 2 | FPSO | 84 | 1 | 0.86582 | 2 | 0.28676
Stybarrow Venture MV16 | AUST/NZ | 3 | IOC | 1 | 3 | 5922 | EPC | 702 | 0.59843 | 1 | 87500 | 2 | 3 | FPSO | 825 | 2 | 0.91429 | 4 | -0.14387
Alima FPU | AFRICA | 2 | IOC | 2 | 1 | 5720 | EPC | 994 | 1.133 | 1 | 100000 | 3 | 1 | BARGE | 600 | 3 | 0.9 | 4 | -0.022133
Jangkrik | SEA | 4 | OC | 2 | 1 | 8824 | EPC | 1052 | 2.6765 | 1 | 79400 | 2 | 2 | BARGE | 120 | 2 | 0.055416 | 3 | 0.11407
Prelude | AUST/NZ | 3 | IOC | 2 | 1 | 7814 | EPC | 2229 | 11.16 | 1 | 148333.3333 | 6 | 5 | FLNG | 250 | 1 | 0.23596 | 5 | 0.24316
CLOV FPSO | AFRICA | 3 | IOC | 2 | 1 | 7534 | EPC | 1383 | 7 | 1 | 198333.3333 | 4 | 2 | FPSO | 1290 | 4 | 0.80672 | 5 | 0.0079537
Dalia | AFRICA | 4 | IOC | 2 | 1 | 4872 | EPC | 1306 | 3.4 | 1 | 287000 | 6 | 3 | FPSO | 1360 | 5 | 0.83624 | 2 | 0.01072
Girassol | AFRICA | 4 | IOC | 2 | 1 | 3103 | EPC | 823 | 2.5 | 1 | 246666.6667 | 5 | 3 | FPSO | 1350 | 1 | 0.81081 | 1 | 0.52126
Kaombo Norte | AFRICA | 5 | IOC | 2 | 1 | 8871 | EPC | 1081 | 1.5 | 2 | 131666.6667 | 3 | 2 | FPSO | 1600 | 2 | 0.87342 | 3 | 0.44773
Kaombo Sul | AFRICA | 5 | IOC | 2 | 1 | 8871 | EPC | 1173 | 1.5 | 2 | 131666.6667 | 3 | 2 | FPSO | 1600 | 2 | 0.87342 | 3 | 0.54646
Kizomba B | AFRICA | 3 | IOC | 2 | 1 | 4756 | EPC | 1071 | 0.76 | 1 | 316666.6667 | 6 | 1 | FPSO | 1250 | 5 | 0.78947 | 2 | -0.14006
Mondo | AFRICA | 4 | IOC | 1 | 1 | 5866 | EPC | 797 | 0.75 | 2 | 115833.3333 | 3 | 1 | FPSO | 728 | 3 | 0.86331 | 3 | -0.10163
Saxi-Batuque | AFRICA | 4 | IOC | 1 | 3 | 5866 | EPC | 797 | 0.75 | 2 | 130000 | 3 | 1 | FPSO | 720 | 3 | 0.80769 | 3 | -0.084065
Greater Plutonio | AFRICA | 3 | IOC | 2 | 1 | 5144 | EPC | 1124 | 1.73 | 1 | 305000 | 6 | 3 | FPSO | 1350 | 2 | 0.81967 | 4 | 0.19039
PSVM FPSO | AFRICA | 5 | IOC | 2 | 1 | 6755 | EPC | 1249 | 10 | 2 | 197833.3333 | 4 | 5 | FPSO | 2000 | 2 | 0.7936 | 1 | 0.29704
Sanha LPG | AFRICA | 1 | IOC | 2 | 1 | 4687 | EPC | 821 | 1.9 | 1 | 37405.31 | 4 | 3 | FPSO | 58 | 1 | 0.99906 | 3 | 0.036541
Baobab Ivoirien MV10 | AFRICA | 1 | OC | 1 | 3 | 4949 | EPC | 711 | 1.5 | 2 | 82500 | 2 | 1 | FPSO | 970 | 3 | 0.84848 | 2 | 0.067511
Prof. John Evans Atta Mills | AFRICA | 4 | IOC | 1 | 3 | 8617 | EPC | 1092 | 4.5 | 2 | 108333.3333 | 3 | 1 | FPSO | 1425 | 2 | 0.73846 | 5 | 0.015568
Agbami | AFRICA | 2 | IOC | 2 | 2 | 5539 | EPC | 1126 | 4.1538 | 1 | 325000 | 6 | 2 | FPSO | 1433 | 2 | 0.76923 | 2 | 0.11368
Akpo | AFRICA | 4 | IOC | 2 | 1 | 5606 | TK | 1303 | 2.345 | 1 | 273333.3333 | 6 | 4 | FPSO | 1325 | 1 | 0.67683 | 2 | 0.072141
Bonga | AFRICA | 4 | IOC | 2 | 1 | 4049 | EPC | 1033 | 2.4 | 1 | 253333.3333 | 6 | 3 | FPSO | 1250 | 1 | 0.88816 | 3 | 0.70765
Egina FPSO | AFRICA | 5 | IOC | 2 | 1 | 8540 | EPC | 1595 | 15 | 1 | 260000 | 6 | 2 | FPSO | 1600 | 3 | 0.76923 | 2 | 0.28715
Erha | AFRICA | 4 | IOC | 2 | 1 | 4671 | EPC | 1081 | 2.6 | 1 | 266666.6667 | 6 | 2 | FPSO | 1180 | 2 | 0.7875 | 2 | 0.19334
Kizomba A | AFRICA | 3 | IOC | 2 | 1 | 4253 | EPC | 1073 | 0.77 | 1 | 316666.6667 | 6 | 2 | FPSO | 1250 | 3 | 0.78947 | 2 | 0.0055918
Ichthys Venturer | AUST/NZ | 4 | IOC | 2 | 1 | 8102 | EPC | 1743 | 2 | 1 | 85000 | 2 | 5 | FPSO | 250 | 2 | 1 | 5 | 0.37636
Pyrenees Venture | AUST/NZ | 3 | IOC | 2 | 2 | 6379 | EPC | 1014 | 1.66 | 2 | 106000 | 3 | 4 | FPSO | 200 | 4 | 0.90566 | 5 | 0.0019724
Ngujima Yin | AUST/NZ | 3 | IOC | 2 | 1 | 5993 | EPC | 716 | 0.72 | 2 | 136666.6667 | 3 | 2 | FPSO | 340 | 2 | 0.87805 | 3 | 0.14665
P 50 | BRAZ | 4 | NOC | 2 | 1 | 4557 | CL | 844 | 0.496 | 2 | 215000 | 5 | 4 | FPSO | 1240 | 1 | 0.83721 | 1 | 0.66351
P 43 | BRAZ | 5 | NOC | 2 | 1 | 4199 | TK | 883 | 1.3 | 2 | 185000 | 4 | 3 | FPSO | 800 | 1 | 0.81081 | 1 | 0.43828
P 74 | BRAZ | 5 | NOC | 2 | 1 | 8110 | CL | 1630 | 1.1658 | 2 | 191166.6667 | 4 | 1 | FPSO | 2190 | 4 | 0.78466 | 1 | 0.36748
P 75 | BRAZ | 5 | NOC | 2 | 1 | 8110 | CL | 1721 | 1.22 | 2 | 191166.6667 | 4 | 1 | FPSO | 1875 | 4 | 0.78466 | 1 | 0.52992
P 76 | BRAZ | 5 | NOC | 2 | 1 | 8110 | CL | 1995 | 1.3242 | 2 | 191166.6667 | 4 | 1 | FPSO | 2030 | 4 | 0.78466 | 1 | 0.36491
P 77 | BRAZ | 5 | NOC | 2 | 1 | 8110 | CL | 2086 | 1.22 | 2 | 191166.6667 | 4 | 1 | FPSO | 1875 | 4 | 0.78466 | 1 | 0.30537
P 48 | BRAZ | 5 | NOC | 2 | 1 | 4199 | TK | 1066 | 1.3 | 2 | 185000 | 4 | 1 | FPSO | 1040 | 2 | 0.81081 | 1 | 0.25516
Frade | BRAZ | 3 | IOC | 2 | 1 | 6014 | EPC | 909 | 2 | 2 | 117666.6667 | 3 | 2 | FPSO | 1080 | 1 | 0.84986 | 4 | 0.20902
P 68 | BRAZ | 5 | NOC | 2 | 1 | 7486 | CL | 2557 | 1.4 | 1 | 187000 | 4 | 1 | FPSO | 2165 | 4 | 0.80214 | 1 | 0.33907
P 70 | BRAZ | 5 | NOC | 2 | 1 | 7486 | EPC | 2557 | 1.4 | 1 | 185333.3333 | 4 | 1 | FPSO | 2240 | 4 | 0.80935 | 1 | 0.42785
Cidade de Itaguai MV26 | BRAZ | 4 | NOC | 1 | 3 | 8352 | EPC | 838 | 1.17 | 2 | 196666.6667 | 4 | 1 | FPSO | 2240 | 3 | 0.76271 | 1 | 0.18138
Cidade de Mangaratiba MV24 | BRAZ | 3 | NOC | 1 | 3 | 7971 | EPC | 1021 | 1.1 | 2 | 197166.6667 | 4 | 1 | FPSO | 2200 | 3 | 0.76078 | 1 | 0.059745
P 57 | BRAZ | 5 | NOC | 1 | 2 | 6622 | EPC | 1041 | 1.195 | 2 | 191833.3333 | 4 | 1 | FPSO | 1300 | 4 | 0.93831 | 1 | -0.045149
Pioneiro de Libra | BRAZ | 5 | NOC | 1 | 3 | 8984 | PS | 831 | 1 | 2 | 73333.3333 | 2 | 1 | FPSO | 2200 | 1 | 0.68182 | 1 | 0.45728
Cidade de Marica | BRAZ | 5 | NOC | 1 | 3 | 8481 | EPC | 1075 | 1.75 | 2 | 185000 | 4 | 1 | FPSO | 2120 | 5 | 0.81081 | 2 | -0.042791
Cidade de Saquarema | BRAZ | 5 | NOC | 1 | 3 | 8460 | EPC | 1127 | 1.75 | 2 | 185000 | 4 | 1 | FPSO | 2200 | 5 | 0.81081 | 2 | -0.015084
P 69 | BRAZ | 4 | NOC | 2 | 1 | 7486 | CL | 2557 | 1.4 | 1 | 185333.3333 | 4 | 1 | FPSO | 2165 | 4 | 0.80935 | 1 | 0.18772
P 67 | BRAZ | 4 | NOC | 2 | 1 | 7486 | CL | 2084 | 1.4 | 1 | 179500 | 4 | 1 | FPSO | 2165 | 4 | 0.83565 | 1 | 0.50432
P 66 | BRAZ | 5 | NOC | 2 | 1 | 7486 | CL | 2024 | 1.4 | 1 | 191166.6667 | 4 | 3 | FPSO | 2165 | 4 | 0.78466 | 1 | 0.2332
P 53 | BRAZ | 4 | NOC | 2 | 2 | 5826 | EPC | 779 | 0.758 | 2 | 215000 | 5 | 2 | FPSO | 1080 | 2 | 0.83721 | 2 | 0.38896
P 63 | BRAZ | 5 | NOC | 2 | 1 | 7213 | EPC | 1383 | 1.3 | 2 | 145833.3333 | 3 | 1 | FPSO | 1170 | 2 | 0.96 | 2 | 0.086768
P 58 | BRAZ | 5 | NOC | 2 | 1 | 7268 | EPC | 1481 | 1.03 | 2 | 215333.3333 | 5 | 1 | FPSO | 1400 | 4 | 0.83591 | 1 | 0.39095
Espirito Santo | BRAZ | 5 | IOC | 1 | 3 | 6153 | EPC | 787 | 1.5086 | 2 | 105000 | 3 | 5 | FPSO | 1780 | 1 | 0.95238 | 2 | 0.24778
P 54 | BRAZ | 5 | NOC | 2 | 1 | 5272 | EPC | 1034 | 0.629 | 2 | 215000 | 5 | 3 | FPSO | 1315 | 3 | 0.83721 | 1 | 0.24468
P 62 | BRAZ | 5 | NOC | 2 | 1 | 7336 | CL | 1413 | 1.01 | 2 | 215333.3333 | 5 | 1 | FPSO | 1600 | 4 | 0.83591 | 1 | 0.22647
Cidade de Ilhabela | BRAZ | 4 | NOC | 1 | 3 | 7851 | EPC | 1172 | 1.5 | 2 | 185333.3333 | 4 | 1 | FPSO | 2100 | 2 | 0.80935 | 2 | 0.052048
Cidade de Campos dos Goytacazes MV29 | BRAZ | 4 | NOC | 1 | 3 | 9101 | EPC | 1018 | 1.263 | 2 | 179500 | 4 | 2 | FPSO | 765 | 4 | 0.83565 | 1 | 0.27898
Terra Nova | CAN | 2 | OC | 2 | 1 | 2800 | EPC | 1157 | 1.3 | 1 | 175000 | 4 | 5 | FPSO | 90 | 1 | 0.85714 | 2 | 0.39412
Sea Rose | CAN | 3 | OC | 2 | 1 | 4476 | EPC | 1229 | 0.49 | 1 | 125000 | 3 | 5 | FPSO | 120 | 1 | 0.8 | 4 | 0.072417
Turritella | GOM | 1 | OC | 2 | 1 | 8528 | EPC | 1149 | 1 | 2 | 62500 | 2 | 4 | FPSO | 2900 | 2 | 0.96 | 5 | 0.11227
Asgard A | NE | 3 | OC | 2 | 1 | 2356 | TK | 870 | 5.2941 | 1 | 300000 | 6 | 4 | FPSO | 300 | 1 | 0.66667 | 3 | 0.20805
Balder | NE | 3 | IOC | 2 | 1 | 1826 | TK | 592 | 0.35 | 1 | 90500 | 2 | 5 | FPSO | 125 | 1 | 0.91713 | 1 | 1.9291
Goliat FPSO | NE | 2 | OC | 2 | 1 | 7218 | EPC | 1364 | 3.9 | 1 | 122500 | 3 | 5 | FPSO | 400 | 1 | 0.81633 | 3 | 0.72361
Petrojarl Knarr | NE | 2 | OC | 1 | 3 | 7850 | EPC | 732 | 1.6119 | 1 | 70833.3333 | 2 | 2 | FPSO | 410 | 2 | 0.88941 | 4 | 0.85656
Norne | NE | 3 | OC | 2 | 1 | 1551 | EPC | 1334 | 4.7 | 1 | 261666.6667 | 6 | 4 | FPSO | 380 | 3 | 0.84076 | 2 | -0.12519
Skarv | NE | 2 | IOC | 2 | 1 | 6240 | EPC | 1245 | 5 | 1 | 167500 | 4 | 4 | FPSO | 370 | 1 | 0.47761 | 3 | 0.73494
Armada Kraken | NE | 1 | OC | 1 | 0 | 8719 | EPC | 1136 | 2.5 | 2 | 83333.3333 | 2 | 1 | FPSO | 116 | 1 | 0.96 | 4 | 0.16285
Glen Lyon | NE | 3 | IOC | 2 | 1 | 7729 | EPC | 1949 | 4.78 | 1 | 166666.6667 | 4 | 2 | FPSO | 424 | 1 | 0.78 | 4 | 0.16675
Western Isles FPSO | NE | 1 | OC | 2 | 1 | 8391 | EPC | 952 | 1.6 | 1 | 40000 | 1 | 3 | FPSO | 165 | 2 | 1 | 3 | 0.8792
Belanak Natuna | SEA | 4 | IOC | 2 | 1 | 4250 | TK | 1137 | 1.6 | 1 | 158333.3333 | 4 | 4 | FPSO | 100 | 2 | 0.63158 | 4 | 0.058927
Kikeh FPSO | SEA | 5 | OC | 1 | 3 | 5513 | EPC | 939 | 0.8 | 2 | 143500 | 3 | 2 | FPSO | 1350 | 1 | 0.83624 | 4 | -0.015974
Song Doc Pride MV 19 | SEA | 1 | NOC | 1 | 1 | 6339 | EPC | 417 | 0.25 | 2 | 30000 | 1 | 1 | FPSO | 55 | 2 | 1 | 1 | 0.35012
Thai Binh Vn | SEA | 1 | NOC | 2 | 1 | 4446 | EPC | 611 | 0.714 | 1 | 68333.3333 | 2 | 1 | FPSO | 48 | 2 | 0.95122 | 3 | 0.037643
Hai Yang Shi You 117 | SEA CH | 4 | NOC | 2 | 1 | 5524 | EPC | 897 | 1.8 | 1 | 190000 | 4 | 1 | FPSO | 27 | 1 | 1 | 3 | 0.72798
Hai Yang Shi You 116 | SEA CH | 4 | NOC | 2 | 1 | 5804 | EPC | 723 | 1.2 | 1 | 106000 | 3 | 2 | FPSO | 125 | 1 | 1 | 1 | 0.3195
Unity | AFRICA | 4 | IOC | 2 | 1 | 4018 | EPC | 545 | 1 | 1 | 125000 | 3 | 2 | FSO | 65 | 3 | 1 | 2 | 0.70092
Yoho | AFRICA | 3 | IOC | 2 | 1 | 4196 | EPC | 505 | 1.2 | 2 | 90000 | 2 | 2 | FSO | 56 | 1 | 1 | 1 | 0.20792
Yoho | AFRICA | 3 | IOC | 2 | 1 | 4623 | EPC | 761 | 1.2 | 2 | 116666.6667 | 3 | 2 | FSO | 56 | 3 | 0.85714 | 2 | 0.6636
Randgrid | NE | 2 | OC | 1 | 0 | 8521 | EPC | 1386 | 3.7 | 2 | 0 | 1 | 1 | FSO | 116 | 2 | 1 | 3 | 0.097403
Hanne Knutsen | NE | 2 | IOC | 1 | 3 | 8124 | EPC | 1691 | 2.8649 | 2 | 100000 | 3 | 3 | FSO | 115 | 1 | 1 | 2 | 0.80958
Ailsa FSO | NE | 2 | IOC | 2 | 1 | 9389 | EPC | 1364 | 4.7 | 1 | 108333.3333 | 3 | 2 | FSO | 90 | 5 | 0.23077 | 5 | 0
Gagak Rimang | SEA | 5 | IOC | 2 | 1 | 7891 | EPC | 1110 | 1.2 | 2 | 165000 | 4 | 2 | FSO | 33 | 1 | 1 | 2 | 0.42973
Rang Dong MV17 | SEA | 1 | NOC | 1 | 3 | 6038 | EPC | 763 | 0.5 | 1 | 60000 | 2 | 1 | FSO | 60 | 2 | 1 | 1 | 0.10747
Ichthys Explorer | AUST/NZ | 4 | OC | 2 | 1 | 8046 | EPC | 1810 | 3 | 1 | 361166.6667 | 6 | 4 | SEMI | 250 | 2 | 0.23535 | 5 | 0.35635
P 51 | BRAZ | 5 | NOC | 2 | 1 | 5201 | EPC | 1418 | 0.83 | 1 | 215000 | 5 | 2 | SEMI | 1250 | 5 | 0.83721 | 1 | 0.24401
P 56 | BRAZ | 5 | NOC | 2 | 1 | 6478 | EPC | 1114 | 1.4 | 1 | 135000 | 3 | 1 | SEMI | 1670 | 5 | 0.74074 | 1 | 0.27379
P 52 | BRAZ | 5 | NOC | 1 | 3 | 5060 | EPC | 1237 | 0.906 | 1 | 235000 | 5 | 2 | SEMI | 1850 | 3 | 0.76596 | 1 | 0.19644
P 55 | BRAZ | 5 | NOC | 2 | 1 | 6517 | EPC | 1518 | 1.65 | 1 | 215333.3333 | 5 | 2 | SEMI | 1790 | 3 | 0.83591 | 1 | 0.49144
Atlantis | GOM | 3 | IOC | 2 | 1 | 4533 | EPC | 1492 | 2.5 | 1 | 230000 | 5 | 3 | SEMI | 2145 | 3 | 0.86957 | 1 | 0.60389
Delta House (Opti-Ex II) | GOM | 1 | OC | 2 | 1 | 8158 | EPC | 1093 | 2 | 1 | 140000 | 3 | 2 | SEMI | 1372 | 5 | 0.71429 | 2 | -0.012809
Blind Faith | GOM | 2 | IOC | 2 | 1 | 5802 | EPC | 846 | 1.151 | 1 | 52500 | 2 | 4 | SEMI | 2130 | 1 | 0.85714 | 5 | 0.28605
Thunder Hawk | GOM | 1 | OC | 1 | 3 | 6086 | EPC | 958 | 0.8 | 1 | 56666.6667 | 2 | 1 | SEMI | 1847 | 4 | 0.79412 | 5 | 0.087683
Thunder Horse | GOM | 3 | IOC | 2 | 1 | 4624 | EPC | 1098 | 5 | 1 | 283333.3333 | 6 | 5 | SEMI | 1830 | 1 | 0.88235 | 4 | 0.92623
Jack / St. Malo Semi | GOM | 1 | IOC | 2 | 1 | 7270 | EPC | 1844 | 7.5 | 1 | 177166.6667 | 4 | 1 | SEMI | 2134 | 4 | 0.95955 | 5 | -0.005423
Asgard B | NE | 4 | OC | 2 | 1 | 2356 | TK | 1570 | 1.3 | 1 | 351666.6667 | 6 | 1 | SEMI | 300 | 5 | 0.38389 | 4 | 0
Gjoa | NE | 2 | OC | 2 | 1 | 6025 | CL | 1461 | 4.4361 | 1 | 108333.3333 | 3 | 4 | SEMI | 380 | 1 | 0.46154 | 3 | 0.08898
Kristin | NE | 4 | OC | 2 | 1 | 4368 | EPC | 1384 | 1.9 | 1 | 128000 | 3 | 5 | SEMI | 370 | 1 | 0.97656 | 2 | 0.023844
Snorre B | NE | 4 | OC | 2 | 1 | 3256 | EPC | 943 | 1.2821 | 1 | 115000 | 3 | 1 | SEMI | 310 | 4 | 1 | 2 | -0.064687
Troll C | NE | 3 | OC | 2 | 1 | 2647 | EPC | 821 | 4.5 | 1 | 243333.3333 | 5 | 5 | SEMI | 340 | 4 | 0.78082 | 3 | 0.18636
Troll B | NE | 3 | OC | 2 | 1 | 379 | EPC | 1263 | 2.9 | 1 | 317000 | 6 | 5 | SEMI | 320 | 2 | 0.85174 | 3 | 0.35234
Visund | NE | 5 | OC | 2 | 1 | 2251 | TK | 851 | 0.7 | 1 | 171333.3333 | 4 | 5 | SEMI | 335 | 1 | 0.65953 | 2 | 0.3396
Gumusut Semi | SEA | 5 | IOC | 1 | 3 | 6588 | EPC | 1233 | 1.6 | 1 | 200000 | 5 | 2 | SEMI | 1220 | 2 | 0.75 | 3 | 0.99919
Perdido Spar | GOM | 2 | IOC | 2 | 1 | 6025 | EPC | 974 | 3 | 1 | 133333.3333 | 3 | 5 | SPAR | 2440 | 1 | 0.75 | 3 | 0.40554
Front Runner Spar | GOM | 2 | OC | 2 | 1 | 4459 | TK | 728 | 0.2 | 1 | 78333.3333 | 2 | 3 | SPAR | 1015 | 1 | 0.76596 | 1 | 0.36676
Tahiti Spar | GOM | 2 | IOC | 2 | 1 | 5597 | EPC | 1159 | 3.5 | 1 | 136666.6667 | 3 | 3 | SPAR | 1280 | 2 | 0.91463 | 2 | 0.26747
Holstein | GOM | 1 | IOC | 2 | 1 | 4070 | EPC | 859 | 1 | 1 | 135000 | 3 | 4 | SPAR | 1345 | 2 | 0.81481 | 3 | 0.6135
Mad Dog | GOM | 1 | IOC | 2 | 1 | 4070 | EPC | 1397 | 1.82 | 1 | 66666.6667 | 2 | 2 | SPAR | 1370 | 1 | 0.9 | 4 | 0.022906
Heidelberg Spar | GOM | 1 | OC | 2 | 1 | 8018 | EPC | 1649 | 6.745 | 1 | 93333.3333 | 2 | 4 | SPAR | 1620 | 5 | 0.85714 | 5 | -0.095816
Lucius Spar | GOM | 1 | OC | 2 | 1 | 8002 | EPC | 1007 | 7.736 | 1 | 155000 | 4 | 4 | SPAR | 2165 | 4 | 0.51613 | 5 | 0.14002
Medusa Spar | GOM | 2 | OC | 2 | 1 | 4077 | TK | 579 | 0.2 | 1 | 58333.3333 | 2 | 3 | SPAR | 675 | 1 | 0.68571 | 1 | 0.74266
Gulfstar 1 | GOM | 1 | IOC | 1 | 3 | 7813 | EPC | 1132 | 2.3 | 1 | 109166.6667 | 3 | 2 | SPAR | 1310 | 2 | 0.73282 | 3 | 0.12191
Devil's Tower Spar | GOM | 3 | OC | 1 | 3 | 4189 | TK | 739 | 0.2 | 1 | 66666.6667 | 2 | 2 | SPAR | 1710 | 2 | 0.9 | 1 | 0.41949
Kikeh Spar | SEA | 5 | OC | 2 | 1 | 5513 | EPC | 939 | 0.5 | 1 | 142500 | 3 | 4 | SPAR | 1330 | 1 | 0.84211 | 4 | -0.015974
Kizomba A Wellhead TLP | AFRICA | 4 | IOC | 2 | 1 | 4253 | EPC | 1073 | 0.65 | 1 | 250000 | 6 | 1 | TLP | 1175 | 3 | 1 | 2 | 0.0055918
Kizomba B Wellhead TLP | AFRICA | 3 | IOC | 2 | 1 | 4756 | EPC | 1071 | 0.6 | 1 | 250000 | 6 | 1 | TLP | 1250 | 5 | 1 | 2 | -0.14006
Okume TLP | AFRICA | 2 | OC | 2 | 1 | 5414 | EPC | 550 | 0.1425 | 1 | 30000 | 1 | 1 | TLP | 500 | 4 | 0.83333 | 4 | 0.04
Oveng TLP | AFRICA | 2 | OC | 2 | 1 | 5414 | EPC | 550 | 0.1425 | 1 | 30000 | 1 | 1 | TLP | 280 | 4 | 0.83333 | 4 | 0.04
P 61 Wellhead TLP | BRAZ | 5 | NOC | 2 | 1 | 7213 | EPC | 1475 | 1.07 | 1 | 145833.3333 | 3 | 3 | TLP | 1180 | 1 | 0.96 | 2 | 0.35051
Auger TLP | GOM | 2 | IOC | 2 | 1 | 287 | EPC | 1233 | 0.86364 | 1 | 65000 | 2 | 4 | TLP | 870 | 2 | 0.61538 | 4 | 0.044607
Magnolia TLP | GOM | 1 | IOC | 2 | 1 | 4392 | EPC | 1040 | 0.6 | 1 | 75000 | 2 | 4 | TLP | 1432 | 2 | 0.66667 | 5 | 0.038462
Brutus TLP | GOM | 1 | IOC | 2 | 1 | 3570 | EPC | 674 | 0.76 | 1 | 155000 | 4 | 2 | TLP | 910 | 4 | 0.83871 | 4 | 0.038576
Stampede TLP | GOM | 1 | OC | 2 | 1 | 8523 | EPC | 1982 | 6.2 | 1 | 86666.6667 | 2 | 1 | TLP | 1160 | 4 | 0.92308 | 5 | -0.1221
Neptune TLP | GOM | 2 | OC | 2 | 1 | 5670 | EPC | 887 | 0.85 | 1 | 58333.3333 | 2 | 2 | TLP | 1300 | 2 | 0.85714 | 3 | 0.2345
Shenzi TLP | GOM | 2 | OC | 2 | 1 | 6001 | EPC | 1119 | 4.41 | 1 | 116666.6667 | 3 | 2 | TLP | 1333 | 2 | 0.85714 | 5 | -0.088472
Mars TLP | GOM | 1 | IOC | 2 | 1 | 1381 | EPC | 1098 | 1.2 | 1 | 230833.3333 | 5 | 2 | TLP | 896 | 4 | 0.86643 | 4 | -0.090164
Olympus TLP | GOM | 1 | IOC | 2 | 1 | 7729 | EPC | 1202 | 3 | 1 | 116666.6667 | 3 | 2 | TLP | 945 | 5 | 0.85714 | 5 | -0.12562
Ursa TLP | GOM | 1 | IOC | 2 | 1 | 2398 | EPC | 1040 | 1.45 | 1 | 216666.6667 | 5 | 3 | TLP | 1160 | 5 | 0.69231 | 4 | -0.081731
Ram Powell TLP | GOM | 1 | IOC | 2 | 1 | 1885 | EPC | 915 | 1 | 1 | 93333.3333 | 2 | 3 | TLP | 990 | 5 | 0.64286 | 4 | 0.015301

## Cost_Sch2
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun
Bohai Ming Zhu | SEA CH | H | NOC | Own | 1 | 4350 | EPC | 259 | 0.4 | NEW | 40000 | VS | L | FPSO | 30 | N | 1 | N | 0.47104 | 0.25
Petrojarl Varg | NE | N | OC | Lease | 1 | 2240 | EPC | 816 | 0.46 | NEW | 65833.3333 | S | L | FPSO | 84 | N | 0.86582 | L | 0.28676 | 0.24
Stybarrow Venture MV16 | AUST/NZ | A | IOC | Lease | 3 | 5922 | EPC | 702 | 0.59843 | NEW | 87500 | S | A | FPSO | 825 | L | 0.91429 | M | -0.14387 | 0.27
Alima FPU | AFRICA | L | IOC | Own | 1 | 5720 | EPC | 994 | 1.133 | NEW | 100000 | M | N | BARGE | 600 | A | 0.9 | M | -0.022133 | 0.35
Jangkrik | SEA | M | OC | Own | 1 | 8824 | EPC | 1052 | 2.6765 | NEW | 79400 | S | L | BARGE | 120 | L | 0.055416 | A | 0.11407 | 0.17
Prelude | AUST/NZ | A | IOC | Own | 1 | 7814 | EPC | 2229 | 11.16 | NEW | 148333.3333 | UL | H | FLNG | 250 | N | 0.23596 | H | 0.24316 | 0.34409
CLOV FPSO | AFRICA | A | IOC | Own | 1 | 7534 | EPC | 1383 | 7 | NEW | 198333.3333 | L | L | FPSO | 1290 | M | 0.80672 | H | 0.0079537 | 0.14286
Dalia | AFRICA | M | IOC | Own | 1 | 4872 | EPC | 1306 | 3.4 | NEW | 287000 | UL | A | FPSO | 1360 | H | 0.83624 | L | 0.01072 | 0.17647
Girassol | AFRICA | M | IOC | Own | 1 | 3103 | EPC | 823 | 2.5 | NEW | 246666.6667 | VL | A | FPSO | 1350 | N | 0.81081 | N | 0.52126 | 0.12
Kizomba B | AFRICA | A | IOC | Own | 1 | 4756 | EPC | 1071 | 0.76 | NEW | 316666.6667 | UL | N | FPSO | 1250 | H | 0.78947 | L | -0.14006 | 0.13333
Mondo | AFRICA | M | IOC | Lease | 1 | 5866 | EPC | 797 | 0.75 | CONV | 115833.3333 | M | N | FPSO | 728 | A | 0.86331 | A | -0.10163 | 0
Saxi-Batuque | AFRICA | M | IOC | Lease | 3 | 5866 | EPC | 797 | 0.75 | CONV | 130000 | M | N | FPSO | 720 | A | 0.80769 | A | -0.084065 | 0
Greater Plutonio | AFRICA | A | IOC | Own | 1 | 5144 | EPC | 1124 | 1.73 | NEW | 305000 | UL | A | FPSO | 1350 | L | 0.81967 | M | 0.19039 | 0.85
PSVM FPSO | AFRICA | H | IOC | Own | 1 | 6755 | EPC | 1249 | 10 | CONV | 197833.3333 | L | H | FPSO | 2000 | L | 0.7936 | N | 0.29704 | 0.4
Baobab Ivoirien MV10 | AFRICA | N | OC | Lease | 3 | 4949 | EPC | 711 | 1.5 | CONV | 82500 | S | N | FPSO | 970 | A | 0.84848 | L | 0.067511 | 0
Prof. John Evans Atta Mills | AFRICA | M | IOC | Lease | 3 | 8617 | EPC | 1092 | 4.5 | CONV | 108333.3333 | M | N | FPSO | 1425 | L | 0.73846 | H | 0.015568 | 0.088889
Agbami | AFRICA | L | IOC | Own | 2 | 5539 | EPC | 1126 | 4.1538 | NEW | 325000 | UL | L | FPSO | 1433 | L | 0.76923 | L | 0.11368 | 0.3
Akpo | AFRICA | M | IOC | Own | 1 | 5606 | TK | 1303 | 2.345 | NEW | 273333.3333 | UL | M | FPSO | 1325 | N | 0.67683 | L | 0.072141 | 1.55
Bonga | AFRICA | M | IOC | Own | 1 | 4049 | EPC | 1033 | 2.4 | NEW | 253333.3333 | UL | A | FPSO | 1250 | N | 0.88816 | A | 0.70765 | 0.5
Egina FPSO | AFRICA | H | IOC | Own | 1 | 8540 | EPC | 1595 | 15 | NEW | 260000 | UL | L | FPSO | 1600 | A | 0.76923 | L | 0.28715 | -0.033333
Erha | AFRICA | M | IOC | Own | 1 | 4671 | EPC | 1081 | 2.6 | NEW | 266666.6667 | UL | L | FPSO | 1180 | L | 0.7875 | L | 0.19334 | 0.57
Kizomba A | AFRICA | A | IOC | Own | 1 | 4253 | EPC | 1073 | 0.77 | NEW | 316666.6667 | UL | L | FPSO | 1250 | A | 0.78947 | L | 0.0055918 | 0.13333
Ichthys Venturer | AUST/NZ | M | IOC | Own | 1 | 8102 | EPC | 1743 | 2 | NEW | 85000 | S | H | FPSO | 250 | L | 1 | H | 0.37636 | 0.32353
Pyrenees Venture | AUST/NZ | A | IOC | Own | 2 | 6379 | EPC | 1014 | 1.66 | CONV | 106000 | M | M | FPSO | 200 | M | 0.90566 | H | 0.0019724 | 0.012028
Ngujima Yin | AUST/NZ | A | IOC | Own | 1 | 5993 | EPC | 716 | 0.72 | CONV | 136666.6667 | M | L | FPSO | 340 | L | 0.87805 | A | 0.14665 | 0.33333
P 50 | BRAZ | M | NOC | Own | 1 | 4557 | CL | 844 | 0.496 | CONV | 215000 | VL | M | FPSO | 1240 | N | 0.83721 | N | 0.66351 | 0.41129
P 43 | BRAZ | H | NOC | Own | 1 | 4199 | TK | 883 | 1.3 | CONV | 185000 | L | A | FPSO | 800 | N | 0.81081 | N | 0.43828 | 0.38462
P 48 | BRAZ | H | NOC | Own | 1 | 4199 | TK | 1066 | 1.3 | CONV | 185000 | L | N | FPSO | 1040 | L | 0.81081 | N | 0.25516 | 0.38462
Frade | BRAZ | A | IOC | Own | 1 | 6014 | EPC | 909 | 2 | CONV | 117666.6667 | M | L | FPSO | 1080 | N | 0.84986 | M | 0.20902 | 1.35
Cidade de Itaguai MV26 | BRAZ | M | NOC | Lease | 3 | 8352 | EPC | 838 | 1.17 | CONV | 196666.6667 | L | N | FPSO | 2240 | A | 0.76271 | N | 0.18138 | 0
P 57 | BRAZ | H | NOC | Lease | 2 | 6622 | EPC | 1041 | 1.195 | CONV | 191833.3333 | L | N | FPSO | 1300 | M | 0.93831 | N | -0.045149 | 0.0041841
Pioneiro de Libra | BRAZ | H | NOC | Lease | 3 | 8984 | PS | 831 | 1 | CONV | 73333.3333 | S | N | FPSO | 2200 | N | 0.68182 | N | 0.45728 | 0.27553
P 63 | BRAZ | H | NOC | Own | 1 | 7213 | EPC | 1383 | 1.3 | CONV | 145833.3333 | M | N | FPSO | 1170 | L | 0.96 | L | 0.086768 | 0.25385
Espirito Santo | BRAZ | H | IOC | Lease | 3 | 6153 | EPC | 787 | 1.5086 | CONV | 105000 | M | H | FPSO | 1780 | N | 0.95238 | L | 0.24778 | 1.32
P 54 | BRAZ | H | NOC | Own | 1 | 5272 | EPC | 1034 | 0.629 | CONV | 215000 | VL | A | FPSO | 1315 | A | 0.83721 | N | 0.24468 | 0.97138
Cidade de Campos dos Goytacazes MV29 | BRAZ | M | NOC | Lease | 3 | 9101 | EPC | 1018 | 1.263 | CONV | 179500 | L | L | FPSO | 765 | M | 0.83565 | N | 0.27898 | 0.0055424
Terra Nova | CAN | L | OC | Own | 1 | 2800 | EPC | 1157 | 1.3 | NEW | 175000 | L | H | FPSO | 90 | N | 0.85714 | L | 0.39412 | 0.30769
Sea Rose | CAN | A | OC | Own | 1 | 4476 | EPC | 1229 | 0.49 | NEW | 125000 | M | H | FPSO | 120 | N | 0.8 | M | 0.072417 | 0.2
Turritella | GOM | N | OC | Own | 1 | 8528 | EPC | 1149 | 1 | Conv | 62500 | S | M | FPSO | 2900 | L | 0.96 | H | 0.11227 | 0.311
Asgard A | NE | A | OC | Own | 1 | 2356 | TK | 870 | 5.2941 | NEW | 300000 | UL | M | FPSO | 300 | N | 0.66667 | A | 0.20805 | 0.36
Balder | NE | A | IOC | Own | 1 | 1826 | TK | 592 | 0.35 | NEW | 90500 | S | H | FPSO | 125 | N | 0.91713 | N | 1.9291 | 0.62
Goliat FPSO | NE | L | OC | Own | 1 | 7218 | EPC | 1364 | 3.9 | NEW | 122500 | M | H | FPSO | 400 | N | 0.81633 | A | 0.72361 | 0.94872
Petrojarl Knarr | NE | L | OC | Lease | 3 | 7850 | EPC | 732 | 1.6119 | NEW | 70833.3333 | S | L | FPSO | 410 | L | 0.88941 | M | 0.85656 | 0.36975
Norne | NE | A | OC | Own | 1 | 1551 | EPC | 1334 | 4.7 | NEW | 261666.6667 | UL | M | FPSO | 380 | A | 0.84076 | L | -0.12519 | 0.6
Skarv | NE | L | IOC | Own | 1 | 6240 | EPC | 1245 | 5 | NEW | 167500 | L | M | FPSO | 370 | N | 0.47761 | A | 0.73494 | 0.7
Armada Kraken | NE | N | OC | Lease | 0 | 8719 | EPC | 1136 | 2.5 | CONV | 83333.3333 | S | N | FPSO | 116 | N | 0.96 | M | 0.16285 | 0
Glen Lyon | NE | A | IOC | Own | 1 | 7729 | EPC | 1949 | 4.78 | NEW | 166666.6667 | L | L | FPSO | 424 | N | 0.78 | M | 0.16675 | 0.19247
Western Isles FPSO | NE | N | OC | Own | 1 | 8391 | EPC | 952 | 1.6 | NEW | 40000 | VS | A | FPSO | 165 | L | 1 | A | 0.8792 | 0.25
Belanak Natuna | SEA | M | IOC | Own | 1 | 4250 | TK | 1137 | 1.6 | NEW | 158333.3333 | L | M | FPSO | 100 | L | 0.63158 | M | 0.058927 | 0.078167
Kikeh FPSO | SEA | H | OC | Lease | 3 | 5513 | EPC | 939 | 0.8 | CONV | 143500 | M | L | FPSO | 1350 | N | 0.83624 | M | -0.015974 | 0.2
Song Doc Pride MV 19 | SEA | N | NOC | Lease | 1 | 6339 | EPC | 417 | 0.25 | CONV | 30000 | VS | N | FPSO | 55 | L | 1 | N | 0.35012 | 0.04087
Thai Binh Vn | SEA | N | NOC | Own | 1 | 4446 | EPC | 611 | 0.714 | NEW | 68333.3333 | S | N | FPSO | 48 | L | 0.95122 | A | 0.037643 | 0.044
Hai Yang Shi You 117 | SEA CH | M | NOC | Own | 1 | 5524 | EPC | 897 | 1.8 | NEW | 190000 | L | N | FPSO | 27 | N | 1 | A | 0.72798 | 0.38889
Hai Yang Shi You 116 | SEA CH | M | NOC | Own | 1 | 5804 | EPC | 723 | 1.2 | NEW | 106000 | M | L | FPSO | 125 | N | 1 | N | 0.3195 | 0.98
Unity | AFRICA | M | IOC | Own | 1 | 4018 | EPC | 545 | 1 | NEW | 125000 | M | L | FSO | 65 | A | 1 | L | 0.70092 | 0.4
Yoho | AFRICA | A | IOC | Own | 1 | 4196 | EPC | 505 | 1.2 | CONV | 90000 | S | L | FSO | 56 | N | 1 | N | 0.20792 | 0.083333
Yoho | AFRICA | A | IOC | Own | 1 | 4623 | EPC | 761 | 1.2 | CONV | 116666.6667 | M | L | FSO | 56 | A | 0.85714 | L | 0.6636 | 0.083333
Randgrid | NE | L | OC | Lease | 0 | 8521 | EPC | 1386 | 3.7 | CONV | 0 | VS | N | FSO | 116 | L | 1 | A | 0.097403 | 0
Hanne Knutsen | NE | L | IOC | Lease | 3 | 8124 | EPC | 1691 | 2.8649 | CONV | 100000 | M | A | FSO | 115 | N | 1 | L | 0.80958 | 0.85
Ailsa FSO | NE | L | IOC | Own | 1 | 9389 | EPC | 1364 | 4.7 | NEW | 108333.3333 | M | L | FSO | 90 | H | 0.23077 | H | 0 | 0
Gagak Rimang | SEA | H | IOC | Own | 1 | 7891 | EPC | 1110 | 1.2 | CONV | 165000 | L | L | FSO | 33 | N | 1 | L | 0.42973 | 1.1667
Rang Dong MV17 | SEA | N | NOC | Lease | 3 | 6038 | EPC | 763 | 0.5 | NEW | 60000 | S | N | FSO | 60 | L | 1 | N | 0.10747 | 0.04087
Ichthys Explorer | AUST/NZ | M | OC | Own | 1 | 8046 | EPC | 1810 | 3 | NEW | 361166.6667 | UL | M | SEMI | 250 | L | 0.23535 | H | 0.35635 | 0.32353
P 51 | BRAZ | H | NOC | Own | 1 | 5201 | EPC | 1418 | 0.83 | NEW | 215000 | VL | L | SEMI | 1250 | H | 0.83721 | N | 0.24401 | 0.25
P 56 | BRAZ | H | NOC | Own | 1 | 6478 | EPC | 1114 | 1.4 | NEW | 135000 | M | N | SEMI | 1670 | H | 0.74074 | N | 0.27379 | 0.071429
P 52 | BRAZ | H | NOC | Lease | 3 | 5060 | EPC | 1237 | 0.906 | NEW | 235000 | VL | L | SEMI | 1850 | A | 0.76596 | N | 0.19644 | 0.43488
Atlantis | GOM | A | IOC | Own | 1 | 4533 | EPC | 1492 | 2.5 | NEW | 230000 | VL | A | SEMI | 2145 | A | 0.86957 | N | 0.60389 | 1.35
Delta House (Opti-Ex II) | GOM | N | OC | Own | 1 | 8158 | EPC | 1093 | 2 | NEW | 140000 | M | L | SEMI | 1372 | H | 0.71429 | L | -0.012809 | 0
Blind Faith | GOM | L | IOC | Own | 1 | 5802 | EPC | 846 | 1.151 | NEW | 52500 | S | M | SEMI | 2130 | N | 0.85714 | H | 0.28605 | 0.95
Thunder Hawk | GOM | N | OC | Lease | 3 | 6086 | EPC | 958 | 0.8 | NEW | 56666.6667 | S | N | SEMI | 1847 | M | 0.79412 | H | 0.087683 | 0
Thunder Horse | GOM | A | IOC | Own | 1 | 4624 | EPC | 1098 | 5 | NEW | 283333.3333 | UL | H | SEMI | 1830 | N | 0.88235 | M | 0.92623 | 2.68
Jack / St. Malo Semi | GOM | N | IOC | Own | 1 | 7270 | EPC | 1844 | 7.5 | NEW | 177166.6667 | L | N | SEMI | 2134 | M | 0.95955 | H | -0.005423 | 0
Asgard B | NE | M | OC | Own | 1 | 2356 | TK | 1570 | 1.3 | New | 351666.6667 | UL | N | SEMI | 300 | H | 0.38389 | M | 0 | 0
Gjoa | NE | L | OC | Own | 1 | 6025 | CL | 1461 | 4.4361 | NEW | 108333.3333 | M | M | SEMI | 380 | N | 0.46154 | A | 0.08898 | 0.33
Kristin | NE | M | OC | Own | 1 | 4368 | EPC | 1384 | 1.9 | New | 128000 | M | H | SEMI | 370 | N | 0.97656 | L | 0.023844 | 0.73684
Snorre B | NE | M | OC | Own | 1 | 3256 | EPC | 943 | 1.2821 | NEW | 115000 | M | N | SEMI | 310 | M | 1 | L | -0.064687 | 0.17
Troll B | NE | A | OC | Own | 1 | 379 | EPC | 1263 | 2.9 | NEW | 317000 | UL | H | SEMI | 320 | L | 0.85174 | A | 0.35234 | 0.14
Visund | NE | H | OC | Own | 1 | 2251 | TK | 851 | 0.7 | NEW | 171333.3333 | L | H | SEMI | 335 | N | 0.65953 | L | 0.3396 | 0.45
Gumusut Semi | SEA | H | IOC | Lease | 3 | 6588 | EPC | 1233 | 1.6 | NEW | 200000 | VL | L | SEMI | 1220 | L | 0.75 | A | 0.99919 | 0.25
Front Runner Spar | GOM | L | OC | Own | 1 | 4459 | TK | 728 | 0.2 | NEW | 78333.3333 | S | A | SPAR | 1015 | N | 0.76596 | N | 0.36676 | 0.075
Tahiti Spar | GOM | L | IOC | Own | 1 | 5597 | EPC | 1159 | 3.5 | NEW | 136666.6667 | M | A | SPAR | 1280 | L | 0.91463 | L | 0.26747 | 1.8
Mad Dog | GOM | N | IOC | Own | 1 | 4070 | EPC | 1397 | 1.82 | NEW | 66666.6667 | S | L | SPAR | 1370 | N | 0.9 | M | 0.022906 | 0.1
Heidelberg Spar | GOM | N | OC | Own | 1 | 8018 | EPC | 1649 | 6.745 | NEW | 93333.3333 | S | M | SPAR | 1620 | H | 0.85714 | H | -0.095816 | 0.0081542
Lucius Spar | GOM | N | OC | Own | 1 | 8002 | EPC | 1007 | 7.736 | NEW | 155000 | L | M | SPAR | 2165 | M | 0.51613 | H | 0.14002 | 0.008273
Medusa Spar | GOM | L | OC | Own | 1 | 4077 | TK | 579 | 0.2 | NEW | 58333.3333 | S | A | SPAR | 675 | N | 0.68571 | N | 0.74266 | 0.365
Gulfstar 1 | GOM | N | IOC | Lease | 3 | 7813 | EPC | 1132 | 2.3 | NEW | 109166.6667 | M | L | SPAR | 1310 | L | 0.73282 | A | 0.12191 | 0.47826
Devil's Tower Spar | GOM | A | OC | Lease | 3 | 4189 | TK | 739 | 0.2 | NEW | 66666.6667 | S | L | SPAR | 1710 | L | 0.9 | N | 0.41949 | 0.06
Kikeh Spar | SEA | H | OC | Own | 1 | 5513 | EPC | 939 | 0.5 | NEW | 142500 | M | M | SPAR | 1330 | N | 0.84211 | M | -0.015974 | 0.28571
Kizomba A Wellhead TLP | AFRICA | M | IOC | Own | 1 | 4253 | EPC | 1073 | 0.65 | NEW | 250000 | UL | N | TLP | 1175 | A | 1 | L | 0.0055918 | 0.13333
Kizomba B Wellhead TLP | AFRICA | A | IOC | Own | 1 | 4756 | EPC | 1071 | 0.6 | NEW | 250000 | UL | N | TLP | 1250 | H | 1 | L | -0.14006 | 0.13333
Okume TLP | AFRICA | L | OC | Own | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | VS | N | TLP | 500 | M | 0.83333 | M | 0.04 | 0
Oveng TLP | AFRICA | L | OC | Own | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | VS | N | TLP | 280 | M | 0.83333 | M | 0.04 | 0
P 61 Wellhead TLP | BRAZ | H | NOC | Own | 1 | 7213 | EPC | 1475 | 1.07 | NEW | 145833.3333 | M | A | TLP | 1180 | N | 0.96 | L | 0.35051 | 0
Auger TLP | GOM | L | IOC | Own | 1 | 287 | EPC | 1233 | 0.86364 | NEW | 65000 | S | M | TLP | 870 | L | 0.61538 | M | 0.044607 | 0.38947
Magnolia TLP | GOM | N | IOC | Own | 1 | 4392 | EPC | 1040 | 0.6 | NEW | 75000 | S | M | TLP | 1432 | L | 0.66667 | H | 0.038462 | 0
Brutus TLP | GOM | N | IOC | Own | 1 | 3570 | EPC | 674 | 0.76 | NEW | 155000 | L | L | TLP | 910 | M | 0.83871 | M | 0.038576 | 0.078947
Stampede TLP | GOM | N | OC | Own | 1 | 8523 | EPC | 1982 | 6.2 | NEW | 86666.6667 | S | N | TLP | 1160 | M | 0.92308 | H | -0.1221 | -0.12903
Neptune TLP | GOM | L | OC | Own | 1 | 5670 | EPC | 887 | 0.85 | NEW | 58333.3333 | S | L | TLP | 1300 | L | 0.85714 | A | 0.2345 | 0.47882
Shenzi TLP | GOM | L | OC | Own | 1 | 6001 | EPC | 1119 | 4.41 | NEW | 116666.6667 | M | L | TLP | 1333 | L | 0.85714 | H | -0.088472 | 0
Mars TLP | GOM | N | IOC | Own | 1 | 1381 | EPC | 1098 | 1.2 | NEW | 230833.3333 | VL | L | TLP | 896 | M | 0.86643 | M | -0.090164 | -0.054167
Olympus TLP | GOM | N | IOC | Own | 1 | 7729 | EPC | 1202 | 3 | NEW | 116666.6667 | M | L | TLP | 945 | H | 0.85714 | H | -0.12562 | 0
Ursa TLP | GOM | N | IOC | Own | 1 | 2398 | EPC | 1040 | 1.45 | NEW | 216666.6667 | VL | A | TLP | 1160 | H | 0.69231 | M | -0.081731 | 0.043448
Ram Powell TLP | GOM | N | IOC | Own | 1 | 1885 | EPC | 915 | 1 | NEW | 93333.3333 | S | A | TLP | 990 | H | 0.64286 | M | 0.015301 | 0
Big Foot | GOM | A | IOC | Own | 1 | 7571 | EPC | 1529 | 4 | NEW | 79166.6667 | S | H | TLP | 1580 | N | 0.94737 | M | 0.94899 | 0.375
Heidrun TLP | NE | N | OC | Own | 1 | 504 | EPC | 1548 | 3.9 | NEW | 283333.3333 | UL | L | TLP | 350 | L | 0.88235 | H | 0.039406 | 0.076923
Malikai TLP | SEA | H | IOC | Own | 1 | 8439 | EPC | 1030 | 1.2825 | NEW | 68333.3333 | S | L | TLP | 470 | A | 0.87805 | H | 0.36796 | 0.077973

## Cost2
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun
Bohai Ming Zhu | SEA CH | 5 | NOC | 2 | 1 | 4350 | EPC | 259 | 0.4 | NEW | 40000 | 1 | 2 | FPSO | 30 | 1 | 1 | 1 | 0.47104 | 0.25
Petrojarl Varg | NE | 1 | OC | 1 | 1 | 2240 | EPC | 816 | 0.46 | NEW | 65833.3333 | 2 | 2 | FPSO | 84 | 1 | 0.86582 | 2 | 0.28676 | 0.24
Stybarrow Venture MV16 | AUST/NZ | 3 | IOC | 1 | 3 | 5922 | EPC | 702 | 0.59843 | NEW | 87500 | 2 | 3 | FPSO | 825 | 2 | 0.91429 | 4 | -0.14387 | 0.27
Alima FPU | AFRICA | 2 | IOC | 2 | 1 | 5720 | EPC | 994 | 1.133 | NEW | 100000 | 3 | 1 | BARGE | 600 | 3 | 0.9 | 4 | -0.022133 | 0.35
Jangkrik | SEA | 4 | OC | 2 | 1 | 8824 | EPC | 1052 | 2.6765 | NEW | 79400 | 2 | 2 | BARGE | 120 | 2 | 0.055416 | 3 | 0.11407 | 0.17
Prelude | AUST/NZ | 3 | IOC | 2 | 1 | 7814 | EPC | 2229 | 11.16 | NEW | 148333.3333 | 6 | 5 | FLNG | 250 | 1 | 0.23596 | 5 | 0.24316 | 0.34409
CLOV FPSO | AFRICA | 3 | IOC | 2 | 1 | 7534 | EPC | 1383 | 7 | NEW | 198333.3333 | 4 | 2 | FPSO | 1290 | 4 | 0.80672 | 5 | 0.0079537 | 0.14286
Dalia | AFRICA | 4 | IOC | 2 | 1 | 4872 | EPC | 1306 | 3.4 | NEW | 287000 | 6 | 3 | FPSO | 1360 | 5 | 0.83624 | 2 | 0.01072 | 0.17647
Girassol | AFRICA | 4 | IOC | 2 | 1 | 3103 | EPC | 823 | 2.5 | NEW | 246666.6667 | 5 | 3 | FPSO | 1350 | 1 | 0.81081 | 1 | 0.52126 | 0.12
Kizomba B | AFRICA | 3 | IOC | 2 | 1 | 4756 | EPC | 1071 | 0.76 | NEW | 316666.6667 | 6 | 1 | FPSO | 1250 | 5 | 0.78947 | 2 | -0.14006 | 0.13333
Mondo | AFRICA | 4 | IOC | 1 | 1 | 5866 | EPC | 797 | 0.75 | CONV | 115833.3333 | 3 | 1 | FPSO | 728 | 3 | 0.86331 | 3 | -0.10163 | 0
Saxi-Batuque | AFRICA | 4 | IOC | 1 | 3 | 5866 | EPC | 797 | 0.75 | CONV | 130000 | 3 | 1 | FPSO | 720 | 3 | 0.80769 | 3 | -0.084065 | 0
Greater Plutonio | AFRICA | 3 | IOC | 2 | 1 | 5144 | EPC | 1124 | 1.73 | NEW | 305000 | 6 | 3 | FPSO | 1350 | 2 | 0.81967 | 4 | 0.19039 | 0.85
PSVM FPSO | AFRICA | 5 | IOC | 2 | 1 | 6755 | EPC | 1249 | 10 | CONV | 197833.3333 | 4 | 5 | FPSO | 2000 | 2 | 0.7936 | 1 | 0.29704 | 0.4
Baobab Ivoirien MV10 | AFRICA | 1 | OC | 1 | 3 | 4949 | EPC | 711 | 1.5 | CONV | 82500 | 2 | 1 | FPSO | 970 | 3 | 0.84848 | 2 | 0.067511 | 0
Prof. John Evans Atta Mills | AFRICA | 4 | IOC | 1 | 3 | 8617 | EPC | 1092 | 4.5 | CONV | 108333.3333 | 3 | 1 | FPSO | 1425 | 2 | 0.73846 | 5 | 0.015568 | 0.088889
Agbami | AFRICA | 2 | IOC | 2 | 2 | 5539 | EPC | 1126 | 4.1538 | NEW | 325000 | 6 | 2 | FPSO | 1433 | 2 | 0.76923 | 2 | 0.11368 | 0.3
Akpo | AFRICA | 4 | IOC | 2 | 1 | 5606 | TK | 1303 | 2.345 | NEW | 273333.3333 | 6 | 4 | FPSO | 1325 | 1 | 0.67683 | 2 | 0.072141 | 1.55
Bonga | AFRICA | 4 | IOC | 2 | 1 | 4049 | EPC | 1033 | 2.4 | NEW | 253333.3333 | 6 | 3 | FPSO | 1250 | 1 | 0.88816 | 3 | 0.70765 | 0.5
Egina FPSO | AFRICA | 5 | IOC | 2 | 1 | 8540 | EPC | 1595 | 15 | NEW | 260000 | 6 | 2 | FPSO | 1600 | 3 | 0.76923 | 2 | 0.28715 | -0.033333
Erha | AFRICA | 4 | IOC | 2 | 1 | 4671 | EPC | 1081 | 2.6 | NEW | 266666.6667 | 6 | 2 | FPSO | 1180 | 2 | 0.7875 | 2 | 0.19334 | 0.57
Kizomba A | AFRICA | 3 | IOC | 2 | 1 | 4253 | EPC | 1073 | 0.77 | NEW | 316666.6667 | 6 | 2 | FPSO | 1250 | 3 | 0.78947 | 2 | 0.0055918 | 0.13333
Ichthys Venturer | AUST/NZ | 4 | IOC | 2 | 1 | 8102 | EPC | 1743 | 2 | NEW | 85000 | 2 | 5 | FPSO | 250 | 2 | 1 | 5 | 0.37636 | 0.32353
Pyrenees Venture | AUST/NZ | 3 | IOC | 2 | 2 | 6379 | EPC | 1014 | 1.66 | CONV | 106000 | 3 | 4 | FPSO | 200 | 4 | 0.90566 | 5 | 0.0019724 | 0.012028
Ngujima Yin | AUST/NZ | 3 | IOC | 2 | 1 | 5993 | EPC | 716 | 0.72 | CONV | 136666.6667 | 3 | 2 | FPSO | 340 | 2 | 0.87805 | 3 | 0.14665 | 0.33333
P 50 | BRAZ | 4 | NOC | 2 | 1 | 4557 | CL | 844 | 0.496 | CONV | 215000 | 5 | 4 | FPSO | 1240 | 1 | 0.83721 | 1 | 0.66351 | 0.41129
P 43 | BRAZ | 5 | NOC | 2 | 1 | 4199 | TK | 883 | 1.3 | CONV | 185000 | 4 | 3 | FPSO | 800 | 1 | 0.81081 | 1 | 0.43828 | 0.38462
P 48 | BRAZ | 5 | NOC | 2 | 1 | 4199 | TK | 1066 | 1.3 | CONV | 185000 | 4 | 1 | FPSO | 1040 | 2 | 0.81081 | 1 | 0.25516 | 0.38462
Frade | BRAZ | 3 | IOC | 2 | 1 | 6014 | EPC | 909 | 2 | CONV | 117666.6667 | 3 | 2 | FPSO | 1080 | 1 | 0.84986 | 4 | 0.20902 | 1.35
Cidade de Itaguai MV26 | BRAZ | 4 | NOC | 1 | 3 | 8352 | EPC | 838 | 1.17 | CONV | 196666.6667 | 4 | 1 | FPSO | 2240 | 3 | 0.76271 | 1 | 0.18138 | 0
P 57 | BRAZ | 5 | NOC | 1 | 2 | 6622 | EPC | 1041 | 1.195 | CONV | 191833.3333 | 4 | 1 | FPSO | 1300 | 4 | 0.93831 | 1 | -0.045149 | 0.0041841
Pioneiro de Libra | BRAZ | 5 | NOC | 1 | 3 | 8984 | PS | 831 | 1 | CONV | 73333.3333 | 2 | 1 | FPSO | 2200 | 1 | 0.68182 | 1 | 0.45728 | 0.27553
P 63 | BRAZ | 5 | NOC | 2 | 1 | 7213 | EPC | 1383 | 1.3 | CONV | 145833.3333 | 3 | 1 | FPSO | 1170 | 2 | 0.96 | 2 | 0.086768 | 0.25385
Espirito Santo | BRAZ | 5 | IOC | 1 | 3 | 6153 | EPC | 787 | 1.5086 | CONV | 105000 | 3 | 5 | FPSO | 1780 | 1 | 0.95238 | 2 | 0.24778 | 1.32
P 54 | BRAZ | 5 | NOC | 2 | 1 | 5272 | EPC | 1034 | 0.629 | CONV | 215000 | 5 | 3 | FPSO | 1315 | 3 | 0.83721 | 1 | 0.24468 | 0.97138
Cidade de Campos dos Goytacazes MV29 | BRAZ | 4 | NOC | 1 | 3 | 9101 | EPC | 1018 | 1.263 | CONV | 179500 | 4 | 2 | FPSO | 765 | 4 | 0.83565 | 1 | 0.27898 | 0.0055424
Terra Nova | CAN | 2 | OC | 2 | 1 | 2800 | EPC | 1157 | 1.3 | NEW | 175000 | 4 | 5 | FPSO | 90 | 1 | 0.85714 | 2 | 0.39412 | 0.30769
Sea Rose | CAN | 3 | OC | 2 | 1 | 4476 | EPC | 1229 | 0.49 | NEW | 125000 | 3 | 5 | FPSO | 120 | 1 | 0.8 | 4 | 0.072417 | 0.2
Turritella | GOM | 1 | OC | 2 | 1 | 8528 | EPC | 1149 | 1 | Conv | 62500 | 2 | 4 | FPSO | 2900 | 2 | 0.96 | 5 | 0.11227 | 0.311
Asgard A | NE | 3 | OC | 2 | 1 | 2356 | TK | 870 | 5.2941 | NEW | 300000 | 6 | 4 | FPSO | 300 | 1 | 0.66667 | 3 | 0.20805 | 0.36
Balder | NE | 3 | IOC | 2 | 1 | 1826 | TK | 592 | 0.35 | NEW | 90500 | 2 | 5 | FPSO | 125 | 1 | 0.91713 | 1 | 1.9291 | 0.62
Goliat FPSO | NE | 2 | OC | 2 | 1 | 7218 | EPC | 1364 | 3.9 | NEW | 122500 | 3 | 5 | FPSO | 400 | 1 | 0.81633 | 3 | 0.72361 | 0.94872
Petrojarl Knarr | NE | 2 | OC | 1 | 3 | 7850 | EPC | 732 | 1.6119 | NEW | 70833.3333 | 2 | 2 | FPSO | 410 | 2 | 0.88941 | 4 | 0.85656 | 0.36975
Norne | NE | 3 | OC | 2 | 1 | 1551 | EPC | 1334 | 4.7 | NEW | 261666.6667 | 6 | 4 | FPSO | 380 | 3 | 0.84076 | 2 | -0.12519 | 0.6
Skarv | NE | 2 | IOC | 2 | 1 | 6240 | EPC | 1245 | 5 | NEW | 167500 | 4 | 4 | FPSO | 370 | 1 | 0.47761 | 3 | 0.73494 | 0.7
Armada Kraken | NE | 1 | OC | 1 | 0 | 8719 | EPC | 1136 | 2.5 | CONV | 83333.3333 | 2 | 1 | FPSO | 116 | 1 | 0.96 | 4 | 0.16285 | 0
Glen Lyon | NE | 3 | IOC | 2 | 1 | 7729 | EPC | 1949 | 4.78 | NEW | 166666.6667 | 4 | 2 | FPSO | 424 | 1 | 0.78 | 4 | 0.16675 | 0.19247
Western Isles FPSO | NE | 1 | OC | 2 | 1 | 8391 | EPC | 952 | 1.6 | NEW | 40000 | 1 | 3 | FPSO | 165 | 2 | 1 | 3 | 0.8792 | 0.25
Belanak Natuna | SEA | 4 | IOC | 2 | 1 | 4250 | TK | 1137 | 1.6 | NEW | 158333.3333 | 4 | 4 | FPSO | 100 | 2 | 0.63158 | 4 | 0.058927 | 0.078167
Kikeh FPSO | SEA | 5 | OC | 1 | 3 | 5513 | EPC | 939 | 0.8 | CONV | 143500 | 3 | 2 | FPSO | 1350 | 1 | 0.83624 | 4 | -0.015974 | 0.2
Song Doc Pride MV 19 | SEA | 1 | NOC | 1 | 1 | 6339 | EPC | 417 | 0.25 | CONV | 30000 | 1 | 1 | FPSO | 55 | 2 | 1 | 1 | 0.35012 | 0.04087
Thai Binh Vn | SEA | 1 | NOC | 2 | 1 | 4446 | EPC | 611 | 0.714 | NEW | 68333.3333 | 2 | 1 | FPSO | 48 | 2 | 0.95122 | 3 | 0.037643 | 0.044
Hai Yang Shi You 117 | SEA CH | 4 | NOC | 2 | 1 | 5524 | EPC | 897 | 1.8 | NEW | 190000 | 4 | 1 | FPSO | 27 | 1 | 1 | 3 | 0.72798 | 0.38889
Hai Yang Shi You 116 | SEA CH | 4 | NOC | 2 | 1 | 5804 | EPC | 723 | 1.2 | NEW | 106000 | 3 | 2 | FPSO | 125 | 1 | 1 | 1 | 0.3195 | 0.98
Unity | AFRICA | 4 | IOC | 2 | 1 | 4018 | EPC | 545 | 1 | NEW | 125000 | 3 | 2 | FSO | 65 | 3 | 1 | 2 | 0.70092 | 0.4
Yoho | AFRICA | 3 | IOC | 2 | 1 | 4196 | EPC | 505 | 1.2 | CONV | 90000 | 2 | 2 | FSO | 56 | 1 | 1 | 1 | 0.20792 | 0.083333
Yoho | AFRICA | 3 | IOC | 2 | 1 | 4623 | EPC | 761 | 1.2 | CONV | 116666.6667 | 3 | 2 | FSO | 56 | 3 | 0.85714 | 2 | 0.6636 | 0.083333
Randgrid | NE | 2 | OC | 1 | 0 | 8521 | EPC | 1386 | 3.7 | CONV | 0 | 1 | 1 | FSO | 116 | 2 | 1 | 3 | 0.097403 | 0
Hanne Knutsen | NE | 2 | IOC | 1 | 3 | 8124 | EPC | 1691 | 2.8649 | CONV | 100000 | 3 | 3 | FSO | 115 | 1 | 1 | 2 | 0.80958 | 0.85
Ailsa FSO | NE | 2 | IOC | 2 | 1 | 9389 | EPC | 1364 | 4.7 | NEW | 108333.3333 | 3 | 2 | FSO | 90 | 5 | 0.23077 | 5 | 0 | 0
Gagak Rimang | SEA | 5 | IOC | 2 | 1 | 7891 | EPC | 1110 | 1.2 | CONV | 165000 | 4 | 2 | FSO | 33 | 1 | 1 | 2 | 0.42973 | 1.1667
Rang Dong MV17 | SEA | 1 | NOC | 1 | 3 | 6038 | EPC | 763 | 0.5 | NEW | 60000 | 2 | 1 | FSO | 60 | 2 | 1 | 1 | 0.10747 | 0.04087
Ichthys Explorer | AUST/NZ | 4 | OC | 2 | 1 | 8046 | EPC | 1810 | 3 | NEW | 361166.6667 | 6 | 4 | SEMI | 250 | 2 | 0.23535 | 5 | 0.35635 | 0.32353
P 51 | BRAZ | 5 | NOC | 2 | 1 | 5201 | EPC | 1418 | 0.83 | NEW | 215000 | 5 | 2 | SEMI | 1250 | 5 | 0.83721 | 1 | 0.24401 | 0.25
P 56 | BRAZ | 5 | NOC | 2 | 1 | 6478 | EPC | 1114 | 1.4 | NEW | 135000 | 3 | 1 | SEMI | 1670 | 5 | 0.74074 | 1 | 0.27379 | 0.071429
P 52 | BRAZ | 5 | NOC | 1 | 3 | 5060 | EPC | 1237 | 0.906 | NEW | 235000 | 5 | 2 | SEMI | 1850 | 3 | 0.76596 | 1 | 0.19644 | 0.43488
Atlantis | GOM | 3 | IOC | 2 | 1 | 4533 | EPC | 1492 | 2.5 | NEW | 230000 | 5 | 3 | SEMI | 2145 | 3 | 0.86957 | 1 | 0.60389 | 1.35
Delta House (Opti-Ex II) | GOM | 1 | OC | 2 | 1 | 8158 | EPC | 1093 | 2 | NEW | 140000 | 3 | 2 | SEMI | 1372 | 5 | 0.71429 | 2 | -0.012809 | 0
Blind Faith | GOM | 2 | IOC | 2 | 1 | 5802 | EPC | 846 | 1.151 | NEW | 52500 | 2 | 4 | SEMI | 2130 | 1 | 0.85714 | 5 | 0.28605 | 0.95
Thunder Hawk | GOM | 1 | OC | 1 | 3 | 6086 | EPC | 958 | 0.8 | NEW | 56666.6667 | 2 | 1 | SEMI | 1847 | 4 | 0.79412 | 5 | 0.087683 | 0
Thunder Horse | GOM | 3 | IOC | 2 | 1 | 4624 | EPC | 1098 | 5 | NEW | 283333.3333 | 6 | 5 | SEMI | 1830 | 1 | 0.88235 | 4 | 0.92623 | 2.68
Jack / St. Malo Semi | GOM | 1 | IOC | 2 | 1 | 7270 | EPC | 1844 | 7.5 | NEW | 177166.6667 | 4 | 1 | SEMI | 2134 | 4 | 0.95955 | 5 | -0.005423 | 0
Asgard B | NE | 4 | OC | 2 | 1 | 2356 | TK | 1570 | 1.3 | New | 351666.6667 | 6 | 1 | SEMI | 300 | 5 | 0.38389 | 4 | 0 | 0
Gjoa | NE | 2 | OC | 2 | 1 | 6025 | CL | 1461 | 4.4361 | NEW | 108333.3333 | 3 | 4 | SEMI | 380 | 1 | 0.46154 | 3 | 0.08898 | 0.33
Kristin | NE | 4 | OC | 2 | 1 | 4368 | EPC | 1384 | 1.9 | New | 128000 | 3 | 5 | SEMI | 370 | 1 | 0.97656 | 2 | 0.023844 | 0.73684
Snorre B | NE | 4 | OC | 2 | 1 | 3256 | EPC | 943 | 1.2821 | NEW | 115000 | 3 | 1 | SEMI | 310 | 4 | 1 | 2 | -0.064687 | 0.17
Troll B | NE | 3 | OC | 2 | 1 | 379 | EPC | 1263 | 2.9 | NEW | 317000 | 6 | 5 | SEMI | 320 | 2 | 0.85174 | 3 | 0.35234 | 0.14
Visund | NE | 5 | OC | 2 | 1 | 2251 | TK | 851 | 0.7 | NEW | 171333.3333 | 4 | 5 | SEMI | 335 | 1 | 0.65953 | 2 | 0.3396 | 0.45
Gumusut Semi | SEA | 5 | IOC | 1 | 3 | 6588 | EPC | 1233 | 1.6 | NEW | 200000 | 5 | 2 | SEMI | 1220 | 2 | 0.75 | 3 | 0.99919 | 0.25
Front Runner Spar | GOM | 2 | OC | 2 | 1 | 4459 | TK | 728 | 0.2 | NEW | 78333.3333 | 2 | 3 | SPAR | 1015 | 1 | 0.76596 | 1 | 0.36676 | 0.075
Tahiti Spar | GOM | 2 | IOC | 2 | 1 | 5597 | EPC | 1159 | 3.5 | NEW | 136666.6667 | 3 | 3 | SPAR | 1280 | 2 | 0.91463 | 2 | 0.26747 | 1.8
Mad Dog | GOM | 1 | IOC | 2 | 1 | 4070 | EPC | 1397 | 1.82 | NEW | 66666.6667 | 2 | 2 | SPAR | 1370 | 1 | 0.9 | 4 | 0.022906 | 0.1
Heidelberg Spar | GOM | 1 | OC | 2 | 1 | 8018 | EPC | 1649 | 6.745 | NEW | 93333.3333 | 2 | 4 | SPAR | 1620 | 5 | 0.85714 | 5 | -0.095816 | 0.0081542
Lucius Spar | GOM | 1 | OC | 2 | 1 | 8002 | EPC | 1007 | 7.736 | NEW | 155000 | 4 | 4 | SPAR | 2165 | 4 | 0.51613 | 5 | 0.14002 | 0.008273
Medusa Spar | GOM | 2 | OC | 2 | 1 | 4077 | TK | 579 | 0.2 | NEW | 58333.3333 | 2 | 3 | SPAR | 675 | 1 | 0.68571 | 1 | 0.74266 | 0.365
Gulfstar 1 | GOM | 1 | IOC | 1 | 3 | 7813 | EPC | 1132 | 2.3 | NEW | 109166.6667 | 3 | 2 | SPAR | 1310 | 2 | 0.73282 | 3 | 0.12191 | 0.47826
Devil's Tower Spar | GOM | 3 | OC | 1 | 3 | 4189 | TK | 739 | 0.2 | NEW | 66666.6667 | 2 | 2 | SPAR | 1710 | 2 | 0.9 | 1 | 0.41949 | 0.06
Kikeh Spar | SEA | 5 | OC | 2 | 1 | 5513 | EPC | 939 | 0.5 | NEW | 142500 | 3 | 4 | SPAR | 1330 | 1 | 0.84211 | 4 | -0.015974 | 0.28571
Kizomba A Wellhead TLP | AFRICA | 4 | IOC | 2 | 1 | 4253 | EPC | 1073 | 0.65 | NEW | 250000 | 6 | 1 | TLP | 1175 | 3 | 1 | 2 | 0.0055918 | 0.13333
Kizomba B Wellhead TLP | AFRICA | 3 | IOC | 2 | 1 | 4756 | EPC | 1071 | 0.6 | NEW | 250000 | 6 | 1 | TLP | 1250 | 5 | 1 | 2 | -0.14006 | 0.13333
Okume TLP | AFRICA | 2 | OC | 2 | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | 1 | 1 | TLP | 500 | 4 | 0.83333 | 4 | 0.04 | 0
Oveng TLP | AFRICA | 2 | OC | 2 | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | 1 | 1 | TLP | 280 | 4 | 0.83333 | 4 | 0.04 | 0
P 61 Wellhead TLP | BRAZ | 5 | NOC | 2 | 1 | 7213 | EPC | 1475 | 1.07 | NEW | 145833.3333 | 3 | 3 | TLP | 1180 | 1 | 0.96 | 2 | 0.35051 | 0
Auger TLP | GOM | 2 | IOC | 2 | 1 | 287 | EPC | 1233 | 0.86364 | NEW | 65000 | 2 | 4 | TLP | 870 | 2 | 0.61538 | 4 | 0.044607 | 0.38947
Magnolia TLP | GOM | 1 | IOC | 2 | 1 | 4392 | EPC | 1040 | 0.6 | NEW | 75000 | 2 | 4 | TLP | 1432 | 2 | 0.66667 | 5 | 0.038462 | 0
Brutus TLP | GOM | 1 | IOC | 2 | 1 | 3570 | EPC | 674 | 0.76 | NEW | 155000 | 4 | 2 | TLP | 910 | 4 | 0.83871 | 4 | 0.038576 | 0.078947
Stampede TLP | GOM | 1 | OC | 2 | 1 | 8523 | EPC | 1982 | 6.2 | NEW | 86666.6667 | 2 | 1 | TLP | 1160 | 4 | 0.92308 | 5 | -0.1221 | -0.12903
Neptune TLP | GOM | 2 | OC | 2 | 1 | 5670 | EPC | 887 | 0.85 | NEW | 58333.3333 | 2 | 2 | TLP | 1300 | 2 | 0.85714 | 3 | 0.2345 | 0.47882
Shenzi TLP | GOM | 2 | OC | 2 | 1 | 6001 | EPC | 1119 | 4.41 | NEW | 116666.6667 | 3 | 2 | TLP | 1333 | 2 | 0.85714 | 5 | -0.088472 | 0
Mars TLP | GOM | 1 | IOC | 2 | 1 | 1381 | EPC | 1098 | 1.2 | NEW | 230833.3333 | 5 | 2 | TLP | 896 | 4 | 0.86643 | 4 | -0.090164 | -0.054167
Olympus TLP | GOM | 1 | IOC | 2 | 1 | 7729 | EPC | 1202 | 3 | NEW | 116666.6667 | 3 | 2 | TLP | 945 | 5 | 0.85714 | 5 | -0.12562 | 0
Ursa TLP | GOM | 1 | IOC | 2 | 1 | 2398 | EPC | 1040 | 1.45 | NEW | 216666.6667 | 5 | 3 | TLP | 1160 | 5 | 0.69231 | 4 | -0.081731 | 0.043448
Ram Powell TLP | GOM | 1 | IOC | 2 | 1 | 1885 | EPC | 915 | 1 | NEW | 93333.3333 | 2 | 3 | TLP | 990 | 5 | 0.64286 | 4 | 0.015301 | 0
Big Foot | GOM | 3 | IOC | 2 | 1 | 7571 | EPC | 1529 | 4 | NEW | 79166.6667 | 2 | 5 | TLP | 1580 | 1 | 0.94737 | 4 | 0.94899 | 0.375
Heidrun TLP | NE | 1 | OC | 2 | 1 | 504 | EPC | 1548 | 3.9 | NEW | 283333.3333 | 6 | 2 | TLP | 350 | 2 | 0.88235 | 5 | 0.039406 | 0.076923
Malikai TLP | SEA | 5 | IOC | 2 | 1 | 8439 | EPC | 1030 | 1.2825 | NEW | 68333.3333 | 2 | 2 | TLP | 470 | 3 | 0.87805 | 2 | 0.36796 | 0.077973

## Cost
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun
Bohai Ming Zhu | 8 | 5 | 2 | 2 | 1 | 4350 | 3 | 259 | 0.4 | 1 | 40000 | 1 | 2 | 4 | 30 | 1 | 1 | 1 | 0.47104 | 0.25
Petrojarl Varg | 5 | 1 | 1 | 1 | 1 | 2240 | 3 | 816 | 0.46 | 1 | 65833.3333 | 2 | 2 | 4 | 84 | 1 | 0.86582 | 2 | 0.28676 | 0.24
Stybarrow Venture MV16 | 4 | 3 | 3 | 1 | 3 | 5922 | 3 | 702 | 0.59843 | 1 | 87500 | 2 | 3 | 4 | 825 | 2 | 0.91429 | 4 | -0.14387 | 0.27
Alima FPU | 1 | 2 | 3 | 2 | 1 | 5720 | 3 | 994 | 1.133 | 1 | 100000 | 3 | 1 | 2 | 600 | 3 | 0.9 | 4 | -0.022133 | 0.35
Jangkrik | 2 | 4 | 1 | 2 | 1 | 8824 | 3 | 1052 | 2.6765 | 1 | 79400 | 2 | 2 | 2 | 120 | 2 | 0.055416 | 3 | 0.11407 | 0.17
Prelude | 4 | 3 | 3 | 2 | 1 | 7814 | 3 | 2229 | 11.16 | 1 | 148333.3333 | 6 | 5 | 5 | 250 | 1 | 0.23596 | 5 | 0.24316 | 0.34409
CLOV FPSO | 1 | 3 | 3 | 2 | 1 | 7534 | 3 | 1383 | 7 | 1 | 198333.3333 | 4 | 2 | 4 | 1290 | 4 | 0.80672 | 5 | 0.0079537 | 0.14286
Dalia | 1 | 4 | 3 | 2 | 1 | 4872 | 3 | 1306 | 3.4 | 1 | 287000 | 6 | 3 | 4 | 1360 | 5 | 0.83624 | 2 | 0.01072 | 0.17647
Girassol | 1 | 4 | 3 | 2 | 1 | 3103 | 3 | 823 | 2.5 | 1 | 246666.6667 | 5 | 3 | 4 | 1350 | 1 | 0.81081 | 1 | 0.52126 | 0.12
Kizomba B | 1 | 3 | 3 | 2 | 1 | 4756 | 3 | 1071 | 0.76 | 1 | 316666.6667 | 6 | 1 | 4 | 1250 | 5 | 0.78947 | 2 | -0.14006 | 0.13333
Mondo | 1 | 4 | 3 | 1 | 1 | 5866 | 3 | 797 | 0.75 | 2 | 115833.3333 | 3 | 1 | 4 | 728 | 3 | 0.86331 | 3 | -0.10163 | 0
Saxi-Batuque | 1 | 4 | 3 | 1 | 3 | 5866 | 3 | 797 | 0.75 | 2 | 130000 | 3 | 1 | 4 | 720 | 3 | 0.80769 | 3 | -0.084065 | 0
Greater Plutonio | 1 | 3 | 3 | 2 | 1 | 5144 | 3 | 1124 | 1.73 | 1 | 305000 | 6 | 3 | 4 | 1350 | 2 | 0.81967 | 4 | 0.19039 | 0.85
PSVM FPSO | 1 | 5 | 3 | 2 | 1 | 6755 | 3 | 1249 | 10 | 2 | 197833.3333 | 4 | 5 | 4 | 2000 | 2 | 0.7936 | 1 | 0.29704 | 0.4
Baobab Ivoirien MV10 | 1 | 1 | 1 | 1 | 3 | 4949 | 3 | 711 | 1.5 | 2 | 82500 | 2 | 1 | 4 | 970 | 3 | 0.84848 | 2 | 0.067511 | 0
Prof. John Evans Atta Mills | 1 | 4 | 3 | 1 | 3 | 8617 | 3 | 1092 | 4.5 | 2 | 108333.3333 | 3 | 1 | 4 | 1425 | 2 | 0.73846 | 5 | 0.015568 | 0.088889
Agbami | 1 | 2 | 3 | 2 | 2 | 5539 | 3 | 1126 | 4.1538 | 1 | 325000 | 6 | 2 | 4 | 1433 | 2 | 0.76923 | 2 | 0.11368 | 0.3
Akpo | 1 | 4 | 3 | 2 | 1 | 5606 | 4 | 1303 | 2.345 | 1 | 273333.3333 | 6 | 4 | 4 | 1325 | 1 | 0.67683 | 2 | 0.072141 | 1.55
Bonga | 1 | 4 | 3 | 2 | 1 | 4049 | 3 | 1033 | 2.4 | 1 | 253333.3333 | 6 | 3 | 4 | 1250 | 1 | 0.88816 | 3 | 0.70765 | 0.5
Egina FPSO | 1 | 5 | 3 | 2 | 1 | 8540 | 3 | 1595 | 15 | 1 | 260000 | 6 | 2 | 4 | 1600 | 3 | 0.76923 | 2 | 0.28715 | -0.033333
Erha | 1 | 4 | 3 | 2 | 1 | 4671 | 3 | 1081 | 2.6 | 1 | 266666.6667 | 6 | 2 | 4 | 1180 | 2 | 0.7875 | 2 | 0.19334 | 0.57
Kizomba A | 1 | 3 | 3 | 2 | 1 | 4253 | 3 | 1073 | 0.77 | 1 | 316666.6667 | 6 | 2 | 4 | 1250 | 3 | 0.78947 | 2 | 0.0055918 | 0.13333
Ichthys Venturer | 4 | 4 | 3 | 2 | 1 | 8102 | 3 | 1743 | 2 | 1 | 85000 | 2 | 5 | 4 | 250 | 2 | 1 | 5 | 0.37636 | 0.32353
Pyrenees Venture | 4 | 3 | 3 | 2 | 2 | 6379 | 3 | 1014 | 1.66 | 2 | 106000 | 3 | 4 | 4 | 200 | 4 | 0.90566 | 5 | 0.0019724 | 0.012028
Ngujima Yin | 4 | 3 | 3 | 2 | 1 | 5993 | 3 | 716 | 0.72 | 2 | 136666.6667 | 3 | 2 | 4 | 340 | 2 | 0.87805 | 3 | 0.14665 | 0.33333
P 50 | 7 | 4 | 2 | 2 | 1 | 4557 | 2 | 844 | 0.496 | 2 | 215000 | 5 | 4 | 4 | 1240 | 1 | 0.83721 | 1 | 0.66351 | 0.41129
P 43 | 7 | 5 | 2 | 2 | 1 | 4199 | 4 | 883 | 1.3 | 2 | 185000 | 4 | 3 | 4 | 800 | 1 | 0.81081 | 1 | 0.43828 | 0.38462
P 48 | 7 | 5 | 2 | 2 | 1 | 4199 | 4 | 1066 | 1.3 | 2 | 185000 | 4 | 1 | 4 | 1040 | 2 | 0.81081 | 1 | 0.25516 | 0.38462
Frade | 7 | 3 | 3 | 2 | 1 | 6014 | 3 | 909 | 2 | 2 | 117666.6667 | 3 | 2 | 4 | 1080 | 1 | 0.84986 | 4 | 0.20902 | 1.35
Cidade de Itaguai MV26 | 7 | 4 | 2 | 1 | 3 | 8352 | 3 | 838 | 1.17 | 2 | 196666.6667 | 4 | 1 | 4 | 2240 | 3 | 0.76271 | 1 | 0.18138 | 0
P 57 | 7 | 5 | 2 | 1 | 2 | 6622 | 3 | 1041 | 1.195 | 2 | 191833.3333 | 4 | 1 | 4 | 1300 | 4 | 0.93831 | 1 | -0.045149 | 0.0041841
Pioneiro de Libra | 7 | 5 | 2 | 1 | 3 | 8984 | 1 | 831 | 1 | 2 | 73333.3333 | 2 | 1 | 4 | 2200 | 1 | 0.68182 | 1 | 0.45728 | 0.27553
P 63 | 7 | 5 | 2 | 2 | 1 | 7213 | 3 | 1383 | 1.3 | 2 | 145833.3333 | 3 | 1 | 4 | 1170 | 2 | 0.96 | 2 | 0.086768 | 0.25385
Espirito Santo | 7 | 5 | 3 | 1 | 3 | 6153 | 3 | 787 | 1.5086 | 2 | 105000 | 3 | 5 | 4 | 1780 | 1 | 0.95238 | 2 | 0.24778 | 1.32
P 54 | 7 | 5 | 2 | 2 | 1 | 5272 | 3 | 1034 | 0.629 | 2 | 215000 | 5 | 3 | 4 | 1315 | 3 | 0.83721 | 1 | 0.24468 | 0.97138
Cidade de Campos dos Goytacazes MV29 | 7 | 4 | 2 | 1 | 3 | 9101 | 3 | 1018 | 1.263 | 2 | 179500 | 4 | 2 | 4 | 765 | 4 | 0.83565 | 1 | 0.27898 | 0.0055424
Terra Nova | 3 | 2 | 1 | 2 | 1 | 2800 | 3 | 1157 | 1.3 | 1 | 175000 | 4 | 5 | 4 | 90 | 1 | 0.85714 | 2 | 0.39412 | 0.30769
Sea Rose | 3 | 3 | 1 | 2 | 1 | 4476 | 3 | 1229 | 0.49 | 1 | 125000 | 3 | 5 | 4 | 120 | 1 | 0.8 | 4 | 0.072417 | 0.2
Turritella | 6 | 1 | 1 | 2 | 1 | 8528 | 3 | 1149 | 1 | 2 | 62500 | 2 | 4 | 4 | 2900 | 2 | 0.96 | 5 | 0.11227 | 0.311
Asgard A | 5 | 3 | 1 | 2 | 1 | 2356 | 4 | 870 | 5.2941 | 1 | 300000 | 6 | 4 | 4 | 300 | 1 | 0.66667 | 3 | 0.20805 | 0.36
Balder | 5 | 3 | 3 | 2 | 1 | 1826 | 4 | 592 | 0.35 | 1 | 90500 | 2 | 5 | 4 | 125 | 1 | 0.91713 | 1 | 1.9291 | 0.62
Goliat FPSO | 5 | 2 | 1 | 2 | 1 | 7218 | 3 | 1364 | 3.9 | 1 | 122500 | 3 | 5 | 4 | 400 | 1 | 0.81633 | 3 | 0.72361 | 0.94872
Petrojarl Knarr | 5 | 2 | 1 | 1 | 3 | 7850 | 3 | 732 | 1.6119 | 1 | 70833.3333 | 2 | 2 | 4 | 410 | 2 | 0.88941 | 4 | 0.85656 | 0.36975
Norne | 5 | 3 | 1 | 2 | 1 | 1551 | 3 | 1334 | 4.7 | 1 | 261666.6667 | 6 | 4 | 4 | 380 | 3 | 0.84076 | 2 | -0.12519 | 0.6
Skarv | 5 | 2 | 3 | 2 | 1 | 6240 | 3 | 1245 | 5 | 1 | 167500 | 4 | 4 | 4 | 370 | 1 | 0.47761 | 3 | 0.73494 | 0.7
Armada Kraken | 5 | 1 | 1 | 1 | 0 | 8719 | 3 | 1136 | 2.5 | 2 | 83333.3333 | 2 | 1 | 4 | 116 | 1 | 0.96 | 4 | 0.16285 | 0
Glen Lyon | 5 | 3 | 3 | 2 | 1 | 7729 | 3 | 1949 | 4.78 | 1 | 166666.6667 | 4 | 2 | 4 | 424 | 1 | 0.78 | 4 | 0.16675 | 0.19247
Western Isles FPSO | 5 | 1 | 1 | 2 | 1 | 8391 | 3 | 952 | 1.6 | 1 | 40000 | 1 | 3 | 4 | 165 | 2 | 1 | 3 | 0.8792 | 0.25
Belanak Natuna | 2 | 4 | 3 | 2 | 1 | 4250 | 4 | 1137 | 1.6 | 1 | 158333.3333 | 4 | 4 | 4 | 100 | 2 | 0.63158 | 4 | 0.058927 | 0.078167
Kikeh FPSO | 2 | 5 | 1 | 1 | 3 | 5513 | 3 | 939 | 0.8 | 2 | 143500 | 3 | 2 | 4 | 1350 | 1 | 0.83624 | 4 | -0.015974 | 0.2
Song Doc Pride MV 19 | 2 | 1 | 2 | 1 | 1 | 6339 | 3 | 417 | 0.25 | 2 | 30000 | 1 | 1 | 4 | 55 | 2 | 1 | 1 | 0.35012 | 0.04087
Thai Binh Vn | 2 | 1 | 2 | 2 | 1 | 4446 | 3 | 611 | 0.714 | 1 | 68333.3333 | 2 | 1 | 4 | 48 | 2 | 0.95122 | 3 | 0.037643 | 0.044
Hai Yang Shi You 117 | 8 | 4 | 2 | 2 | 1 | 5524 | 3 | 897 | 1.8 | 1 | 190000 | 4 | 1 | 4 | 27 | 1 | 1 | 3 | 0.72798 | 0.38889
Hai Yang Shi You 116 | 8 | 4 | 2 | 2 | 1 | 5804 | 3 | 723 | 1.2 | 1 | 106000 | 3 | 2 | 4 | 125 | 1 | 1 | 1 | 0.3195 | 0.98
Unity | 1 | 4 | 3 | 2 | 1 | 4018 | 3 | 545 | 1 | 1 | 125000 | 3 | 2 | 6 | 65 | 3 | 1 | 2 | 0.70092 | 0.4
Yoho | 1 | 3 | 3 | 2 | 1 | 4196 | 3 | 505 | 1.2 | 2 | 90000 | 2 | 2 | 6 | 56 | 1 | 1 | 1 | 0.20792 | 0.083333
Yoho | 1 | 3 | 3 | 2 | 1 | 4623 | 3 | 761 | 1.2 | 2 | 116666.6667 | 3 | 2 | 6 | 56 | 3 | 0.85714 | 2 | 0.6636 | 0.083333
Randgrid | 5 | 2 | 1 | 1 | 0 | 8521 | 3 | 1386 | 3.7 | 2 | 0 | 1 | 1 | 6 | 116 | 2 | 1 | 3 | 0.097403 | 0
Hanne Knutsen | 5 | 2 | 3 | 1 | 3 | 8124 | 3 | 1691 | 2.8649 | 2 | 100000 | 3 | 3 | 6 | 115 | 1 | 1 | 2 | 0.80958 | 0.85
Ailsa FSO | 5 | 2 | 3 | 2 | 1 | 9389 | 3 | 1364 | 4.7 | 1 | 108333.3333 | 3 | 2 | 6 | 90 | 5 | 0.23077 | 5 | 0 | 0
Gagak Rimang | 2 | 5 | 3 | 2 | 1 | 7891 | 3 | 1110 | 1.2 | 2 | 165000 | 4 | 2 | 6 | 33 | 1 | 1 | 2 | 0.42973 | 1.1667
Rang Dong MV17 | 2 | 1 | 2 | 1 | 3 | 6038 | 3 | 763 | 0.5 | 1 | 60000 | 2 | 1 | 6 | 60 | 2 | 1 | 1 | 0.10747 | 0.04087
Ichthys Explorer | 4 | 4 | 1 | 2 | 1 | 8046 | 3 | 1810 | 3 | 1 | 361166.6667 | 6 | 4 | 7 | 250 | 2 | 0.23535 | 5 | 0.35635 | 0.32353
P 51 | 7 | 5 | 2 | 2 | 1 | 5201 | 3 | 1418 | 0.83 | 1 | 215000 | 5 | 2 | 7 | 1250 | 5 | 0.83721 | 1 | 0.24401 | 0.25
P 56 | 7 | 5 | 2 | 2 | 1 | 6478 | 3 | 1114 | 1.4 | 1 | 135000 | 3 | 1 | 7 | 1670 | 5 | 0.74074 | 1 | 0.27379 | 0.071429
P 52 | 7 | 5 | 2 | 1 | 3 | 5060 | 3 | 1237 | 0.906 | 1 | 235000 | 5 | 2 | 7 | 1850 | 3 | 0.76596 | 1 | 0.19644 | 0.43488
Atlantis | 6 | 3 | 3 | 2 | 1 | 4533 | 3 | 1492 | 2.5 | 1 | 230000 | 5 | 3 | 7 | 2145 | 3 | 0.86957 | 1 | 0.60389 | 1.35
Delta House (Opti-Ex II) | 6 | 1 | 1 | 2 | 1 | 8158 | 3 | 1093 | 2 | 1 | 140000 | 3 | 2 | 7 | 1372 | 5 | 0.71429 | 2 | -0.012809 | 0
Blind Faith | 6 | 2 | 3 | 2 | 1 | 5802 | 3 | 846 | 1.151 | 1 | 52500 | 2 | 4 | 7 | 2130 | 1 | 0.85714 | 5 | 0.28605 | 0.95
Thunder Hawk
Thunder Horse | 6 | 2 | 1 | 2 | 1 | 4077 | 4 | 579 | 0.2 | 1 | 58333.3333 | 2 | 3 | 3 | 675 | 1 | 0.68571 | 1 | 0.74266 | 0.365
Jack / St. Malo Semi | 5 | 2 | 1 | 1 | 3 | 7850 | 3 | 732 | 1.6119 | 1 | 70833.3333 | 2 | 2 | 4 | 410 | 2 | 0.88941 | 4 | 0.85656 | 0.36975
Asgard B | 1 | 3 | 3 | 2 | 1 | 4196 | 3 | 505 | 1.2 | 2 | 90000 | 2 | 2 | 6 | 56 | 1 | 1 | 1 | 0.20792 | 0.083333
Gjoa | 5 | 3 | 1 | 2 | 1 | 379 | 3 | 1263 | 2.9 | 1 | 317000 | 6 | 5 | 7 | 320 | 2 | 0.85174 | 3 | 0.35234 | 0.14
Kristin | 6 | 3 | 3 | 2 | 1 | 7571 | 3 | 1529 | 4 | 1 | 79166.6667 | 2 | 5 | 1 | 1580 | 1 | 0.94737 | 4 | 0.94899 | 0.375
Snorre B | 2 | 1 | 2 | 1 | 3 | 6038 | 3 | 763 | 0.5 | 1 | 60000 | 2 | 1 | 6 | 60 | 2 | 1 | 1 | 0.10747 | 0.04087
Troll B | 5 | 3 | 3 | 2 | 1 | 1826 | 4 | 592 | 0.35 | 1 | 90500 | 2 | 5 | 4 | 125 | 1 | 0.91713 | 1 | 1.9291 | 0.62
Visund | 5 | 1 | 1 | 2 | 1 | 8391 | 3 | 952 | 1.6 | 1 | 40000 | 1 | 3 | 4 | 165 | 2 | 1 | 3 | 0.8792 | 0.25
Gumusut Semi | 7 | 5 | 2 | 2 | 1 | 6478 | 3 | 1114 | 1.4 | 1 | 135000 | 3 | 1 | 7 | 1670 | 5 | 0.74074 | 1 | 0.27379 | 0.071429
Front Runner Spar | 2 | 5 | 3 | 1 | 3 | 6588 | 3 | 1233 | 1.6 | 1 | 200000 | 5 | 2 | 7 | 1220 | 2 | 0.75 | 3 | 0.99919 | 0.25
Tahiti Spar | 1 | 4 | 3 | 2 | 1 | 3103 | 3 | 823 | 2.5 | 1 | 246666.6667 | 5 | 3 | 4 | 1350 | 1 | 0.81081 | 1 | 0.52126 | 0.12
Mad Dog | 2 | 5 | 3 | 2 | 1 | 8439 | 3 | 1030 | 1.2825 | 1 | 68333.3333 | 2 | 2 | 1 | 470 | 3 | 0.87805 | 5 | 0.36796 | 0.077973
Heidelberg Spar | 6 | 2 | 1 | 2 | 1 | 4459 | 4 | 728 | 0.2 | 1 | 78333.3333 | 2 | 3 | 3 | 1015 | 1 | 0.76596 | 1 | 0.36676 | 0.075
Lucius Spar | 6 | 3 | 1 | 1 | 3 | 4189 | 4 | 739 | 0.2 | 1 | 66666.6667 | 2 | 2 | 3 | 1710 | 2 | 0.9 | 1 | 0.41949 | 0.06
Medusa Spar | 1 | 3 | 3 | 2 | 1 | 4623 | 3 | 761 | 1.2 | 2 | 116666.6667 | 3 | 2 | 6 | 56 | 3 | 0.85714 | 2 | 0.6636 | 0.083333
Gulfstar 1 | 2 | 1 | 2 | 1 | 1 | 6339 | 3 | 417 | 0.25 | 2 | 30000 | 1 | 1 | 4 | 55 | 2 | 1 | 1 | 0.35012 | 0.04087
Devil's Tower Spar | 6 | 1 | 1 | 2 | 1 | 8002 | 3 | 1007 | 7.736 | 1 | 155000 | 4 | 4 | 3 | 2165 | 4 | 0.51613 | 5 | 0.14002 | 0.008273
Kikeh Spar | 7 | 4 | 2 | 1 | 3 | 9101 | 3 | 1018 | 1.263 | 2 | 179500 | 4 | 2 | 4 | 765 | 4 | 0.83565 | 1 | 0.27898 | 0.0055424
Kizomba A Wellhead TLP | 6 | 1 | 3 | 2 | 1 | 7729 | 3 | 1202 | 3 | 1 | 116666.6667 | 3 | 2 | 1 | 945 | 5 | 0.85714 | 5 | -0.12562 | 0
Kizomba B Wellhead TLP | 1 | 4 | 3 | 1 | 1 | 5866 | 3 | 797 | 0.75 | 2 | 115833.3333 | 3 | 1 | 4 | 728 | 3 | 0.86331 | 3 | -0.10163 | 0
Okume TLP | 6 | 2 | 1 | 2 | 1 | 6001 | 3 | 1119 | 4.41 | 1 | 116666.6667 | 3 | 2 | 1 | 1333 | 2 | 0.85714 | 5 | -0.088472 | 0
Oveng TLP | 1 | 4 | 3 | 1 | 3 | 5866 | 3 | 797 | 0.75 | 2 | 130000 | 3 | 1 | 4 | 720 | 3 | 0.80769 | 3 | -0.084065 | 0
P 61 Wellhead TLP | 6 | 1 | 1 | 2 | 1 | 8158 | 3 | 1093 | 2 | 1 | 140000 | 3 | 2 | 7 | 1372 | 5 | 0.71429 | 2 | -0.012809 | 0
Auger TLP | 6 | 1 | 3 | 2 | 1 | 7270 | 3 | 1844 | 7.5 | 1 | 177166.6667 | 4 | 1 | 7 | 2134 | 4 | 0.95955 | 5 | -0.005423 | 0
Magnolia TLP | 5 | 2 | 3 | 2 | 1 | 9389 | 3 | 1364 | 4.7 | 1 | 108333.3333 | 3 | 2 | 6 | 90 | 5 | 0.23077 | 5 | 0 | 0
Brutus TLP | 5 | 4 | 1 | 2 | 1 | 2356 | 4 | 1570 | 1.3 | 1 | 351666.6667 | 6 | 1 | 7 | 300 | 5 | 0.38389 | 4 | 0 | 0
Stampede TLP | 6 | 1 | 3 | 2 | 1 | 1885 | 3 | 915 | 1 | 1 | 93333.3333 | 2 | 3 | 1 | 990 | 5 | 0.64286 | 4 | 0.015301 | 0
Neptune TLP | 6 | 1 | 3 | 2 | 1 | 4392 | 3 | 1040 | 0.6 | 1 | 75000 | 2 | 4 | 1 | 1432 | 2 | 0.66667 | 5 | 0.038462 | 0
Shenzi TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.1425 | 1 | 30000 | 1 | 1 | 1 | 500 | 4 | 0.83333 | 4 | 0.04 | 0
Mars TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.1425 | 1 | 30000 | 1 | 1 | 1 | 280 | 4 | 0.83333 | 4 | 0.04 | 0
Olympus TLP | 1 | 1 | 1 | 1 | 3 | 4949 | 3 | 711 | 1.5 | 2 | 82500 | 2 | 1 | 4 | 970 | 3 | 0.84848 | 2 | 0.067511 | 0
Ursa TLP | 6 | 1 | 1 | 1 | 3 | 6086 | 3 | 958 | 0.8 | 1 | 56666.6667 | 2 | 1 | 7 | 1847 | 4 | 0.79412 | 5 | 0.087683 | 0
Ram Powell TLP | 5 | 2 | 1 | 1 | 0 | 8521 | 3 | 1386 | 3.7 | 2 | 0 | 1 | 1 | 6 | 116 | 2 | 1 | 3 | 0.097403 | 0
Big Foot | 5 | 1 | 1 | 1 | 0 | 8719 | 3 | 1136 | 2.5 | 2 | 83333.3333 | 2 | 1 | 4 | 116 | 1 | 0.96 | 4 | 0.16285 | 0
Heidrun TLP | 7 | 4 | 2 | 1 | 3 | 8352 | 3 | 838 | 1.17 | 2 | 196666.6667 | 4 | 1 | 4 | 2240 | 3 | 0.76271 | 1 | 0.18138 | 0
Malikai TLP | 7 | 5 | 2 | 2 | 1 | 7213 | 3 | 1475 | 1.07 | 1 | 145833.3333 | 3 | 3 | 1 | 1180 | 1 | 0.96 | 2 | 0.35051 | 0

## Cost_Sch_Class
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun | chd
Rang Dong MV17 | 2 | 1 | 2 | 1 | 3 | 6038 | 3 | 763 | 0.5 | 1 | 60000 | 2 | 1 | 6 | 60 | 2 | 1 | 1 | 0.10747 | 0.04087 | 1
Lucius Spar | 6 | 1 | 1 | 2 | 1 | 8002 | 3 | 1007 | 7.736 | 1 | 155000 | 4 | 4 | 3 | 2165 | 4 | 0.51613 | 5 | 0.14002 | 0.008273 | 1
Armada Kraken | 5 | 1 | 1 | 1 | 0 | 8719 | 3 | 1136 | 2.5 | 2 | 83333.3333 | 2 | 1 | 4 | 116 | 1 | 0.96 | 4 | 0.16285 | 0 | 1
Cidade de Itaguai MV26 | 7 | 4 | 2 | 1 | 3 | 8352 | 3 | 838 | 1.17 | 2 | 196666.6667 | 4 | 1 | 4 | 2240 | 3 | 0.76271 | 1 | 0.18138 | 0 | 1
Yoho | 1 | 3 | 3 | 2 | 1 | 4196 | 3 | 505 | 1.2 | 2 | 90000 | 2 | 2 | 6 | 56 | 1 | 1 | 1 | 0.20792 | 0.083333 | 1
P 56 | 7 | 5 | 2 | 2 | 1 | 6478 | 3 | 1114 | 1.4 | 1 | 135000 | 3 | 1 | 7 | 1670 | 5 | 0.74074 | 1 | 0.27379 | 0.071429 | 1
Cidade de Campos dos Goytacazes MV29 | 7 | 4 | 2 | 1 | 3 | 9101 | 3 | 1018 | 1.263 | 2 | 179500 | 4 | 2 | 4 | 765 | 4 | 0.83565 | 1 | 0.27898 | 0.0055424 | 1
Song Doc Pride MV 19 | 2 | 1 | 2 | 1 | 1 | 6339 | 3 | 417 | 0.25 | 2 | 30000 | 1 | 1 | 4 | 55 | 2 | 1 | 1 | 0.35012 | 0.04087 | 1
P 61 Wellhead TLP | 7 | 5 | 2 | 2 | 1 | 7213 | 3 | 1475 | 1.07 | 1 | 145833.3333 | 3 | 3 | 1 | 1180 | 1 | 0.96 | 2 | 0.35051 | 0 | 1
Troll B | 5 | 3 | 1 | 2 | 1 | 379 | 3 | 1263 | 2.9 | 1 | 317000 | 6 | 5 | 7 | 320 | 2 | 0.85174 | 3 | 0.35234 | 0.14 | 1
Front Runner Spar | 6 | 2 | 1 | 2 | 1 | 4459 | 4 | 728 | 0.2 | 1 | 78333.3333 | 2 | 3 | 3 | 1015 | 1 | 0.76596 | 1 | 0.36676 | 0.075 | 1
Malikai TLP | 2 | 5 | 3 | 2 | 1 | 8439 | 3 | 1030 | 1.2825 | 1 | 68333.3333 | 2 | 2 | 1 | 470 | 3 | 0.87805 | 5 | 0.36796 | 0.077973 | 1
Devil's Tower Spar | 6 | 3 | 1 | 1 | 3 | 4189 | 4 | 739 | 0.2 | 1 | 66666.6667 | 2 | 2 | 3 | 1710 | 2 | 0.9 | 1 | 0.41949 | 0.06 | 1 | 0 | 699.1%
Girassol | 1 | 4 | 3 | 2 | 1 | 3103 | 3 | 823 | 2.5 | 1 | 246666.6667 | 5 | 3 | 4 | 1350 | 1 | 0.81081 | 1 | 0.52126 | 0.12 | 1
Yoho | 1 | 3 | 3 | 2 | 1 | 4623 | 3 | 761 | 1.2 | 2 | 116666.6667 | 3 | 2 | 6 | 56 | 3 | 0.85714 | 2 | 0.6636 | 0.083333 | 1
Medusa Spar | 6 | 2 | 1 | 2 | 1 | 4077 | 4 | 579 | 0.2 | 1 | 58333.3333 | 2 | 3 | 3 | 675 | 1 | 0.68571 | 1 | 0.74266 | 0.365 | 1
Petrojarl Knarr | 5 | 2 | 1 | 1 | 3 | 7850 | 3 | 732 | 1.6119 | 1 | 70833.3333 | 2 | 2 | 4 | 410 | 2 | 0.88941 | 4 | 0.85656 | 0.36975 | 1
Western Isles FPSO | 5 | 1 | 1 | 2 | 1 | 8391 | 3 | 952 | 1.6 | 1 | 40000 | 1 | 3 | 4 | 165 | 2 | 1 | 3 | 0.8792 | 0.25 | 1
Big Foot | 6 | 3 | 3 | 2 | 1 | 7571 | 3 | 1529 | 4 | 1 | 79166.6667 | 2 | 5 | 1 | 1580 | 1 | 0.94737 | 4 | 0.94899 | 0.375 | 1
Gumusut Semi | 2 | 5 | 3 | 1 | 3 | 6588 | 3 | 1233 | 1.6 | 1 | 200000 | 5 | 2 | 7 | 1220 | 2 | 0.75 | 3 | 0.99919 | 0.25 | 1 | 0 | 399.7%
Balder | 5 | 3 | 3 | 2 | 1 | 1826 | 4 | 592 | 0.35 | 1 | 90500 | 2 | 5 | 4 | 125 | 1 | 0.91713 | 1 | 1.9291 | 0.62 | 1
Stybarrow Venture MV16 | 4 | 3 | 3 | 1 | 3 | 5922 | 3 | 702 | 0.59843 | 1 | 87500 | 2 | 3 | 4 | 825 | 2 | 0.91429 | 4 | -0.14387 | 0.27 | 0
Norne | 5 | 3 | 1 | 2 | 1 | 1551 | 3 | 1334 | 4.7 | 1 | 261666.6667 | 6 | 4 | 4 | 380 | 3 | 0.84076 | 2 | -0.12519 | 0.6 | 0
Alima FPU | 1 | 2 | 3 | 2 | 1 | 5720 | 3 | 994 | 1.133 | 1 | 100000 | 3 | 1 | 2 | 600 | 3 | 0.9 | 4 | -0.022133 | 0.35 | 0
Kikeh Spar | 2 | 5 | 1 | 2 | 1 | 5513 | 3 | 939 | 0.5 | 1 | 142500 | 3 | 4 | 3 | 1330 | 1 | 0.84211 | 4 | -0.015974 | 0.28571 | 0 | 0 | -5.591%
Kristin | 5 | 4 | 1 | 2 | 1 | 4368 | 3 | 1384 | 1.9 | 1 | 128000 | 3 | 5 | 7 | 370 | 1 | 0.97656 | 2 | 0.023844 | 0.73684 | 0
Akpo | 1 | 4 | 3 | 2 | 1 | 5606 | 4 | 1303 | 2.345 | 1 | 273333.3333 | 6 | 4 | 4 | 1325 | 1 | 0.67683 | 2 | 0.072141 | 1.55 | 0 | 0 | 4.654%
Auger TLP | 6 | 2 | 3 | 2 | 1 | 287 | 3 | 1233 | 0.86364 | 1 | 65000 | 2 | 4 | 1 | 870 | 2 | 0.61538 | 4 | 0.044607 | 0.38947 | 0 | 0 | 11.45%
Tahiti Spar | 6 | 2 | 3 | 2 | 1 | 5597 | 3 | 1159 | 3.5 | 1 | 136666.6667 | 3 | 3 | 3 | 1280 | 2 | 0.91463 | 2 | 0.26747 | 1.8 | 0
Frade | 7 | 3 | 3 | 2 | 1 | 6014 | 3 | 909 | 2 | 2 | 117666.6667 | 3 | 2 | 4 | 1080 | 1 | 0.84986 | 4 | 0.20902 | 1.35 | 0
Espirito Santo | 7 | 5 | 3 | 1 | 3 | 6153 | 3 | 787 | 1.5086 | 2 | 105000 | 3 | 5 | 4 | 1780 | 1 | 0.95238 | 2 | 0.24778 | 1.32 | 0
Greater Plutonio | 1 | 3 | 3 | 2 | 1 | 5144 | 3 | 1124 | 1.73 | 1 | 305000 | 6 | 3 | 4 | 1350 | 2 | 0.81967 | 4 | 0.19039 | 0.85 | 0
P 54 | 7 | 5 | 2 | 2 | 1 | 5272 | 3 | 1034 | 0.629 | 2 | 215000 | 5 | 3 | 4 | 1315 | 3 | 0.83721 | 1 | 0.24468 | 0.97138 | 0
Gulfstar 1 | 6 | 1 | 3 | 1 | 3 | 7813 | 3 | 1132 | 2.3 | 1 | 109166.6667 | 3 | 2 | 3 | 1310 | 2 | 0.73282 | 3 | 0.12191 | 0.47826 | 0
Gjoa | 5 | 2 | 1 | 2 | 1 | 6025 | 2 | 1461 | 4.4361 | 1 | 108333.3333 | 3 | 4 | 7 | 380 | 1 | 0.46154 | 3 | 0.08898 | 0.33 | 0
Blind Faith | 6 | 2 | 3 | 2 | 1 | 5802 | 3 | 846 | 1.151 | 1 | 52500 | 2 | 4 | 7 | 2130 | 1 | 0.85714 | 5 | 0.28605 | 0.95 | 0
Hai Yang Shi You 116 | 8 | 4 | 2 | 2 | 1 | 5804 | 3 | 723 | 1.2 | 1 | 106000 | 3 | 2 | 4 | 125 | 1 | 1 | 1 | 0.3195 | 0.98 | 0 | 1 | 32.6%
Erha | 1 | 4 | 3 | 2 | 1 | 4671 | 3 | 1081 | 2.6 | 1 | 266666.6667 | 6 | 2 | 4 | 1180 | 2 | 0.7875 | 2 | 0.19334 | 0.57 | 0
P 63 | 7 | 5 | 2 | 2 | 1 | 7213 | 3 | 1383 | 1.3 | 2 | 145833.3333 | 3 | 1 | 4 | 1170 | 2 | 0.96 | 2 | 0.086768 | 0.25385 | 0
Thunder Horse | 6 | 3 | 3 | 2 | 1 | 4624 | 3 | 1098 | 5 | 1 | 283333.3333 | 6 | 5 | 7 | 1830 | 1 | 0.88235 | 4 | 0.92623 | 2.68 | 0 | 0 | 34.56%
Turritella | 6 | 1 | 1 | 2 | 1 | 8528 | 3 | 1149 | 1 | 2 | 62500 | 2 | 4 | 4 | 2900 | 2 | 0.96 | 5 | 0.11227 | 0.311 | 0
Gagak Rimang | 2 | 5 | 3 | 2 | 1 | 7891 | 3 | 1110 | 1.2 | 2 | 165000 | 4 | 2 | 6 | 33 | 1 | 1 | 2 | 0.42973 | 1.1667 | 0
Agbami | 1 | 2 | 3 | 2 | 2 | 5539 | 3 | 1126 | 4.1538 | 1 | 325000 | 6 | 2 | 4 | 1433 | 2 | 0.76923 | 2 | 0.11368 | 0.3 | 0
Ngujima Yin | 4 | 3 | 3 | 2 | 1 | 5993 | 3 | 716 | 0.72 | 2 | 136666.6667 | 3 | 2 | 4 | 340 | 2 | 0.87805 | 3 | 0.14665 | 0.33333 | 0 | 1 | 43.99%
Atlantis | 6 | 3 | 3 | 2 | 1 | 4533 | 3 | 1492 | 2.5 | 1 | 230000 | 5 | 3 | 7 | 2145 | 3 | 0.86957 | 1 | 0.60389 | 1.35 | 0
P 52 | 7 | 5 | 2 | 1 | 3 | 5060 | 3 | 1237 | 0.906 | 1 | 235000 | 5 | 2 | 7 | 1850 | 3 | 0.76596 | 1 | 0.19644 | 0.43488 | 0
Neptune TLP | 6 | 2 | 1 | 2 | 1 | 5670 | 3 | 887 | 0.85 | 1 | 58333.3333 | 2 | 2 | 1 | 1300 | 2 | 0.85714 | 3 | 0.2345 | 0.47882 | 0

## Cost_T1
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun | 18 | 11 | 7 | Error(18) | Error(11) | Error(7)
Bohai Ming Zhu | 8 | 5 | 2 | 2 | 1 | 4350 | 3 | 259 | 0.4 | 1 | 40000 | 1 | 2 | 4 | 30 | 1 | 1 | 1 | 0.47104 | 25% | 28.11% | 29.16% | 42.99% | -12.43% | -16.63% | -71.96%
Petrojarl Varg | 5 | 1 | 1 | 1 | 1 | 2240 | 3 | 816 | 0.46 | 1 | 65833.3333 | 2 | 2 | 4 | 84 | 1 | 0.86582 | 2 | 0.28676 | 24% | 27.91% | 26.03% | 21.45% | -16.3% | -8.463% | 10.62%
Stybarrow Venture MV16 | 4 | 3 | 3 | 1 | 3 | 5922 | 3 | 702 | 0.59843 | 1 | 87500 | 2 | 3 | 4 | 825 | 2 | 0.91429 | 4 | -0.14387 | 27% | 27.81% | 25.52% | 10.21% | -2.989% | 5.485% | 62.19%
Alima FPU | 1 | 2 | 3 | 2 | 1 | 5720 | 3 | 994 | 1.133 | 1 | 100000 | 3 | 1 | 2 | 600 | 3 | 0.9 | 4 | -0.022133 | 35% | 28.03% | 23.72% | 6.583% | 19.9% | 32.22% | 81.19%
Jangkrik | 2 | 4 | 1 | 2 | 1 | 8824 | 3 | 1052 | 2.6765 | 1 | 79400 | 2 | 2 | 2 | 120 | 2 | 0.055416 | 3 | 0.11407 | 17% | 28.81% | 25.07% | 29.7% | -69.45% | -47.45% | -74.7%
Prelude | 4 | 3 | 3 | 2 | 1 | 7814 | 3 | 2229 | 11.16 | 1 | 148333.3333 | 6 | 5 | 5 | 250 | 1 | 0.23596 | 5 | 0.24316 | 34.41% | 28.71% | 29.98% | 53.73% | 16.56% | 12.88% | -56.14%
CLOV FPSO | 1 | 3 | 3 | 2 | 1 | 7534 | 3 | 1383 | 7 | 1 | 198333.3333 | 4 | 2 | 4 | 1290 | 4 | 0.80672 | 5 | 0.0079537 | 14.29% | 28.14% | 23.38% | 4.382% | -96.98% | -63.63% | 69.32%
Dalia | 1 | 4 | 3 | 2 | 1 | 4872 | 3 | 1306 | 3.4 | 1 | 287000 | 6 | 3 | 4 | 1360 | 5 | 0.83624 | 2 | 0.01072 | 17.65% | 28.19% | 24.57% | 9.646% | -59.74% | -39.2% | 45.34%
Girassol | 1 | 4 | 3 | 2 | 1 | 3103 | 3 | 823 | 2.5 | 1 | 246666.6667 | 5 | 3 | 4 | 1350 | 1 | 0.81081 | 1 | 0.52126 | 12% | 28.22% | 28.5% | 42.9% | -135.1% | -137.5% | -257.5%
Kizomba B | 1 | 3 | 3 | 2 | 1 | 4756 | 3 | 1071 | 0.76 | 1 | 316666.6667 | 6 | 1 | 4 | 1250 | 5 | 0.78947 | 2 | -0.14006 | 13.33% | 27.96% | 23.46% | 4.097% | -109.7% | -75.94% | 69.27%
Mondo | 1 | 4 | 3 | 1 | 1 | 5866 | 3 | 797 | 0.75 | 2 | 115833.3333 | 3 | 1 | 4 | 728 | 3 | 0.86331 | 3 | -0.10163 | 0% | 28.24% | 24.61% | 6.966% | -28.24% | -24.61% | -6.966%
Saxi-Batuque | 1 | 4 | 3 | 1 | 3 | 5866 | 3 | 797 | 0.75 | 2 | 130000 | 3 | 1 | 4 | 720 | 3 | 0.80769 | 3 | -0.084065 | 0% | 28.17% | 24.57% | 6.966% | -28.17% | -24.57% | -6.966%
Greater Plutonio | 1 | 3 | 3 | 2 | 1 | 5144 | 3 | 1124 | 1.73 | 1 | 305000 | 6 | 3 | 4 | 1350 | 2 | 0.81967 | 4 | 0.19039 | 85% | 28.11% | 26.02% | 19.41% | 66.93% | 69.39% | 77.16%
PSVM FPSO | 1 | 5 | 3 | 2 | 1 | 6755 | 3 | 1249 | 10 | 2 | 197833.3333 | 4 | 5 | 4 | 2000 | 2 | 0.7936 | 1 | 0.29704 | 40% | 28.89% | 29.22% | 37.04% | 27.77% | 26.94% | 7.391%
Baobab Ivoirien MV10 | 1 | 1 | 1 | 1 | 3 | 4949 | 3 | 711 | 1.5 | 2 | 82500 | 2 | 1 | 4 | 970 | 3 | 0.84848 | 2 | 0.067511 | 0% | 28.29% | 23.66% | 4.985% | -28.29% | -23.66% | -4.985%
Prof. John Evans Atta Mills | 1 | 4 | 3 | 1 | 3 | 8617 | 3 | 1092 | 4.5 | 2 | 108333.3333 | 3 | 1 | 4 | 1425 | 2 | 0.73846 | 5 | 0.015568 | 8.889% | 28.18% | 24.23% | 6.644% | -217% | -172.6% | 25.26%
Agbami | 1 | 2 | 3 | 2 | 2 | 5539 | 3 | 1126 | 4.1538 | 1 | 325000 | 6 | 2 | 4 | 1433 | 2 | 0.76923 | 2 | 0.11368 | 30% | 28.09% | 25.6% | 17.46% | 6.383% | 14.65% | 41.81%
Akpo | 1 | 4 | 3 | 2 | 1 | 5606 | 4 | 1303 | 2.345 | 1 | 273333.3333 | 6 | 4 | 4 | 1325 | 1 | 0.67683 | 2 | 0.072141 | 155% | 28.28% | 27.12% | 36.02% | 81.75% | 82.5% | 76.76%
Bonga | 1 | 4 | 3 | 2 | 1 | 4049 | 3 | 1033 | 2.4 | 1 | 253333.3333 | 6 | 3 | 4 | 1250 | 1 | 0.88816 | 3 | 0.70765 | 50% | 28.23% | 28.26% | 39.46% | 43.53% | 43.48% | 21.07%
Egina FPSO | 1 | 5 | 3 | 2 | 1 | 8540 | 3 | 1595 | 15 | 1 | 260000 | 6 | 2 | 4 | 1600 | 3 | 0.76923 | 2 | 0.28715 | -3.333% | 28.27% | 24.75% | 22.73% | -28.27% | -24.75% | -22.73%
Erha | 1 | 4 | 3 | 2 | 1 | 4671 | 3 | 1081 | 2.6 | 1 | 266666.6667 | 6 | 2 | 4 | 1180 | 2 | 0.7875 | 2 | 0.19334 | 57% | 28.2% | 26.62% | 27.48% | 50.53% | 53.3% | 51.78%
Kizomba A | 1 | 3 | 3 | 2 | 1 | 4253 | 3 | 1073 | 0.77 | 1 | 316666.6667 | 6 | 2 | 4 | 1250 | 3 | 0.78947 | 2 | 0.0055918 | 13.33% | 28.09% | 25.44% | 14.94% | -110.7% | -90.82% | -12.02%
Ichthys Venturer | 4 | 4 | 3 | 2 | 1 | 8102 | 3 | 1743 | 2 | 1 | 85000 | 2 | 5 | 4 | 250 | 2 | 1 | 5 | 0.37636 | 32.35% | 28.58% | 27.8% | 33.08% | 11.65% | 14.09% | -2.238%
Pyrenees Venture | 4 | 3 | 3 | 2 | 2 | 6379 | 3 | 1014 | 1.66 | 2 | 106000 | 3 | 4 | 4 | 200 | 4 | 0.90566 | 5 | 0.0019724 | 1.203% | 28.51% | 25.9% | 12.76% | -2271% | -2053% | -960.5%
Ngujima Yin | 4 | 3 | 3 | 2 | 1 | 5993 | 3 | 716 | 0.72 | 2 | 136666.6667 | 3 | 2 | 4 | 340 | 2 | 0.87805 | 3 | 0.14665 | 33.33% | 28.37% | 26.73% | 24.12% | 14.88% | 19.82% | 27.65%
P 50 | 7 | 4 | 2 | 2 | 1 | 4557 | 2 | 844 | 0.496 | 2 | 215000 | 5 | 4 | 4 | 1240 | 1 | 0.83721 | 1 | 0.66351 | 41.13% | 28.2% | 26.46% | 22.47% | 31.44% | 35.66% | 45.36%
P 43 | 7 | 5 | 2 | 2 | 1 | 4199 | 4 | 883 | 1.3 | 2 | 185000 | 4 | 3 | 4 | 800 | 1 | 0.81081 | 1 | 0.43828 | 38.46% | 28.26% | 26.58% | 27.28% | 26.52% | 30.9% | 29.06%
P 48 | 7 | 5 | 2 | 2 | 1 | 4199 | 4 | 1066 | 1.3 | 2 | 185000 | 4 | 1 | 4 | 1040 | 2 | 0.81081 | 1 | 0.25516 | 38.46% | 28.32% | 28.57% | 41.26% | 26.36% | 25.71% | -7.273%
Frade | 7 | 3 | 3 | 2 | 1 | 6014 | 3 | 909 | 2 | 2 | 117666.6667 | 3 | 2 | 4 | 1080 | 1 | 0.84986 | 4 | 0.20902 | 135% | 28.11% | 27.55% | 44.95% | 79.18% | 79.59% | 66.7%
Cidade de Itaguai MV26 | 7 | 4 | 2 | 1 | 3 | 8352 | 3 | 838 | 1.17 | 2 | 196666.6667 | 4 | 1 | 4 | 2240 | 3 | 0.76271 | 1 | 0.18138 | 0% | 28.16% | 26.04% | 10.6% | -28.16% | -26.04% | -10.6%
P 57 | 7 | 5 | 2 | 1 | 2 | 6622 | 3 | 1041 | 1.195 | 2 | 191833.3333 | 4 | 1 | 4 | 1300 | 4 | 0.93831 | 1 | -0.045149 | 0.4184% | 28.13% | 24.14% | 8.875% | -6623% | -5669% | -2021%
Pioneiro de Libra | 7 | 5 | 2 | 1 | 3 | 8984 | 1 | 831 | 1 | 2 | 73333.3333 | 2 | 1 | 4 | 2200 | 1 | 0.68182 | 1 | 0.45728 | 27.55% | 28.47% | 27.97% | 36.99% | -3.313% | -1.497% | -34.26%
P 63 | 7 | 5 | 2 | 2 | 1 | 7213 | 3 | 1383 | 1.3 | 2 | 145833.3333 | 3 | 1 | 4 | 1170 | 2 | 0.96 | 2 | 0.086768 | 25.38% | 28.3% | 30.95% | 11.31% | -11.49% | -21.91% | 55.46%
Espirito Santo | 7 | 5 | 3 | 1 | 3 | 6153 | 3 | 787 | 1.5086 | 2 | 105000 | 3 | 5 | 4 | 1780 | 1 | 0.95238 | 2 | 0.24778 | 132% | 28.37% | 26.61% | 23.87% | 78.51% | 79.84% | 81.91%
P 54 | 7 | 5 | 2 | 2 | 1 | 5272 | 3 | 1034 | 0.629 | 2 | 215000 | 5 | 3 | 4 | 1315 | 3 | 0.83721 | 1 | 0.24468 | 97.14% | 28.44% | 26.45% | 11.15% | 70.72% | 72.77% | 88.52%
Cidade de Campos dos Goytacazes MV29 | 7 | 4 | 2 | 1 | 3 | 9101 | 3 | 1018 | 1.263 | 2 | 179500 | 4 | 2 | 4 | 765 | 4 | 0.83565 | 1 | 0.27898 | 0.5542% | 28.61% | 29.65% | 44.1% | -5061% | -5250% | -7858%
Terra Nova | 3 | 2 | 1 | 2 | 1 | 2800 | 3 | 1157 | 1.3 | 1 | 175000 | 4 | 5 | 4 | 90 | 1 | 0.85714 | 2 | 0.39412 | 30.77% | 28.66% | 28.93% | 42.76% | 6.854% | 5.987% | -38.96%
Sea Rose | 3 | 3 | 1 | 2 | 1 | 4476 | 3 | 1229 | 0.49 | 1 | 125000 | 3 | 5 | 4 | 120 | 1 | 0.8 | 4 | 0.072417 | 20% | 28.62% | 26.26% | 32.52% | -43.08% | -31.29% | -62.58%
Turritella | 6 | 1 | 1 | 2 | 1 | 8528 | 3 | 1149 | 1 | 2 | 62500 | 2 | 4 | 4 | 2900 | 2 | 0.96 | 5 | 0.11227 | 31.1% | 28.23% | 29.39% | 47.16% | 9.223% | 5.483% | -51.64%
Asgard A | 5 | 3 | 1 | 2 | 1 | 2356 | 4 | 870 | 5.2941 | 1 | 300000 | 6 | 4 | 4 | 300 | 1 | 0.66667 | 3 | 0.20805 | 36% | 28.25% | 30.33% | 40.53% | 21.52% | 15.74% | -12.59%
Balder | 5 | 3 | 3 | 2 | 1 | 1826 | 4 | 592 | 0.35 | 1 | 90500 | 2 | 5 | 4 | 125 | 1 | 0.91713 | 1 | 1.9291 | 62% | 28.68% | 28.5% | 46.69% | 53.75% | 54.03% | 24.7%
Goliat FPSO | 5 | 2 | 1 | 2 | 1 | 7218 | 3 | 1364 | 3.9 | 1 | 122500 | 3 | 5 | 4 | 400 | 1 | 0.81633 | 3 | 0.72361 | 94.87% | 28.05% | 24.71% | 11.28% | 70.43% | 73.95% | 88.11%
Petrojarl Knarr | 5 | 2 | 1 | 1 | 3 | 7850 | 3 | 732 | 1.6119 | 1 | 70833.3333 | 2 | 2 | 4 | 410 | 2 | 0.88941 | 4 | 0.85656 | 36.97% | 28.08% | 26.66% | 23.72% | 24.06% | 27.89% | 35.84%
Norne | 5 | 3 | 1 | 2 | 1 | 1551 | 3 | 1334 | 4.7 | 1 | 261666.6667 | 6 | 4 | 4 | 380 | 3 | 0.84076 | 2 | -0.12519 | 60% | 28.25% | 27.51% | 46.38% | 52.92% | 54.14% | 22.7%
Skarv | 5 | 2 | 3 | 2 | 1 | 6240 | 3 | 1245 | 5 | 1 | 167500 | 4 | 4 | 4 | 370 | 1 | 0.47761 | 3 | 0.73494 | 70% | 28.23% | 26.72% | 41.99% | 59.67% | 61.83% | 40.01%
Armada Kraken | 5 | 1 | 1 | 1 | 0 | 8719 | 3 | 1136 | 2.5 | 2 | 83333.3333 | 2 | 1 | 4 | 116 | 1 | 0.96 | 4 | 0.16285 | 0% | 28.55% | 25.67% | 28.35% | -28.55% | -25.67% | -28.35%
Glen Lyon | 5 | 3 | 3 | 2 | 1 | 7729 | 3 | 1949 | 4.78 | 1 | 166666.6667 | 4 | 2 | 4 | 424 | 1 | 0.78 | 4 | 0.16675 | 19.25% | 28.37% | 27.28% | 32.25% | -47.39% | -41.75% | -67.54%
Western Isles FPSO | 5 | 1 | 1 | 2 | 1 | 8391 | 3 | 952 | 1.6 | 1 | 40000 | 1 | 3 | 4 | 165 | 2 | 1 | 3 | 0.8792 | 25% | 28.42% | 27.16% | 11.9% | -13.69% | -8.656% | 52.41%
Belanak Natuna | 2 | 4 | 3 | 2 | 1 | 4250 | 4 | 1137 | 1.6 | 1 | 158333.3333 | 4 | 4 | 4 | 100 | 2 | 0.63158 | 4 | 0.058927 | 7.817% | 28.45% | 24.98% | 11.45% | -264% | -219.5% | -46.54%
Kikeh FPSO | 2 | 5 | 1 | 1 | 3 | 5513 | 3 | 939 | 0.8 | 2 | 143500 | 3 | 2 | 4 | 1350 | 1 | 0.83624 | 4 | -0.015974 | 20% | 28.07% | 24.21% | 11.62% | -40.33% | -21.04% | 41.91%
Song Doc Pride MV 19 | 2 | 1 | 2 | 1 | 1 | 6339 | 3 | 417 | 0.25 | 2 | 30000 | 1 | 1 | 4 | 55 | 2 | 1 | 1 | 0.35012 | 4.087% | 27.97% | 28.11% | 53.01% | -584.4% | -587.8% | -1197%
Thai Binh Vn | 2 | 1 | 2 | 2 | 1 | 4446 | 3 | 611 | 0.714 | 1 | 68333.3333 | 2 | 1 | 4 | 48 | 2 | 0.95122 | 3 | 0.037643 | 4.4% | 28.03% | 27.16% | 52.3% | -537% | -517.2% | -1089%
Hai Yang Shi You 117 | 8 | 4 | 2 | 2 | 1 | 5524 | 3 | 897 | 1.8 | 1 | 190000 | 4 | 1 | 4 | 27 | 1 | 1 | 3 | 0.72798 | 38.89% | 28.27% | 28.08% | 27.67% | 27.29% | 27.79% | 28.84%
Hai Yang Shi You 116 | 8 | 4 | 2 | 2 | 1 | 5804 | 3 | 723 | 1.2 | 1 | 106000 | 3 | 2 | 4 | 125 | 1 | 1 | 1 | 0.3195 | 98% | 28.75% | 30.49% | 48.91% | 70.66% | 68.89% | 50.1%
Unity | 1 | 4 | 3 | 2 | 1 | 4018 | 3 | 545 | 1 | 1 | 125000 | 3 | 2 | 6 | 65 | 3 | 1 | 2 | 0.70092 | 40% | 28.68% | 28.56% | 23.31% | 28.3% | 28.61% | 41.74%
Yoho | 1 | 3 | 3 | 2 | 1 | 4196 | 3 | 505 | 1.2 | 2 | 90000 | 2 | 2 | 6 | 56 | 1 | 1 | 1 | 0.20792 | 8.333% | 28.56% | 30.59% | 41.15% | -242.8% | -267.1% | -393.8%
Yoho | 1 | 3 | 3 | 2 | 1 | 4623 | 3 | 761 | 1.2 | 2 | 116666.6667 | 3 | 2 | 6 | 56 | 3 | 0.85714 | 2 | 0.6636 | 8.333% | 28.24% | 24.12% | 9.947% | -238.9% | -189.4% | -19.37%
Randgrid | 5 | 2 | 1 | 1 | 0 | 8521 | 3 | 1386 | 3.7 | 2 | 0 | 1 | 1 | 6 | 116 | 2 | 1 | 3 | 0.097403 | 0% | 28.99% | 30.8% | 50.94% | -28.99% | -30.8% | -50.94%
Hanne Knutsen | 5 | 2 | 3 | 1 | 3 | 8124 | 3 | 1691 | 2.8649 | 2 | 100000 | 3 | 3 | 6 | 115 | 1 | 1 | 2 | 0.80958 | 85% | 28.18% | 26.43% | 18.72% | 66.85% | 68.91% | 77.97%
Ailsa FSO | 5 | 2 | 3 | 2 | 1 | 9389 | 3 | 1364 | 4.7 | 1 | 108333.3333 | 3 | 2 | 6 | 90 | 5 | 0.23077 | 5 | 0 | 0% | 28.74% | 29.06% | 43.79% | -28.74% | -29.06% | -43.79%
Gagak Rimang | 2 | 5 | 3 | 2 | 1 | 7891 | 3 | 1110 | 1.2 | 2 | 165000 | 4 | 2 | 6 | 33 | 1 | 1 | 2 | 0.42973 | 116.7% | 28.12% | 27.07% | 32.79% | 75.9% | 76.8% | 71.89%
Rang Dong MV17 | 2 | 1 | 2 | 1 | 3 | 6038 | 3 | 763 | 0.5 | 1 | 60000 | 2 | 1 | 6 | 60 | 2 | 1 | 1 | 0.10747 | 4.087% | 28.02% | 25.35% | 27.31% | -585.6% | -520.4% | -568.1%
Ichthys Explorer | 4 | 4 | 1 | 2 | 1 | 8046 | 3 | 1810 | 3 | 1 | 361166.6667 | 6 | 4 | 7 | 250 | 2 | 0.23535 | 5 | 0.35635 | 32.35% | 27.88% | 28.27% | 17.96% | 13.84% | 12.62% | 44.49%
P 51 | 7 | 5 | 2 | 2 | 1 | 5201 | 3 | 1418 | 0.83 | 1 | 215000 | 5 | 2 | 7 | 1250 | 5 | 0.83721 | 1 | 0.24401 | 25% | 27.84% | 26.2% | 25.53% | -11.35% | -4.782% | -2.104%
P 56 | 7 | 5 | 2 | 2 | 1 | 6478 | 3 | 1114 | 1.4 | 1 | 135000 | 3 | 1 | 7 | 1670 | 5 | 0.74074 | 1 | 0.27379 | 7.143% | 28.27% | 24.23% | 10.92% | -295.8% | -239.3% | -52.85%
P 52 | 7 | 5 | 2 | 1 | 3 | 5060 | 3 | 1237 | 0.906 | 1 | 235000 | 5 | 2 | 7 | 1850 | 3 | 0.76596 | 1 | 0.19644 | 43.49% | 27.73% | 26.36% | 50.68% | 36.23% | 39.4% | -16.54%
Atlantis | 6 | 3 | 3 | 2 | 1 | 4533 | 3 | 1492 | 2.5 | 1 | 230000 | 5 | 3 | 7 | 2145 | 3 | 0.86957 | 1 | 0.60389 | 135% | 27.62% | 23.19% | 5.007% | 79.54% | 82.82% | 96.29%
Delta House (Opti-Ex II) | 6 | 1 | 1 | 2 | 1 | 8158 | 3 | 1093 | 2 | 1 | 140000 | 3 | 2 | 7 | 1372 | 5 | 0.71429 | 2 | -0.012809 | 0% | 28.01% | 30.58% | 55.6% | -28.01% | -30.58% | -55.6%
Blind Faith | 6 | 2 | 3 | 2 | 1 | 5802 | 3 | 846 | 1.151 | 1 | 52500 | 2 | 4 | 7 | 2130 | 1 | 0.85714 | 5 | 0.28605 | 95% | 27.63% | 23.58% | 9.528% | 70.92% | 75.18% | 89.97%
Thunder Hawk | 6 | 1 | 1 | 1 | 3 | 6086 | 3 | 958 | 0.8 | 1 | 56666.6667 | 2 | 1 | 7 | 1847 | 4 | 0.79412 | 5 | 0.087683 | 0% | 27.95% | 24.72% | 8.489% | -27.95% | -24.72% | -8.489%
Thunder Horse | 6 | 3 | 3 | 2 | 1 | 4624 | 3 | 1098 | 5 | 1 | 283333.3333 | 6 | 5 | 7 | 1830 | 1 | 0.88235 | 4 | 0.92623 | 268% | 28.56% | 28.77% | 54.7% | 89.34% | 89.27% | 79.59%
Jack / St. Malo Semi | 6 | 1 | 3 | 2 | 1 | 7270 | 3 | 1844 | 7.5 | 1 | 177166.6667 | 4 | 1 | 7 | 2134 | 4 | 0.95955 | 5 | -0.005423 | 0% | 28.72% | 32.12% | 56.55% | -28.72% | -32.12% | -56.55%
Asgard B | 5 | 4 | 1 | 2 | 1 | 2356 | 4 | 1570 | 1.3 | 1 | 351666.6667 | 6 | 1 | 7 | 300 | 5 | 0.38389 | 4 | 0 | 0% | 28.09% | 25.89% | 21.24% | -28.09% | -25.89% | -21.24%
Gjoa | 5 | 2 | 1 | 2 | 1 | 6025 | 2 | 1461 | 4.4361 | 1 | 108333.3333 | 3 | 4 | 7 | 380 | 1 | 0.46154 | 3 | 0.08898 | 33% | 28.25% | 31.29% | 48.63% | 14.39% | 5.192% | -47.37%
Kristin | 5 | 4 | 1 | 2 | 1 | 4368 | 3 | 1384 | 1.9 | 1 | 128000 | 3 | 5 | 7 | 370 | 1 | 0.97656 | 2 | 0.023844 | 73.68% | 28.58% | 32.52% | 56.35% | 61.21% | 55.87% | 23.52%
Snorre B | 5 | 4 | 1 | 2 | 1 | 3256 | 3 | 943 | 1.2821 | 1 | 115000 | 3 | 1 | 7 | 310 | 4 | 1 | 2 | -0.064687 | 17% | 28.08% | 26.54% | 10.27% | -65.16% | -56.11% | 39.62%
Troll B | 5 | 3 | 1 | 2 | 1 | 379 | 3 | 1263 | 2.9 | 1 | 317000 | 6 | 5 | 7 | 320 | 2 | 0.85174 | 3 | 0.35234 | 14% | 28.38% | 29.15% | 56.86% | -102.7% | -108.2% | -306.2%
Visund | 5 | 5 | 1 | 2 | 1 | 2251 | 4 | 851 | 0.7 | 1 | 171333.3333 | 4 | 5 | 7 | 335 | 1 | 0.65953 | 2 | 0.3396 | 45% | 28.05% | 27.86% | 48.26% | 37.66% | 38.09% | -7.233%
Gumusut Semi | 2 | 5 | 3 | 1 | 3 | 6588 | 3 | 1233 | 1.6 | 1 | 200000 | 5 | 2 | 7 | 1220 | 2 | 0.75 | 3 | 0.99919 | 25% | 27.76% | 26.61% | 50.35% | -11.02% | -6.424% | -101.4%
Front Runner Spar | 6 | 2 | 1 | 2 | 1 | 4459 | 4 | 728 | 0.2 | 1 | 78333.3333 | 2 | 3 | 3 | 1015 | 1 | 0.76596 | 1 | 0.36676 | 7.5% | 28.23% | 23.81% | 11.13% | -276.5% | -217.5% | -48.37%
Tahiti Spar | 6 | 2 | 3 | 2 | 1 | 5597 | 3 | 1159 | 3.5 | 1 | 136666.6667 | 3 | 3 | 3 | 1280 | 2 | 0.91463 | 2 | 0.26747 | 180% | 28.19% | 24.49% | 19.58% | 84.34% | 86.4% | 89.12%
Mad Dog | 6 | 1 | 3 | 2 | 1 | 4070 | 3 | 1397 | 1.82 | 1 | 66666.6667 | 2 | 2 | 3 | 1370 | 1 | 0.9 | 4 | 0.022906 | 10% | 28.39% | 29.15% | 56.86% | -183.9% | -191.5% | -468.6%
Heidelberg Spar | 6 | 1 | 1 | 2 | 1 | 8018 | 3 | 1649 | 6.745 | 1 | 93333.3333 | 2 | 4 | 3 | 1620 | 5 | 0.85714 | 5 | -0.095816 | 0.8154% | 27.8% | 25.64% | 22.51% | -3309% | -3044% | -2660%
Lucius Spar | 6 | 1 | 1 | 2 | 1 | 8002 | 3 | 1007 | 7.736 | 1 | 155000 | 4 | 4 | 3 | 2165 | 4 | 0.51613 | 5 | 0.14002 | 0.8273% | 27.94% | 27.06% | 21.65% | -3277% | -3171% | -2516%
Medusa Spar | 6 | 2 | 1 | 2 | 1 | 4077 | 4 | 579 | 0.2 | 1 | 58333.3333 | 2 | 3 | 3 | 675 | 1 | 0.68571 | 1 | 0.74266 | 36.5% | 28.66% | 28.98% | 46.07% | 21.48% | 20.6% | -26.23%
Gulfstar 1 | 6 | 1 | 3 | 1 | 3 | 7813 | 3 | 1132 | 2.3 | 1 | 109166.6667 | 3 | 2 | 3 | 1310 | 2 | 0.73282 | 3 | 0.12191 | 47.83% | 28.09% | 26.04% | 16.43% | 41.27% | 45.55% | 65.64%
Devil's Tower Spar | 6 | 3 | 1 | 1 | 3 | 4189 | 4 | 739 | 0.2 | 1 | 66666.6667 | 2 | 2 | 3 | 1710 | 2 | 0.9 | 1 | 0.41949 | 6% | 28.02% | 24.07% | 4.599% | -367.1% | -301.1% | 23.35%
Kikeh Spar | 2 | 5 | 1 | 2 | 1 | 5513 | 3 | 939 | 0.5 | 1 | 142500 | 3 | 4 | 3 | 1330 | 1 | 0.84211 | 4 | -0.015974 | 28.57% | 28.21% | 23.04% | 3.778% | 1.252% | 19.36% | 86.78%
Kizomba A Wellhead TLP | 1 | 4 | 3 | 2 | 1 | 4253 | 3 | 1073 | 0.65 | 1 | 250000 | 6 | 1 | 1 | 1175 | 3 | 1 | 2 | 0.0055918 | 13.33% | 28.24% | 23.08% | 3.778% | -111.8% | -73.08% | 71.67%
Kizomba B Wellhead TLP | 1 | 3 | 3 | 2 | 1 | 4756 | 3 | 1071 | 0.6 | 1 | 250000 | 6 | 1 | 1 | 1250 | 5 | 1 | 2 | -0.14006 | 13.33% | 28.44% | 30.4% | 54.09% | -113.3% | -128% | -305.6%
Okume TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.1425 | 1 | 30000 | 1 | 1 | 1 | 500 | 4 | 0.83333 | 4 | 0.04 | 0% | 27.73% | 27.14% | 45.17% | -27.73% | -27.14% | -45.17%
Oveng TLP | 1 | 2 | 1 | 2 | 1 | 5414 | 3 | 550 | 0.1425 | 1 | 30000 | 1 | 1 | 1 | 280 | 4 | 0.83333 | 4 | 0.04 | 0% | 27.86% | 26.25% | 41.47% | -27.86% | -26.25% | -41.47%
P 61 Wellhead TLP | 7 | 5 | 2 | 2 | 1 | 7213 | 3 | 1475 | 1.07 | 1 | 145833.3333 | 3 | 3 | 1 | 1180 | 1 | 0.96 | 2 | 0.35051 | 0% | 27.63% | 24.43% | 10.14% | -27.63% | -24.43% | -10.14%
Auger TLP | 6 | 2 | 3 | 2 | 1 | 287 | 3 | 1233 | 0.86364 | 1 | 65000 | 2 | 4 | 1 | 870 | 2 | 0.61538 | 4 | 0.044607 | 38.95% | 28.07% | 23.02% | 6.632% | 27.93% | 40.89% | 82.97%
Magnolia TLP | 6 | 1 | 3 | 2 | 1 | 4392 | 3 | 1040 | 0.6 | 1 | 75000 | 2 | 4 | 1 | 1432 | 2 | 0.66667 | 5 | 0.038462 | 0% | 28.11% | 25.76% | 34.86% | -28.11% | -25.76% | -34.86%
Brutus TLP | 6 | 1 | 3 | 2 | 1 | 3570 | 3 | 674 | 0.76 | 1 | 155000 | 4 | 2 | 1 | 910 | 4 | 0.83871 | 4 | 0.038576 | 7.895% | 28.03% | 25.44% | 31.35% | -255.1% | -222.2% | -297.1%
Stampede TLP | 6 | 1 | 1 | 2 | 1 | 8523 | 3 | 1982 | 6.2 | 1 | 86666.6667 | 2 | 1 | 1 | 1160 | 4 | 0.92308 | 5 | -0.1221 | -12.9% | 27.5% | 24.71% | 10.14% | -27.5% | -24.71% | -10.14%
Neptune TLP | 6 | 2 | 1 | 2 | 1 | 5670 | 3 | 887 | 0.85 | 1 | 58333.3333 | 2 | 2 | 1 | 1300 | 2 | 0.85714 | 3 | 0.2345 | 47.88% | 27.83% | 23.23% | 4.719% | 41.87% | 51.48% | 90.14%
Shenzi TLP | 6 | 2 | 1 | 2 | 1 | 6001 | 3 | 1119 | 4.41 | 1 | 116666.6667 | 3 | 2 | 1 | 1333 | 2 | 0.85714 | 5 | -0.088472 | 0% | 27.63% | 24.29% | 7.65% | -27.63% | -24.29% | -7.65%
Mars TLP | 6 | 1 | 3 | 2 | 1 | 1381 | 3 | 1098 | 1.2 | 1 | 230833.3333 | 5 | 2 | 1 | 896 | 4 | 0.86643 | 4 | -0.090164 | -5.417% | 27.55% | 23.64% | 7.65% | -27.55% | -23.64% | -7.65%
Olympus TLP | 6 | 1 | 3 | 2 | 1 | 7729 | 3 | 1202 | 3 | 1 | 116666.6667 | 3 | 2 | 1 | 945 | 5 | 0.85714 | 5 | -0.12562 | 0% | 28.32% | 29.36% | 50.65% | -28.32% | -29.36% | -50.65%
Ursa TLP | 6 | 1 | 3 | 2 | 1 | 2398 | 3 | 1040 | 1.45 | 1 | 216666.6667 | 5 | 3 | 1 | 1160 | 5 | 0.69231 | 4 | -0.081731 | 4.345% | 27.81% | 26.23% | 24.24% | -540.1% | -503.7% | -457.9%
Ram Powell TLP | 6 | 1 | 3 | 2 | 1 | 1885 | 3 | 915 | 1 | 1 | 93333.3333 | 2 | 3 | 1 | 990 | 5 | 0.64286 | 4 | 0.015301 | 0% | 28.34% | 25.12% | 19.38% | -28.34% | -25.12% | -19.38%
Big Foot | 6 | 3 | 3 | 2 | 1 | 7571 | 3 | 1529 | 4 | 1 | 79166.6667 | 2 | 5 | 1 | 1580 | 1 | 0.94737 | 4 | 0.94899 | 0.375
Heidrun TLP | 5 | 1 | 1 | 2 | 1 | 504 | 3 | 1548 | 3.9 | 1 | 283333.3333 | 6 | 2 | 1 | 350 | 2 | 0.88235 | 5 | 0.039406 | 0.076923
Malikai TLP | 2 | 5 | 3 | 2 | 1 | 8439 | 3 | 1030 | 1.2825 | 1 | 68333.3333 | 2 | 2 | 1 | 470 | 3 | 0.87805 | 5 | 0.36796 | 0.077973

## Cost_T2
Unit Name | Region | Local Content Requirment (H,M,A,L, N) | Company (NOC, IOC, OC) | Lease/ Own | Contract2 | Contracting Date | Contract (EPC, CL, PS, TK) | Planned_Duration | Planned_Cost | Hull Type | BOE/day | Topsides (VL, L, M, S, VS) | Technology Novelt (H,M,A,L,N) | Type Unit | Water_Depth (meters) | Lessons Learned | Oil/Gas_Prod | FEED_Detail | Schedule_Overrun | Cost_Overrun
Bohai Ming Zhu | SEA CH | 5 | NOC | 2 | 1 | 4350 | EPC | 259 | 0.4 | NEW | 40000 | 1 | 2 | FPSO | 30 | 1 | 1 | 1 | 0.47104 | 0.25
Petrojarl Varg | NE | 1 | OC | 1 | 1 | 2240 | EPC | 816 | 0.46 | NEW | 65833.3333 | 2 | 2 | FPSO | 84 | 1 | 0.86582 | 2 | 0.28676 | 0.24
Stybarrow Venture MV16 | AUST/NZ | 3 | IOC | 1 | 3 | 5922 | EPC | 702 | 0.59843 | NEW | 87500 | 2 | 3 | FPSO | 825 | 2 | 0.91429 | 4 | -0.14387 | 0.27
Alima FPU | AFRICA | 2 | IOC | 2 | 1 | 5720 | EPC | 994 | 1.133 | NEW | 100000 | 3 | 1 | BARGE | 600 | 3 | 0.9 | 4 | -0.022133 | 0.35
Jangkrik | SEA | 4 | OC | 2 | 1 | 8824 | EPC | 1052 | 2.6765 | NEW | 79400 | 2 | 2 | BARGE | 120 | 2 | 0.055416 | 3 | 0.11407 | 0.17
Prelude | AUST/NZ | 3 | IOC | 2 | 1 | 7814 | EPC | 2229 | 11.16 | NEW | 148333.3333 | 6 | 5 | FLNG | 250 | 1 | 0.23596 | 5 | 0.24316 | 0.34409
CLOV FPSO | AFRICA | 3 | IOC | 2 | 1 | 7534 | EPC | 1383 | 7 | NEW | 198333.3333 | 4 | 2 | FPSO | 1290 | 4 | 0.80672 | 5 | 0.0079537 | 0.14286
Dalia | AFRICA | 4 | IOC | 2 | 1 | 4872 | EPC | 1306 | 3.4 | NEW | 287000 | 6 | 3 | FPSO | 1360 | 5 | 0.83624 | 2 | 0.01072 | 0.17647
Girassol | AFRICA | 4 | IOC | 2 | 1 | 3103 | EPC | 823 | 2.5 | NEW | 246666.6667 | 5 | 3 | FPSO | 1350 | 1 | 0.81081 | 1 | 0.52126 | 0.12
Kizomba B | AFRICA | 3 | IOC | 2 | 1 | 4756 | EPC | 1071 | 0.76 | NEW | 316666.6667 | 6 | 1 | FPSO | 1250 | 5 | 0.78947 | 2 | -0.14006 | 0.13333
Mondo | AFRICA | 4 | IOC | 1 | 1 | 5866 | EPC | 797 | 0.75 | CONV | 115833.3333 | 3 | 1 | FPSO | 728 | 3 | 0.86331 | 3 | -0.10163 | 0
Saxi-Batuque | AFRICA | 4 | IOC | 1 | 3 | 5866 | EPC | 797 | 0.75 | CONV | 130000 | 3 | 1 | FPSO | 720 | 3 | 0.80769 | 3 | -0.084065 | 0
Greater Plutonio | AFRICA | 3 | IOC | 2 | 1 | 5144 | EPC | 1124 | 1.73 | NEW | 305000 | 6 | 3 | FPSO | 1350 | 2 | 0.81967 | 4 | 0.19039 | 0.85
PSVM FPSO | AFRICA | 5 | IOC | 2 | 1 | 6755 | EPC | 1249 | 10 | CONV | 197833.3333 | 4 | 5 | FPSO | 2000 | 2 | 0.7936 | 1 | 0.29704 | 0.4
Baobab Ivoirien MV10 | AFRICA | 1 | OC | 1 | 3 | 4949 | EPC | 711 | 1.5 | CONV | 82500 | 2 | 1 | FPSO | 970 | 3 | 0.84848 | 2 | 0.067511 | 0
Prof. John Evans Atta Mills | AFRICA | 4 | IOC | 1 | 3 | 8617 | EPC | 1092 | 4.5 | CONV | 108333.3333 | 3 | 1 | FPSO | 1425 | 2 | 0.73846 | 5 | 0.015568 | 0.088889
Agbami | AFRICA | 2 | IOC | 2 | 2 | 5539 | EPC | 1126 | 4.1538 | NEW | 325000 | 6 | 2 | FPSO | 1433 | 2 | 0.76923 | 2 | 0.11368 | 0.3
Akpo | AFRICA | 4 | IOC | 2 | 1 | 5606 | TK | 1303 | 2.345 | NEW | 273333.3333 | 6 | 4 | FPSO | 1325 | 1 | 0.67683 | 2 | 0.072141 | 1.55
Bonga | AFRICA | 4 | IOC | 2 | 1 | 4049 | EPC | 1033 | 2.4 | NEW | 253333.3333 | 6 | 3 | FPSO | 1250 | 1 | 0.88816 | 3 | 0.70765 | 0.5
Egina FPSO | AFRICA | 5 | IOC | 2 | 1 | 8540 | EPC | 1595 | 15 | NEW | 260000 | 6 | 2 | FPSO | 1600 | 3 | 0.76923 | 2 | 0.28715 | -0.033333
Erha | AFRICA | 4 | IOC | 2 | 1 | 4671 | EPC | 1081 | 2.6 | NEW | 266666.6667 | 6 | 2 | FPSO | 1180 | 2 | 0.7875 | 2 | 0.19334 | 0.57
Kizomba A | AFRICA | 3 | IOC | 2 | 1 | 4253 | EPC | 1073 | 0.77 | NEW | 316666.6667 | 6 | 2 | FPSO | 1250 | 3 | 0.78947 | 2 | 0.0055918 | 0.13333
Ichthys Venturer | AUST/NZ | 4 | IOC | 2 | 1 | 8102 | EPC | 1743 | 2 | NEW | 85000 | 2 | 5 | FPSO | 250 | 2 | 1 | 5 | 0.37636 | 0.32353
Pyrenees Venture | AUST/NZ | 3 | IOC | 2 | 2 | 6379 | EPC | 1014 | 1.66 | CONV | 106000 | 3 | 4 | FPSO | 200 | 4 | 0.90566 | 5 | 0.0019724 | 0.012028
Ngujima Yin | AUST/NZ | 3 | IOC | 2 | 1 | 5993 | EPC | 716 | 0.72 | CONV | 136666.6667 | 3 | 2 | FPSO | 340 | 2 | 0.87805 | 3 | 0.14665 | 0.33333
P 50 | BRAZ | 4 | NOC | 2 | 1 | 4557 | CL | 844 | 0.496 | CONV | 215000 | 5 | 4 | FPSO | 1240 | 1 | 0.83721 | 1 | 0.66351 | 0.41129
P 43 | BRAZ | 5 | NOC | 2 | 1 | 4199 | TK | 883 | 1.3 | CONV | 185000 | 4 | 3 | FPSO | 800 | 1 | 0.81081 | 1 | 0.43828 | 0.38462
P 48 | BRAZ | 5 | NOC | 2 | 1 | 4199 | TK | 1066 | 1.3 | CONV | 185000 | 4 | 1 | FPSO | 1040 | 2 | 0.81081 | 1 | 0.25516 | 0.38462
Frade | BRAZ | 3 | IOC | 2 | 1 | 6014 | EPC | 909 | 2 | CONV | 117666.6667 | 3 | 2 | FPSO | 1080 | 1 | 0.84986 | 4 | 0.20902 | 1.35
Cidade de Itaguai MV26 | BRAZ | 4 | NOC | 1 | 3 | 8352 | EPC | 838 | 1.17 | CONV | 196666.6667 | 4 | 1 | FPSO | 2240 | 3 | 0.76271 | 1 | 0.18138 | 0
P 57 | BRAZ | 5 | NOC | 1 | 2 | 6622 | EPC | 1041 | 1.195 | CONV | 191833.3333 | 4 | 1 | FPSO | 1300 | 4 | 0.93831 | 1 | -0.045149 | 0.0041841
Pioneiro de Libra | BRAZ | 5 | NOC | 1 | 3 | 8984 | PS | 831 | 1 | CONV | 73333.3333 | 2 | 1 | FPSO | 2200 | 1 | 0.68182 | 1 | 0.45728 | 0.27553
P 63 | BRAZ | 5 | NOC | 2 | 1 | 7213 | EPC | 1383 | 1.3 | CONV | 145833.3333 | 3 | 1 | FPSO | 1170 | 2 | 0.96 | 2 | 0.086768 | 0.25385
Espirito Santo | BRAZ | 5 | IOC | 1 | 3 | 6153 | EPC | 787 | 1.5086 | CONV | 105000 | 3 | 5 | FPSO | 1780 | 1 | 0.95238 | 2 | 0.24778 | 1.32
P 54 | BRAZ | 5 | NOC | 2 | 1 | 5272 | EPC | 1034 | 0.629 | CONV | 215000 | 5 | 3 | FPSO | 1315 | 3 | 0.83721 | 1 | 0.24468 | 0.97138
Cidade de Campos dos Goytacazes MV29 | BRAZ | 4 | NOC | 1 | 3 | 9101 | EPC | 1018 | 1.263 | CONV | 179500 | 4 | 2 | FPSO | 765 | 4 | 0.83565 | 1 | 0.27898 | 0.0055424
Terra Nova | CAN | 2 | OC | 2 | 1 | 2800 | EPC | 1157 | 1.3 | NEW | 175000 | 4 | 5 | FPSO | 90 | 1 | 0.85714 | 2 | 0.39412 | 0.30769
Sea Rose | CAN | 3 | OC | 2 | 1 | 4476 | EPC | 1229 | 0.49 | NEW | 125000 | 3 | 5 | FPSO | 120 | 1 | 0.8 | 4 | 0.072417 | 0.2
Turritella | GOM | 1 | OC | 2 | 1 | 8528 | EPC | 1149 | 1 | Conv | 62500 | 2 | 4 | FPSO | 2900 | 2 | 0.96 | 5 | 0.11227 | 0.311
Asgard A | NE | 3 | OC | 2 | 1 | 2356 | TK | 870 | 5.2941 | NEW | 300000 | 6 | 4 | FPSO | 300 | 1 | 0.66667 | 3 | 0.20805 | 0.36
Balder | NE | 3 | IOC | 2 | 1 | 1826 | TK | 592 | 0.35 | NEW | 90500 | 2 | 5 | FPSO | 125 | 1 | 0.91713 | 1 | 1.9291 | 0.62
Goliat FPSO | NE | 2 | OC | 2 | 1 | 7218 | EPC | 1364 | 3.9 | NEW | 122500 | 3 | 5 | FPSO | 400 | 1 | 0.81633 | 3 | 0.72361 | 0.94872
Petrojarl Knarr | NE | 2 | OC | 1 | 3 | 7850 | EPC | 732 | 1.6119 | NEW | 70833.3333 | 2 | 2 | FPSO | 410 | 2 | 0.88941 | 4 | 0.85656 | 0.36975
Norne | NE | 3 | OC | 2 | 1 | 1551 | EPC | 1334 | 4.7 | NEW | 261666.6667 | 6 | 4 | FPSO | 380 | 3 | 0.84076 | 2 | -0.12519 | 0.6
Skarv | NE | 2 | IOC | 2 | 1 | 6240 | EPC | 1245 | 5 | NEW | 167500 | 4 | 4 | FPSO | 370 | 1 | 0.47761 | 3 | 0.73494 | 0.7
Armada Kraken | NE | 1 | OC | 1 | 0 | 8719 | EPC | 1136 | 2.5 | CONV | 83333.3333 | 2 | 1 | FPSO | 116 | 1 | 0.96 | 4 | 0.16285 | 0
Glen Lyon | NE | 3 | IOC | 2 | 1 | 7729 | EPC | 1949 | 4.78 | NEW | 166666.6667 | 4 | 2 | FPSO | 424 | 1 | 0.78 | 4 | 0.16675 | 0.19247
Western Isles FPSO | NE | 1 | OC | 2 | 1 | 8391 | EPC | 952 | 1.6 | NEW | 40000 | 1 | 3 | FPSO | 165 | 2 | 1 | 3 | 0.8792 | 0.25
Belanak Natuna | SEA | 4 | IOC | 2 | 1 | 4250 | TK | 1137 | 1.6 | NEW | 158333.3333 | 4 | 4 | FPSO | 100 | 2 | 0.63158 | 4 | 0.058927 | 0.078167
Kikeh FPSO | SEA | 5 | OC | 1 | 3 | 5513 | EPC | 939 | 0.8 | CONV | 143500 | 3 | 2 | FPSO | 1350 | 1 | 0.83624 | 4 | -0.015974 | 0.2
Song Doc Pride MV 19 | SEA | 1 | NOC | 1 | 1 | 6339 | EPC | 417 | 0.25 | CONV | 30000 | 1 | 1 | FPSO | 55 | 2 | 1 | 1 | 0.35012 | 0.04087
Thai Binh Vn | SEA | 1 | NOC | 2 | 1 | 4446 | EPC | 611 | 0.714 | NEW | 68333.3333 | 2 | 1 | FPSO | 48 | 2 | 0.95122 | 3 | 0.037643 | 0.044
Hai Yang Shi You 117 | SEA CH | 4 | NOC | 2 | 1 | 5524 | EPC | 897 | 1.8 | NEW | 190000 | 4 | 1 | FPSO | 27 | 1 | 1 | 3 | 0.72798 | 0.38889
Hai Yang Shi You 116 | SEA CH | 4 | NOC | 2 | 1 | 5804 | EPC | 723 | 1.2 | NEW | 106000 | 3 | 2 | FPSO | 125 | 1 | 1 | 1 | 0.3195 | 0.98
Unity | AFRICA | 4 | IOC | 2 | 1 | 4018 | EPC | 545 | 1 | NEW | 125000 | 3 | 2 | FSO | 65 | 3 | 1 | 2 | 0.70092 | 0.4
Yoho | AFRICA | 3 | IOC | 2 | 1 | 4196 | EPC | 505 | 1.2 | CONV | 90000 | 2 | 2 | FSO | 56 | 1 | 1 | 1 | 0.20792 | 0.083333
Yoho | AFRICA | 3 | IOC | 2 | 1 | 4623 | EPC | 761 | 1.2 | CONV | 116666.6667 | 3 | 2 | FSO | 56 | 3 | 0.85714 | 2 | 0.6636 | 0.083333
Randgrid | NE | 2 | OC | 1 | 0 | 8521 | EPC | 1386 | 3.7 | CONV | 0 | 1 | 1 | FSO | 116 | 2 | 1 | 3 | 0.097403 | 0
Hanne Knutsen | NE | 2 | IOC | 1 | 3 | 8124 | EPC | 1691 | 2.8649 | CONV | 100000 | 3 | 3 | FSO | 115 | 1 | 1 | 2 | 0.80958 | 0.85
Ailsa FSO | NE | 2 | IOC | 2 | 1 | 9389 | EPC | 1364 | 4.7 | NEW | 108333.3333 | 3 | 2 | FSO | 90 | 5 | 0.23077 | 5 | 0 | 0
Gagak Rimang | SEA | 5 | IOC | 2 | 1 | 7891 | EPC | 1110 | 1.2 | CONV | 165000 | 4 | 2 | FSO | 33 | 1 | 1 | 2 | 0.42973 | 1.1667
Rang Dong MV17 | SEA | 1 | NOC | 1 | 3 | 6038 | EPC | 763 | 0.5 | NEW | 60000 | 2 | 1 | FSO | 60 | 2 | 1 | 1 | 0.10747 | 0.04087
Ichthys Explorer | AUST/NZ | 4 | OC | 2 | 1 | 8046 | EPC | 1810 | 3 | NEW | 361166.6667 | 6 | 4 | SEMI | 250 | 2 | 0.23535 | 5 | 0.35635 | 0.32353
P 51 | BRAZ | 5 | NOC | 2 | 1 | 5201 | EPC | 1418 | 0.83 | NEW | 215000 | 5 | 2 | SEMI | 1250 | 5 | 0.83721 | 1 | 0.24401 | 0.25
P 56 | BRAZ | 5 | NOC | 2 | 1 | 6478 | EPC | 1114 | 1.4 | NEW | 135000 | 3 | 1 | SEMI | 1670 | 5 | 0.74074 | 1 | 0.27379 | 0.071429
P 52 | BRAZ | 5 | NOC | 1 | 3 | 5060 | EPC | 1237 | 0.906 | NEW | 235000 | 5 | 2 | SEMI | 1850 | 3 | 0.76596 | 1 | 0.19644 | 0.43488
Atlantis | GOM | 3 | IOC | 2 | 1 | 4533 | EPC | 1492 | 2.5 | NEW | 230000 | 5 | 3 | SEMI | 2145 | 3 | 0.86957 | 1 | 0.60389 | 1.35
Delta House (Opti-Ex II) | GOM | 1 | OC | 2 | 1 | 8158 | EPC | 1093 | 2 | NEW | 140000 | 3 | 2 | SEMI | 1372 | 5 | 0.71429 | 2 | -0.012809 | 0
Blind Faith | GOM | 2 | IOC | 2 | 1 | 5802 | EPC | 846 | 1.151 | NEW | 52500 | 2 | 4 | SEMI | 2130 | 1 | 0.85714 | 5 | 0.28605 | 0.95
Thunder Hawk | GOM | 1 | OC | 1 | 3 | 6086 | EPC | 958 | 0.8 | NEW | 56666.6667 | 2 | 1 | SEMI | 1847 | 4 | 0.79412 | 5 | 0.087683 | 0
Thunder Horse | GOM | 3 | IOC | 2 | 1 | 4624 | EPC | 1098 | 5 | NEW | 283333.3333 | 6 | 5 | SEMI | 1830 | 1 | 0.88235 | 4 | 0.92623 | 2.68
Jack / St. Malo Semi | GOM | 1 | IOC | 2 | 1 | 7270 | EPC | 1844 | 7.5 | NEW | 177166.6667 | 4 | 1 | SEMI | 2134 | 4 | 0.95955 | 5 | -0.005423 | 0
Asgard B | NE | 4 | OC | 2 | 1 | 2356 | TK | 1570 | 1.3 | New | 351666.6667 | 6 | 1 | SEMI | 300 | 5 | 0.38389 | 4 | 0 | 0
Gjoa | NE | 2 | OC | 2 | 1 | 6025 | CL | 1461 | 4.4361 | NEW | 108333.3333 | 3 | 4 | SEMI | 380 | 1 | 0.46154 | 3 | 0.08898 | 0.33
Kristin | NE | 4 | OC | 2 | 1 | 4368 | EPC | 1384 | 1.9 | New | 128000 | 3 | 5 | SEMI | 370 | 1 | 0.97656 | 2 | 0.023844 | 0.73684
Snorre B | NE | 4 | OC | 2 | 1 | 3256 | EPC | 943 | 1.2821 | NEW | 115000 | 3 | 1 | SEMI | 310 | 4 | 1 | 2 | -0.064687 | 0.17
Troll B | NE | 3 | OC | 2 | 1 | 379 | EPC | 1263 | 2.9 | NEW | 317000 | 6 | 5 | SEMI | 320 | 2 | 0.85174 | 3 | 0.35234 | 0.14
Visund | NE | 5 | OC | 2 | 1 | 2251 | TK | 851 | 0.7 | NEW | 171333.3333 | 4 | 5 | SEMI | 335 | 1 | 0.65953 | 2 | 0.3396 | 0.45
Gumusut Semi | SEA | 5 | IOC | 1 | 3 | 6588 | EPC | 1233 | 1.6 | NEW | 200000 | 5 | 2 | SEMI | 1220 | 2 | 0.75 | 3 | 0.99919 | 0.25
Front Runner Spar | GOM | 2 | OC | 2 | 1 | 4459 | TK | 728 | 0.2 | NEW | 78333.3333 | 2 | 3 | SPAR | 1015 | 1 | 0.76596 | 1 | 0.36676 | 0.075
Tahiti Spar | GOM | 2 | IOC | 2 | 1 | 5597 | EPC | 1159 | 3.5 | NEW | 136666.6667 | 3 | 3 | SPAR | 1280 | 2 | 0.91463 | 2 | 0.26747 | 1.8
Mad Dog | GOM | 1 | IOC | 2 | 1 | 4070 | EPC | 1397 | 1.82 | NEW | 66666.6667 | 2 | 2 | SPAR | 1370 | 1 | 0.9 | 4 | 0.022906 | 0.1
Heidelberg Spar | GOM | 1 | OC | 2 | 1 | 8018 | EPC | 1649 | 6.745 | NEW | 93333.3333 | 2 | 4 | SPAR | 1620 | 5 | 0.85714 | 5 | -0.095816 | 0.0081542
Lucius Spar | GOM | 1 | OC | 2 | 1 | 8002 | EPC | 1007 | 7.736 | NEW | 155000 | 4 | 4 | SPAR | 2165 | 4 | 0.51613 | 5 | 0.14002 | 0.008273
Medusa Spar | GOM | 2 | OC | 2 | 1 | 4077 | TK | 579 | 0.2 | NEW | 58333.3333 | 2 | 3 | SPAR | 675 | 1 | 0.68571 | 1 | 0.74266 | 0.365
Gulfstar 1 | GOM | 1 | IOC | 1 | 3 | 7813 | EPC | 1132 | 2.3 | NEW | 109166.6667 | 3 | 2 | SPAR | 1310 | 2 | 0.73282 | 3 | 0.12191 | 0.47826
Devil's Tower Spar | GOM | 3 | OC | 1 | 3 | 4189 | TK | 739 | 0.2 | NEW | 66666.6667 | 2 | 2 | SPAR | 1710 | 2 | 0.9 | 1 | 0.41949 | 0.06
Kikeh Spar | SEA | 5 | OC | 2 | 1 | 5513 | EPC | 939 | 0.5 | NEW | 142500 | 3 | 4 | SPAR | 1330 | 1 | 0.84211 | 4 | -0.015974 | 0.28571
Kizomba A Wellhead TLP | AFRICA | 4 | IOC | 2 | 1 | 4253 | EPC | 1073 | 0.65 | NEW | 250000 | 6 | 1 | TLP | 1175 | 3 | 1 | 2 | 0.0055918 | 0.13333
Kizomba B Wellhead TLP | AFRICA | 3 | IOC | 2 | 1 | 4756 | EPC | 1071 | 0.6 | NEW | 250000 | 6 | 1 | TLP | 1250 | 5 | 1 | 2 | -0.14006 | 0.13333
Okume TLP | AFRICA | 2 | OC | 2 | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | 1 | 1 | TLP | 500 | 4 | 0.83333 | 4 | 0.04 | 0
Oveng TLP | AFRICA | 2 | OC | 2 | 1 | 5414 | EPC | 550 | 0.1425 | NEW | 30000 | 1 | 1 | TLP | 280 | 4 | 0.83333 | 4 | 0.04 | 0
P 61 Wellhead TLP | BRAZ | 5 | NOC | 2 | 1 | 7213 | EPC | 1475 | 1.07 | NEW | 145833.3333 | 3 | 3 | TLP | 1180 | 1 | 0.96 | 2 | 0.35051 | 0
Auger TLP | GOM | 2 | IOC | 2 | 1 | 287 | EPC | 1233 | 0.86364 | NEW | 65000 | 2 | 4 | TLP | 870 | 2 | 0.61538 | 4 | 0.044607 | 0.38947
Magnolia TLP | GOM | 1 | IOC | 2 | 1 | 4392 | EPC | 1040 | 0.6 | NEW | 75000 | 2 | 4 | TLP | 1432 | 2 | 0.66667 | 5 | 0.038462 | 0
Brutus TLP | GOM | 1 | IOC | 2 | 1 | 3570 | EPC | 674 | 0.76 | NEW | 155000 | 4 | 2 | TLP | 910 | 4 | 0.83871 | 4 | 0.038576 | 0.078947
Stampede TLP | GOM | 1 | OC | 2 | 1 | 8523 | EPC | 1982 | 6.2 | NEW | 86666.6667 | 2 | 1 | TLP | 1160 | 4 | 0.92308 | 5 | -0.1221 | -0.12903
Neptune TLP | GOM | 2 | OC | 2 | 1 | 5670 | EPC | 887 | 0.85 | NEW | 58333.3333 | 2 | 2 | TLP | 1300 | 2 | 0.85714 | 3 | 0.2345 | 0.47882
Shenzi TLP | GOM | 2 | OC | 2 | 1 | 6001 | EPC | 1119 | 4.41 | NEW | 116666.6667 | 3 | 2 | TLP | 1333 | 2 | 0.85714 | 5 | -0.088472 | 0
Mars TLP | GOM | 1 | IOC | 2 | 1 | 1381 | EPC | 1098 | 1.2 | NEW | 230833.3333 | 5 | 2 | TLP | 896 | 4 | 0.86643 | 4 | -0.090164 | -0.054167
Olympus TLP | GOM | 1 | IOC | 2 | 1 | 7729 | EPC | 1202 | 3 | NEW | 116666.6667 | 3 | 2 | TLP | 945 | 5 | 0.85714 | 5 | -0.12562 | 0
Ursa TLP | GOM | 1 | IOC | 2 | 1 | 2398 | EPC | 1040 | 1.45 | NEW | 216666.6667 | 5 | 3 | TLP | 1160 | 5 | 0.69231 | 4 | -0.081731 | 0.043448
Ram Powell TLP | GOM | 1 | IOC | 2 | 1 | 1885 | EPC | 915 | 1 | NEW | 93333.3333 | 2 | 3 | TLP | 990 | 5 | 0.64286 | 4 | 0.015301 | 0
Big Foot | GOM | 3 | IOC | 2 | 1 | 7571 | EPC | 1529 | 4 | NEW | 79166.6667 | 2 | 5 | TLP | 1580 | 1 | 0.94737 | 4 | 0.94899 | 0.375
Heidrun TLP | NE | 1 | OC | 2 | 1 | 504 | EPC | 1548 | 3.9 | NEW | 283333.3333 | 6 | 2 | TLP | 350 | 2 | 0.88235 | 5 | 0.039406 | 0.076923
Malikai TLP | SEA | 5 | IOC | 2 | 1 | 8439 | EPC | 1030 | 1.2825 | NEW | 68333.3333 | 2 | 2 | TLP | 470 | 3 | 0.87805 | 2 | 0.36796 | 0.077973

## Coding
| H | High | 5 |  | H | 5
| M | Medium | 4
| A | Average | 3
| L | Low | 2
| N | Negligible | 1
Schedule | OC | National Oil Company | 1 | Cost | OC | National Oil Company | 1
| IOC | International Oil Company | 2 |  | NOC | International Oil Company | 2
| NOC | Oil Company | 3 |  | IOC | Oil Company | 3
| EPC | Engineering, Procurement, Construction | 3
| TK | Turnkey | 4
| CL | Client as Integrator | 2
| PS | Production Sharing | 1
| BARGE | 1 |  |  | BARGE | 2
| FLNG | 4 |  |  | FLNG | 5
| FPSO | 5 |  |  | FPSO | 4
| FSO | 7 |  |  | FSO | 6
| SEMI | 6 |  |  | SEMI | 7
| SPAR | 3 |  |  | SPAR | 3
| TLP | 2 |  |  | TLP | 1
| FSO (LNG) | 8 |  |  | FSO (LNG) | 8
| MOPU | 9 |  |  | MOPU | 9
Schedule | AFRICA | 1 | Cost | AFRICA | 1
| SEA | 2 |  | SEA | 2
| GOM | 3 |  | CAN | 3
| AUST/NZ | 4 |  | AUST/NZ | 4
| CAN | 5 |  | NE | 5
| BRAZ | 6 |  | GOM | 6
| NE | 7 |  | BRAZ | 7
| SEA CH | 8 |  | SEA CH | 8
| Lease | 1
| Own | 2
H 1 = FOO & FOM – Field Operator Owned FPSO & Field Operator Managed FPSO
Schedule | 1 | H 2 = FOO & CM – Field Operator Owned & Contractor Managed FPSO
| 2 | H 3 = CO & CM – Contractor Owned FPSO & Contractor Managed FPSO
| 3 | H 4 = CO & FOM – Contractor Owned FPSO & Field Operator Managed FPSO
4
| NEW | 1
| CONV | 2
| VS | Very Small | 1
| S | Small | 2
| M | Medium | 3
| L | Large | 4
| VL | Very Large | 5
| UL | Ultra Large | 6

## Hydro
Schedule_Overrun | Cost_Overrun
402% | 416%
32% | 11%
33% | 63%
6% | 2%
21% | -7%
26% | -18%
0% | 50%
68% | 87%
58% | 101%
-29% | -3%
116% | 21%
21% | -2%
31% | -3%
10% | 12%
27% | 15%
60% | -20%
100% | 23%
49% | 200%
-22% | -51%
130% | 26%
56% | -17%
3% | 143%
-2% | -6%
325% | 513%
38% | 353%
32% | 88%
98% | -16%
147% | 402%

## Nuclear
Schedule_Overrun | Cost_Overrun
-0.15 | 0.81623
-0.083333 | 0.32827
0.78333 | 1.0097
1.25 | 2.0199
0.16667 | 0.044919
0.91667 | 1.5123
0.18333 | 2.1207
0.18333 | 0.92665
0 | 0.034501
0.35417 | 0.022218
0.35417 | 0.022218
0.35417 | 0.066663
0.35417 | 0.088881
0.18 | 0.96735
0 | 2.2701
0 | 0.10632
1.0167 | 1.7095
1.0333 | 4.3533
0.61667 | 1.4803
1.4 | 4.0992
0 | 0.29511
0.016667 | 0.74884

## Solar
Schedule_Overrun | Cost_Overrun
3% | -9%
-8% | 0%
0% | 31%
-3% | -2%
-10% | -19%
0% | -16%
-2% | 13%
0% | 5%
0% | 12%
-4% | 0%
0% | 13%
-4% | 8%
25% | -3%

## Thermal
Schedule_Overrun | Cost_Overrun
15% | 10%
-3% | -14%
0% | 120%
50% | 0%
0% | 4%
17% | 75%
46% | 75%
23% | 57%
17% | 31%
10% | 9%
9% | 9%
0% | 11%
0% | 9%
13% | 69%
0% | -17%
67% | -9%
-7% | -31%
-11% | -42%
0% | 15%
4% | 1%
0% | -50%
0% | 13%
0% | 14%
0% | 3%

## Wind
Schedule_Overrun | Cost_Overrun
0.1 | -0.0083871
0 | 0.35713
0.25 | 0.10088
0 | -0.0056899
-0.083333 | 0
0 | 0
0.6 | 0.21359
-0.19048 | 0
0.15 | 0.17699
-0.125 | 0.017319
0.5 | 0.064516
-0.052632 | 0
-0.1 | 0
0 | 0.0041494
0.2 | -0.021033
0.33333 | 0.065097
-0.15 | -0.0082372
0.28571 | -0.033708

## Transmission
Schedule_Overrun | Cost_Overrun
0% | 15%
0% | 21%
0% | 14%
0% | 18%
0% | 33%
0% | 33%
0% | 11%
0% | 0%
0% | -33%
0% | 13%
0% | -4%
0% | 71%
0% | 4%
0% | -11%
0% | -21%