## Energy
Date | Energy Source | Name | Location | Capacity.MW | Initial.Budget.millions.of.USD.2012 | Actual.Cost.millions.of.USD.2012. | Cost.overrun.millions.USD | Cost.overrun.Percent | Proposed.time.months | Actual.time.months | Time.overrun.months | Time.overrun.Percentage | Cost.per.kW
2011 | Hydro | Bakun Hydroelectric Project | Malaysia | 2400 | 940.26 | 4856 | 3915.7 | 416.5 | 60 | 301 | 241 | 401.7 | 2023.3
1978 | Hydro | Brabovica and Salakovac (Middle Neretva Phase I) | Yugoslavia | 321 | 658.99 | 731.38 | 72.4 | 11 | 56 | 74 | 18 | 32.1 | 2278.4
1971 | Hydro | Churchill Falls | Canada | 5428 | 2400 | 3911 | 1511 | 63 | 60 | 80 | 20 | 33.3 | 720.5
1956 | Hydro | Folsom Dam | United States | 162 | 666.55 | 679.05 | 12.5 | 1.9 | 90 | 95 | 5 | 5.6 | 4191.7
1980 | Hydro | Fourth Guadalupe | Colombia | 213 | 436.28 | 404.55 | -31.7 | -7.3 | 57 | 69 | 12 | 21.1 | 1899.3
1983 | Hydro | Fourth Power Mtera | Tanzania | 80 | 327.24 | 266.81 | -60.4 | -18.5 | 72 | 91 | 19 | 26.4 | 3335.1
1942 | Hydro | Grand Coulee Dam I | United States | 2280 | 2989.36 | 4484.04 | 1494.7 | 50 | 78 | 78 | 0 | 0 | 1966.7
1973 | Hydro | Grand Coulee Dam II | United States | 4215 | 2645.5 | 4951.83 | 2306.3 | 87.2 | 50 | 84 | 34 | 68 | 1174.8
1986 | Hydro | Guri (Raul Leoni) | Venezuela | 10300 | 5100 | 10230 | 5130 | 100.6 | 120 | 190 | 70 | 58.3 | 993.2
1936 | Hydro | Hoover Dam | United States | 2080 | 2877.18 | 2792.56 | -84.6 | -2.9 | 84 | 60 | -24 | -28.6 | 1342.6
1991 | Hydro | Itaipu Dam | Brazil/Paraguay | 12600 | 24738.42 | 29885.34 | 5146.9 | 20.8 | 100 | 216 | 116 | 116 | 2371.9
1980 | Hydro | Karakaya | Turkey | 1800 | 2115.9 | 2070.78 | -45.1 | -2.1 | 122 | 148 | 26 | 21.3 | 1150.4
1959 | Hydro | Kariba Stage 1 | Zambia/Zimbabwe | 319 | 1003.41 | 978.32 | -25.1 | -2.5 | 55 | 72 | 17 | 30.9 | 3066.8
1993 | Hydro | King River Hydro | Australia | 143 | 583.43 | 653.73 | 70.3 | 12 | 120 | 132 | 12 | 10 | 4571.5
1978 | Hydro | Mostar (Middle Neretva Phase II) | Yugoslavia | 75 | 295.25 | 339.96 | 44.7 | 15.1 | 44 | 56 | 12 | 27.3 | 4532.8
1980 | Hydro | Ninth Power | Malaysia | 192 | 463.31 | 369.42 | -93.9 | -20.3 | 60 | 96 | 36 | 60 | 1924.1
1977 | Hydro | Nispero Power | Honduras | 22 | 124.12 | 152.46 | 28.3 | 22.8 | 18 | 36 | 18 | 100 | 6930
1976 | Hydro | Nurek | Tajikistan | 2700 | 7960 | 23870 | 15910 | 199.9 | 150 | 223 | 73 | 48.7 | 8840.7
1991 | Hydro | Pehuenche | Chile | 500 | 1327.08 | 655.73 | -671.4 | -50.6 | 78 | 61 | -17 | -21.8 | 1311.5
2003 | Hydro | Pergau Dam | Malaysia | 600 | 682.11 | 856.94 | 174.8 | 25.6 | 60 | 138 | 78 | 130 | 1428.2
1981 | Hydro | Playas | Colombia | 200 | 692.35 | 577.5 | -114.9 | -16.6 | 54 | 84 | 30 | 55.6 | 2887.5
1981 | Hydro | Robert-Bourassa | Canada | 5616 | 3500 | 8510 | 5010 | 143.1 | 70 | 72 | 2 | 2.9 | 1515.3
1984 | Hydro | Ruzizi II | Burundi. Rwanda. Zaire | 26.6 | 154.81 | 145.69 | -9.1 | -5.9 | 56 | 55 | -1 | -1.8 | 5477.1
2006 | Hydro | Sardar Sarovar Dam | India | 1450 | 1321 | 8094 | 6773 | 512.7 | 65 | 276 | 211 | 324.6 | 5582.1
1978 | Hydro | SayanoÐShushenskaya | Russia | 6400 | 4900 | 22199 | 17299 | 353 | 150 | 207 | 57 | 38 | 3468.6
1970 | Hydro | Second Power (Bayano) | Panama | 190 | 217.78 | 409.78 | 192 | 88.2 | 56.25 | 74.25 | 18 | 32 | 2156.7
1973 | Hydro | Sixth Power Project | Honduras | 40 | 130.44 | 109.83 | -20.6 | -15.8 | 43 | 85 | 42 | 97.7 | 2745.8
2012 | Hydro | Three Gorges Dam | China | 22500 | 11850 | 59480 | 47630 | 401.9 | 72 | 178 | 106 | 147.2 | 2643.6
1972 | Nuclear | Surry 1 | United States | 810 | 724.87 | 1316.53 | 591.7 | 81.6 | 60 | 51 | -9 | -15 | 1625.3
1973 | Nuclear | Surry 2 | United States | 815 | 569.17 | 756.01 | 186.8 | 32.8 | 60 | 55 | -5 | -8.3 | 927.6
1983 | Nuclear | Susquehanna 1 | United States | 1105 | 2284.64 | 4591.42 | 2306.8 | 101 | 60 | 107 | 47 | 78.3 | 4155.1
1985 | Nuclear | Susquehanna 2 | United States | 1140 | 1302.69 | 3934.02 | 2631.3 | 202 | 60 | 135 | 75 | 125 | 3450.9
1969 | Nuclear | Tarapur I and II | India | 320 | 89.05 | 93.05 | 4 | 4.5 | 60 | 70 | 10 | 16.7 | 290.8
2005 | Nuclear | Tarapur III and IV | India | 1080 | 517.92 | 1301.19 | 783.3 | 151.2 | 60 | 115 | 55 | 91.7 | 1204.8
1974 | Nuclear | Three Mile Island 1 | United States | 786 | 558.79 | 1743.84 | 1185.1 | 212.1 | 60 | 71 | 11 | 18.3 | 2218.6
1984 | Nuclear | Three Mile Island 2 | United States | 790 | 1155.64 | 2226.51 | 1070.9 | 92.7 | 60 | 71 | 11 | 18.3 | 2818.4
1978 | Nuclear | Tokai-Daini | Japan | 1100 | 2521.65 | 2608.65 | 87 | 3.5 | 60 | 60 | 0 | 0 | 2371.5
1980 | Nuclear | Tricastin 1 | France | 955 | 943.4 | 964.36 | 21 | 2.2 | 48 | 65 | 17 | 35.4 | 1009.8
1980 | Nuclear | Tricastin 2 | France | 955 | 943.4 | 964.36 | 21 | 2.2 | 48 | 65 | 17 | 35.4 | 1009.8
1980 | Nuclear | Tricastin 3 | France | 955 | 943.4 | 1006.29 | 62.9 | 6.7 | 48 | 65 | 17 | 35.4 | 1053.7
1981 | Nuclear | Tricastin 4 | France | 955 | 943.4 | 1027.25 | 83.9 | 8.9 | 48 | 65 | 17 | 35.4 | 1075.7
1975 | Nuclear | Trojan | United States | 1130 | 1006.86 | 1980.85 | 974 | 96.7 | 50 | 59 | 9 | 18 | 1753
1970 | Nuclear | Tsuruga-1 | Japan | 357 | 126.08 | 412.29 | 286.2 | 227 | 48 | 48 | 0 | 0 | 1154.9
1987 | Nuclear | Tsuruga-2 | Japan | 1160 | 4791.13 | 5300.51 | 509.4 | 10.6 | 60 | 60 | 0 | 0 | 4569.4
1984 | Nuclear | Virgil Summer 1 | United States | 966 | 1089.9 | 2953.11 | 1863.2 | 171 | 60 | 121 | 61 | 101.7 | 3057
1985 | Nuclear | Waterford 3 | United States | 1089 | 1067.41 | 5714.19 | 4646.8 | 435.3 | 60 | 122 | 62 | 103.3 | 5247.2
1985 | Nuclear | Wolf Creek 1 | United States | 1165 | 1977.39 | 4904.55 | 2927.2 | 148 | 60 | 97 | 37 | 61.7 | 4209.9
1984 | Nuclear | WPPSS 2 | United States | 1150 | 1359.78 | 6933.84 | 5574.1 | 409.9 | 60 | 144 | 84 | 140 | 6029.4
1973 | Nuclear | Zion 1 | United States | 1040 | 1025.89 | 1328.64 | 302.8 | 29.5 | 60 | 60 | 0 | 0 | 1277.5
1974 | Nuclear | Zion 2 | United States | 1040 | 743.9 | 1300.96 | 557.1 | 74.9 | 60 | 61 | 1 | 1.7 | 1250.9
2010 | Solar | ISCC Ain Beni Mathar | Morocco | 20 | 596.54 | 543.6 | -52.9 | -8.9 | 40 | 41 | 1 | 2.5 | 27180
2011 | Solar | ISCC Hassi R'mel | Algeria | 25 | 447.82 | 447.82 | 0 | 0 | 60 | 55 | -5 | -8.3 | 17912.8
2011 | Solar | ISCC Kuraymat | Egypt | 20 | 334.45 | 436.78 | 102.3 | 30.6 | 30 | 30 | 0 | 0 | 21839
2008 | Solar | La Risca (Alvarado 1) | Spain | 50 | 357.17 | 351.21 | -6 | -1.7 | 25 | 24.25 | -0.75 | -3 | 7024.2
2011 | Solar | Manchasol-1 (MS-1) | Spain | 50 | 544.18 | 438.86 | -105.3 | -19.4 | 30 | 27 | -3 | -10 | 8777.2
2010 | Solar | Martin Next Generation Solar Energy Center (MNGSEC) | United States | 75 | 500.09 | 420.24 | -79.9 | -16 | 24 | 24 | 0 | 0 | 5603.2
2011 | Solar | Palma del Rio I | Spain | 50 | 334.18 | 378.73 | 44.6 | 13.3 | 26 | 25.5 | -0.5 | -1.9 | 7574.6
2010 | Solar | Palma del Rio II | Spain | 50 | 334.72 | 350.06 | 15.3 | 4.6 | 26 | 26 | 0 | 0 | 7001.2
2010 | Solar | Rovigo Photovoltaic Power Plant | Italy | 72 | 359.31 | 401.33 | 42 | 11.7 | 8 | 8 | 0 | 0 | 5574
2013 | Solar | Shams 1 | United Arab Emirates | 100 | 796.8 | 796.8 | 0 | 0 | 34 | 32.5 | -1.5 | -4.4 | 7968
2010 | Solar | Solnova 3 | Spain | 50 | 265.34 | 298.51 | 33.2 | 12.5 | 36 | 36 | 0 | 0 | 5970.2
2012 | Solar | Soluz Guzman | Spain | 50 | 334.26 | 359.97 | 25.7 | 7.7 | 24 | 23 | -1 | -4.2 | 7199.4
2011 | Solar | Termesol 50 (Valle 1 and 2) | Spain | 100 | 848.5 | 822.78 | -25.7 | -3 | 20 | 25 | 5 | 25 | 8227.8
2003 | Thermal | Belungang Phase II | China | 1800 | 1122 | 1235 | 113 | 10.1 | 82 | 94 | 12 | 14.6 | 686.1
2013 | Thermal | Cape Canaveral Next Generation Clean Energy Center | United States | 1200 | 990 | 851 | -139 | -14 | 30 | 29 | -1 | -3.3 | 709.2
2013 | Thermal | Cliffside | United States | 800 | 990 | 2178 | 1188 | 120 | 72 | 72 | 0 | 0 | 2722.5
2011 | Thermal | Comanche 3 | United States | 766 | 1377 | 1377 | 0 | 0 | 48 | 72 | 24 | 50 | 1797.7
2011 | Thermal | Dry Fork | United States | 385 | 1326 | 1377 | 51 | 3.8 | 60 | 60 | 0 | 0 | 3576.6
2013 | Thermal | Edwardsport | United States | 618 | 1980 | 3465 | 1485 | 75 | 72 | 84 | 12 | 16.7 | 5606.8
2013 | Thermal | Argenne | United States | 960 | 2000 | 3500 | 1500 | 75 | 48 | 70 | 22 | 45.8 | 3645.8
2012 | Thermal | El Tebbin | Egypt | 700 | 450 | 705 | 255 | 56.7 | 52 | 64 | 12 | 23.1 | 1007.1
2012 | Thermal | Hempstead | United States | 600 | 1300 | 1700 | 400 | 30.8 | 60 | 70 | 10 | 16.7 | 2833.3
2010 | Thermal | Iatan 2 Power Plant | United States | 850 | 1150 | 1250 | 100 | 8.7 | 42 | 46 | 4 | 9.5 | 1470.6
1999 | Thermal | Jamaia Energy Sector | Jamaica | 90 | 224 | 245 | 21 | 9.4 | 22 | 24 | 2 | 9.1 | 2722.2
2011 | Thermal | Longview | United States | 695 | 1836 | 2040 | 204 | 11.1 | 60 | 60 | 0 | 0 | 2935.3
2011 | Thermal | Oak Creek | United States | 1230 | 2234 | 2428 | 194 | 8.7 | 60 | 60 | 0 | 0 | 1974
2012 | Thermal | Prairie State | United States | 1600 | 2900 | 4900 | 2000 | 69 | 60 | 68 | 8 | 13.3 | 3062.5
1999 | Thermal | Quick Start GT Hungary | Hungary | 200 | 131 | 109 | -22 | -16.8 | 16 | 16 | 0 | 0 | 545
2005 | Thermal | Ry-sana'a Emergency Power | Yemen | 30 | 70 | 64 | -6 | -8.6 | 36 | 60 | 24 | 66.7 | 2133.3
1982 | Thermal | Second Korba | India | 1500 | 2235.76 | 1532.68 | -703.1 | -31.4 | 84 | 78 | -6 | -7.1 | 1021.8
1982 | Thermal | Second Ramagundam | India | 1500 | 3009.42 | 1736.71 | -1272.7 | -42.3 | 84 | 75 | -9 | -10.7 | 1157.8
2008 | Thermal | Snowflake - Renergy | United States | 24 | 55 | 63 | 8 | 14.5 | 12 | 12 | 0 | 0 | 2625
2012 | Thermal | Vindhyacahl Expansion | India | 1200 | 726 | 735 | 9 | 1.2 | 46 | 48 | 2 | 4.3 | 612.5
1999 | Thermal | Vindhyacahl- II Power Station | India | 1000 | 558 | 279 | -279 | -50 | 48 | 48 | 0 | 0 | 279
2012 | Thermal | Virginia City Hybrid Energy Center | United States | 585 | 1600 | 1800 | 200 | 12.5 | 60 | 60 | 0 | 0 | 3076.9
1998 | Thermal | Yanshi Thermal Power Project | China | 600 | 497 | 567 | 70 | 14.1 | 60 | 60 | 0 | 0 | 945
2000 | Thermal | Zouxian Thermal Power | China | 600 | 1049 | 1077 | 28 | 2.7 | 48 | 48 | 0 | 0 | 1795
2013 | Wind | BRW | Canada | 6 | 15.5 | 15.37 | -0.1 | -0.8 | 10 | 11 | 1 | 10 | 2561.7
2007 | Wind | Cedar Creek II | United States | 250 | 357.35 | 484.97 | 127.6 | 35.7 | 9 | 9 | 0 | 0 | 1939.9
2002 | Wind | Ferndale I | Canada | 2 | 4.56 | 5.02 | 0.5 | 10.1 | 4 | 5 | 1 | 25 | 2510
2006 | Wind | Ferndale II | Canada | 3 | 7.03 | 6.99 | 0 | -0.6 | 5 | 5 | 0 | 0 | 2330
2010 | Wind | Fowler Ridge II | United States | 200 | 81.11 | 81.11 | 0 | 0 | 12 | 11 | -1 | -8.3 | 405.6
2011 | Wind | Hallett 5 (The Bluff) | Australia | 53 | 122.19 | 122.19 | 0 | 0 | 16 | 16 | 0 | 0 | 2305.5
2002 | Wind | Horns Rev I | Denmark | 160 | 309 | 375 | 66 | 21.4 | 10 | 16 | 6 | 60 | 2343.8
2009 | Wind | Horns Rev II | Denmark | 209 | 635 | 635 | 0 | 0 | 21 | 17 | -4 | -19 | 3038.3
2008 | Wind | Lillgrund | Sweden | 110 | 226 | 266 | 40 | 17.7 | 20 | 23 | 3 | 15 | 2418.2
2012 | Wind | London Array | United Kingdom | 630 | 2921.6 | 2972.2 | 50.6 | 1.7 | 24 | 21 | -3 | -12.5 | 4717.8
2000 | Wind | Middelgrunden | Denmark | 40 | 62 | 66 | 4 | 6.5 | 4 | 6 | 2 | 50 | 1650
2003 | Wind | Nysted | Denmark | 166 | 363 | 363 | 0 | 0 | 19 | 18 | -1 | -5.3 | 2186.7
2012 | Wind | Oaklands Hill Wind Farm | Australia | 63 | 207.1 | 207.1 | 0 | 0 | 20 | 18 | -2 | -10 | 3287.3
2014 | Wind | Oxley | Canada | 6 | 16.87 | 16.94 | 0.1 | 0.4 | 7 | 7 | 0 | 0 | 2823.3
2010 | Wind | Proof Line | Canada | 7 | 15.69 | 15.36 | -0.3 | -2.1 | 5 | 6 | 1 | 20 | 2194.3
2008 | Wind | Ravenswood | Canada | 10 | 21.66 | 23.07 | 1.4 | 6.5 | 6 | 8 | 2 | 33.3 | 2307
2010 | Wind | R¿dsand II | Denmark | 207 | 607 | 602 | -5 | -0.8 | 20 | 17 | -3 | -15 | 2908.2
2003 | Wind | Sams¿ | Denmark | 23 | 44.5 | 43 | -1.5 | -3.4 | 7 | 9 | 2 | 28.6 | 1869.6
2013 | Transmission | Riley to Edith Clarke | United States | 345 | 79 | 91 | 12 | 15.19 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Tesla to Riley | United States | 345 | 111 | 134 | 23 | 20.72 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Tesla to Edith Clarke | United States | 345 | 85 | 97 | 12 | 14.12 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Edith Clarke to Clear Crossing | United States | 345 | 132 | 156 | 24 | 18.18 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Clear Crossing to Dermott | United States | 345 | 141 | 187 | 46 | 32.62 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Clear Crossing to West Shackelford | United States | 345 | 57 | 76 | 19 | 33.33 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Edith Clarke to Cottonwood | United States | 345 | 156 | 173 | 17 | 10.9 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Gray to Tesla | United States | 345 | 168 | 168 | 0 | 0 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Twin Buttes to Big Hill | United States | 345 | 75 | 50 | -25 | -33.33 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Willow Creek to Hicks | United States | 345 | 87 | 98 | 11 | 12.64 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Brown-Newton | United States | 345 | 162 | 155 | -7 | -4.32 | 30 | 30 | 0 | 0 | NA
2011 | Transmission | Alamathy-Sriperumbudur | India | 400 | 14 | 24 | 10 | 71.43 | 30 | 30 | 0 | 0 | NA
2013 | Transmission | Riley to West Krum | United States | 345 | 251 | 262 | 11 | 4.38 | 28 | 28 | 0 | 0 | NA
2013 | Transmission | Nazareth to Silverton | United States | 345 | 74 | 66 | -8 | -10.81 | 28 | 28 | 0 | 0 | NA
2013 | Transmission | Scurry County South to West Shackelford | United States | 345 | 192 | 151 | -41 | -21.35 | 27 | 27 | 0 | 0 | NA

## Rail
| Project ID | DoD, date of decision to build, yr:mo | Est durat yrs | Actual durat, yrs | Actual/estimated duration | Act/ est cost, local cur, constant prices
1 | Bao-Lan Line, 2002-2003 | 2002:1 | 1.9 | 1.4 | 0.74 | 1.15 |  |  | 0.95 | 3 | 1 | 0.12 | 12% | 95% | 88%
1 | Salt Lake City Medical Center LRT extension, tilføj Utah Transit Authority 2006, ridership, 1997-2003, OVERLAP | 1997 | 7.5 | 6.3 | 0.84 | 1.28 |  |  | 1.05 | 9 | 2 | 0.36 | 48% | 105% | 52%
1 | Salt Lake City University & Medical Center LRT Extensions, OVERLAP, 1997-2003 | 1997 | 7.5 | 6.3 | 0.84 | 1.02 |  |  | 1.15 | 7 | 3 | 0.28 | 76% | 115% | 24%
1 | Denver Southeast LRT Corridor, 1997-2006 | 1997 | 11 | 9.4 | 0.85 | 1.45 |  |  | 1.25 | 2 | 4 | 0.08 | 84% | 125% | 16%
1 | Dallas North Central LRT Extension, 1996-2002 | 1996 | 7.5 | 6.5 | 0.87 | 1.31 |  |  | 1.35 | 1 | 5 | 0.04 | 88% | 135% | 12%
1 | Baltimore Central LRT Double Tracking, 2000-2006 | 2000 | 6.5 | 5.67 | 0.87 | 1.4 |  |  | 1.45 | 2 | 6 | 0.08 | 96% | 145% | 4%
1 | Chicago Metra UP West, 1998-2006 | 1998:8 | 8.3 | 7.4 | 0.89 | 1.07 |  |  | 1.55 | 0 | 7 | 0 | 96% | 155% | 4%
1 | Chicago Metra North Central, 1998-2006 | 1998:8 | 8.3 | 7.4 | 0.89 | 1.06 |  |  | 1.65 | 1 | 8 | 0.04 | 100% | 165% | 0%
1 | Chicago Metra Southwest Corridor, 1998-2006 | 1998:8 | 8.3 | 7.4 | 0.89 | 1.04 |  |  |  | 25 | 9 | 1
1 | Xian-Hefei Railways, 2000-2004 | 2000:8 | 4.8 | 4.3 | 0.9 | 0.92 |  |  |  |  | 10
1 | Portland Interstate MAX LRT Extension, 1998-2004 | 1998 | 6.3 | 5.9 | 0.94 | 1.22 |  |  |  |  | 1
1 | Shenmu-Yanan Railway, 1997-2003 | 1997:9 | 5.4 | 5.3 | 0.98 | 1.02 |  |  |  |  | 2
1 | Washington Largo Metrorail Extension, 1996-2004 | 1996 | 8.5 | 8.5 | 1 | 1.14 |  |  |  |  | 3
1 | Memphis Medical Center LRT Extension, 1997-2004 | 1997 | 6.8 | 6.8 | 1 | 1.61 |  |  |  |  | 4
1 | Santa Clara Vasona Line, 1999-2005; 110804 krause em bf | 1999 | 6 | 6 | 1 | 1.18 |  |  |  |  | 5
1 | Santa Clara Capitol Line, 1999-2004; 110804 krause em bf | 1999 | 5 | 5 | 1 | 1.1 |  |  |  |  | 6
1 | Chicago Douglas Branch Reconstruction, 2000-2005 | 2000 | 4.6 | 4.6 | 1 | 0.92 |  |  |  |  | 7
1 | Sacramento South LRT Phase 1, 1996-2003 | 1996 | 7.3 | 7.5 | 1.03 | 1.08 |  |  |  |  | 8
1 | Zhe-Gan Line Imporvements, 2004-2007 | 2004:6 | 2.6 | 2.8 | 1.08 | 1.01 |  |  |  |  | 9
1 | Channel Tunnel Rail Link, High Speed 1 | 1996:2 | 10.5 | 11.4 | 1.09 | 1.18 |  |  |  |  | 10
1 | Newark Elizabeth Rail Link MOS-1, 1997-2006 | 1997 | 8 | 9.1 | 1.14 | 1.15 |  |  |  |  | 1
1 | Ganzhou Longyan Line, 2001-2007 | 2001:9 | 5.3 | 6.3 | 1.19 | 0.93 |  |  |  |  | 2
1 | Liupanshui-Shuicheng Guizhou Shuibai Line, 1998-2004 | 1998:8 | 4.8 | 6.3 | 1.31 | 1.11 |  |  |  |  | 3
1 | Miami South Florida Tri-Rail Double Tracking Segment 5, 1998-2007 | 1998 | 6.8 | 9 | 1.32 | 1.05 |  |  |  |  | 4
1 | Daxian-Wanxian Railway, 1996-2002 | 1996:6 | 4.4 | 6.5 | 1.48 | 1.18 |  |  |  |  | 5
6
7
| 0.04 | 1 | 0.75 | 0.7-0.8 | 0.04 | 75% | 4% | 96% |  |  | 8
| 0.32 | 8 | 0.85 | 0.8-0.9 | 0.36 | 85% | 36% | 64% |  |  | 9
| 0.32 | 8 | 0.95 | 0.9-1 | 0.68 | 95% | 68% | 32% |  |  | 10
| 0.12 | 3 | 1.05 | 1.0-1.1 | 0.8 | 105% | 80% | 20%
| 0.08 | 2 | 1.15 | 1.1-1.2 | 0.88 | 115% | 88% | 12%
| 0 | 0 | 1.25 | 1.2-1.3 | 0.88 | 125% | 88% | 12%
| 0.08 | 2 | 1.35 | 1.3-1.4 | 0.96 | 135% | 96% | 4%
| 0.04 | 1 | 1.45 | 1.4-1.5 | 1 | 145% | 100% | 0%
| 1 | 25
4

## Roads
Region | Length km, size, at opening | DoD, date of decision to build, yr:mo | Actual duration, yrs | Actual/estimated duration | Act/ est cost, local cur, constant prices
Asia | 0.40037 | 1990-09-02 |  | 4.8628 | 1.287
N Eu | 2 | 1998 | 4 | 4 | 0.92718
E Eu | 0.8 | 1998:7 | 3.9 | 3.9 | 0.92
Asia | 2.5004 | 1998-08-02 |  | 3.5504 | 1.6849
Asia | 1.3001 | 1993-01-02 |  | 3.2283 | 2.2043
Africa | 74 | 1996:05 | 7.1 | 3.15 | 4.33
Africa | 150 | 1996:05 | 7.1 | 3.15 | 1.55
Africa | 80 | 1996:05 | 7.1 | 3.15 | 1.29
Asia |  | 1990-10-02 |  | 3.1002
N Eu | 4.5 | 1992 | 3 | 3 | 1.2557
E Eu | 3.7 | 2000:1 | 3.9 | 3 | 1.01
E Eu | 2.4 | 2000:1 | 5.4 | 3 | 0.59
E Eu | 0.9 | 2000:5 | 2.8 | 2.8 | 1.03
E Eu | 8.2 | 1996:4 | 9.33 | 2.54 | 1.28
N Eu | 1.2 | 1997 | 5 | 2.5 | 1.1676
N Eu | 1 | 1995 | 7 | 2.3333 | 0.87529
E Eu | 1.3 | 1998:10 | 2.1 | 2.33 | 0.95
E Eu | 3.3 | 1998:11 | 3.3 | 2.2 | 1.24
Asia |  | 1994-01-02 |  | 2.168
Asia |  | 1999-03-02 |  | 2.1465 | 0.70911
Southeast Asia | 52.6 | 2000:02 | 7.0833 | 2.13 | 3.65
Southeast Asia | 46.1 | 2000:02 | 7.0833 | 2.13 | 1.61
E Eu | 20.3 | 1996:9 | 6.8 | 2.13 | 1.55
Southeast Asia | 48.3 | 2000:02 | 7.0833 | 2.13 | 1.32
Southeast Asia | 59.1 | 2000:02 | 7.0833 | 2.13 | 1.18
Southeast Asia | 84.8 | 2000:02 | 7.0833 | 2.13 | 0.73
Southeast Asia | 46.2 | 2000:02 | 7.0833 | 2.13 | 0.72
Asia | 6.1983 | 2006-03-02 |  | 2.1283 | 0.67255
Asia | 8.5028 | 1997-06-02 |  | 2.0217 | 0.78235
N Eu | 7.7 | 1994 | 10 | 2 | 1.35
N Eu | 35.7 | 1995 | 6 | 2 | 1.3156
N Eu | 1 | 1997 | 4 | 2 | 1.2126
N Eu | 12.2 | 1996 | 6 | 2 | 1.2064
E Eu | 6.8 | 2000:10 | 4.2 | 2 | 0.97
N Eu | 1 | 1989 | 8 | 2 | 0.848
N Eu | 1 | 1988 | 8 | 2 | 0.59724
S Eu | 88 | 2000 | 4 | 2
S Eu | 28.9 | 1999 | 5 | 2
Asia |  | 2003-03-02 |  | 1.9197 | 1.0238

## Fixed Links
Region | Project type | DoD, date of decision to build, yr:mo | Actual durat, yrs | Actual/estimated duration | Actual/ estimated cost, local cur, constant prices
N Eu | Tunnel | 1989 | 12 | 3 | 2.6404
N Eu | Bridge | 1985 | 13 | 1.86 | 0.88679
N Am | Tunnel | 1987 | 20.5 | 1.86 | 3.2844
| Tunnel |  |  | 1.8364 | 1.6244
N Eu | Tunnel | 1988 | 14 | 1.75 | 1.242
E Asia | Bridge | 1989:3 | 5.8 | 1.76 | 2.06
N Eu | Tunnel | 1987:5 | 10 | 1.67 | 2.2
N Eu | Bridge | 1997:2 | 5.6667 | 1.54 | 0.9
N Eu | Tunnel | 2001 | 9.5 | 1.36 | 0.91
N Eu | Tunnel | 1992:5 | 4.9167 | 1.16 | 0.94855
N Eu | Bridge | 1967:4 | 14.1 | 1.44 | 2.76
Asia | Tunnel | 1989:5 | 7.92 | 1.12 | 1.08
N Am | Bridge | 1938 | 1.83 | 1.38 | 0.99
Asia | Bridge | 2000:4 | 9.67 | 1.35 | 1.03
N Eu | Tunnel | 1992:9 | 15.3 | 1.1087 | 2
N Eu | Tunnel | 1999:5 | 4.3 | 1.06 | 1.32
N Eu | Tunnel | 1996:6 | 6.75 | 1.02 | 1
N Eu | Tunnel | 1984 | 10 | 1.01 | 1.2536
N Eu | Bridge | 1972 | 8.1 | 1.35 | 0.87
N Eu | Bridge | 1988 | 8 | 1.33 | 0.82863
W EU | Tunnel | 2009:04 | 6 | 1 | 2.517

## IT
Project ID | ProjectType | Year of Decision to Build | Year of Go-Live | Actual/estimated cost | Actual/estimated schedule | Actual/estimated benefits | Actual cost (2015 USD, millions)
2166 | Standard SW | NA | NA | 0.9889 | 1.5517 | -2.4857 | 15.7613
1349 | Other | NA | NA | 1.1026 |  | -0.3356 | 8676.6907
1460 | Bespoke SW | 2008 | 2009 | 1.0599 |  | 0 | 1.9773
2122 | IT Architecture | 2007 | 2008 | 0.9982 |  | 0 | 29.3679
2507 | Bespoke SW | 2007 | 2007 | 0.9407 |  | 0 | 24.7162
2707 | Bespoke SW | 2009 | 2010 | 0.8981 |  | 0 | 1.3356
2716 | Organisation | 2009 | 2010 | 0.8961 |  | 0 | 3.4945
2739 | Organisation | 2009 | 2010 | 0.889 |  | 0 | 0.93698
2891 | Infrastructure | 2008 | 2008 | 0.8339 |  | 0 | 11.7933
2963 | Standard SW | 2006 | 2008 | 0.8123 |  | 0 | 16.9978
3002 | Bespoke SW | 2008 | 2010 | 0.7935 |  | 0 | 5.0716
3279 | Bespoke SW | 2009 | 2010 | 0.6206 |  | 0 | 0.89405
3330 | Bespoke SW | 2009 | 2010 | 0.5689 |  | 0 | 0.67785
3419 | Bespoke SW | 2007 | 2008 | 0.4834 |  | 0 | 1.6345
3156 | Standard SW | 2005 | 2008 | 0.7142 | 1.037 | 0.0116 | 18.0095
3240 | Bespoke SW | 2007 | NA | 0.6445 |  | 0.08 | 0.1995
2149 | Organisation | 2006 | 2007 | 0.9925 |  | 0.3016 | 8.2413
4295 | Other | 2012 | 2012 | 1 | 0.79739 | 0.36 | 0.013096
2329 | Bespoke SW | 2008 | 2009 | 0.9581 |  | 0.6946 | 3.657
1552 | Standard Softwa | 2010 | 2010 | 1.0319 |  | 0.72 | NA
2306 | Integration | 2006 | 2007 | 0.9612 | 2.25 | 0.7294 | 7.187
2141 | Integration | 2006 | 2007 | 0.995 | 1.4 | 0.8 | 2.1419
1012 | Integration | 2005 | 2006 | 1.3161 | 1 | 0.8381 | 12.3818
1371 | Bespoke SW | 2007 | 2009 | 1.0914 | 2.1818 | 0.8571 | 3.4692
4286 | System deployment - Standard SW | 2012 | 2013 | 2 | 6.9836 | 1 | 0.033085
4301 | System deployment - Integration | 2010 | 2012 | 0.87692 | 6.9688 | 1 | 0.0098222
4287 | Other | 2012 | 2013 | 1.0746 | 4.1622 | 1 | 0.31776
855 | Bespoke SW | 2007 | 2009 | 1.4973 | 3.75 | 1 | 1.6943
4288 | Outsourcing and offshoring | 2011 | 2013 | 1.2556 | 2.6612 | 1 | 0.038944
4302 | System deployment - Integration | 2013 | 2013 | 1.3753 | 1.5143 | 1 | 0.3791
4299 | System deployment - Integration | 2012 | 2013 | 1.3277 | 1.5021 | 1 | 1.0598
4304 | Other | 2012 | 2013 | 0.99563 | 1.3026 | 1 | 0.039289
4298 | Other | 2012 | 2013 | 1.3813 | 1.1613 | 1 | 0.038083
1627 | Bespoke SW | 2007 | 2009 | 1.0057 | 1.1429 | 1 | 0.53537
2539 | Integration | 2007 | 2007 | 0.9356 | 1.1429 | 1 | 0.93792
1624 | Standard SW | 2007 | 2008 | 1.0064 | 1.0909 | 1 | 1.2827
4306 | Other | 2012 | 2013 | 1.1145 | 1.0048 | 1 | 0.12579
718 | Standard SW | 2008 | 2009 | 1.6861 | 1 | 1 | 190.5777
1021 | Infrastructure | 2005 | 2006 | 1.3103 | 1 | 1 | 2.7418
1330 | Bespoke SW | 2007 | 2008 | 1.1101 | 1 | 1 | 0.41124
2072 | Bespoke SW | NA | NA | 1 | 1 | 1 | 9.7602
2264 | Integration | 2007 | 2008 | 0.9685 | 1 | 1 | 0.90245
4292 | Other | 2013 | 2013 | 0.88926 | 1 | 1 | 0.028755
2932 | Integration | 2007 | 2008 | 0.8257 | 1 | 1 | 23.7589
3113 | Integration | 2007 | 2008 | 0.7358 | 1 | 1 | 2.3271
4291 | Other | 2012 | 2012 | 0.52174 | 1 | 1 | 0.0062035
4290 | System deployment - Cust. Dev. | 2013 | 2013 | 0.91545 | 0.9759 | 1 | 0.071235
385 | IT Infrastructu | 2007 | 2010 | 2.8793 |  | 1 | 1.4219
471 | IT Infrastructu | 2009 | 2009 | 2.3104 |  | 1 | NA
509 | Standard Softwa | 2009 | 2009 | 2.165 |  | 1 | NA
611 | O&O | 2008 | 2009 | 1.9364 |  | 1 | 0.0030601
4293 | Other | 2012 | 2013 | 1.6745 |  | 1 | 0.19131
1115 | Bespoke SW | 2009 | 2009 | 1.2333 |  | 1 | 37.7976
1201 | Standard Softwa | 2007 | 2008 | 1.1772 |  | 1 | 2.0693
1379 | Standard Softwa | 2009 | 2010 | 1.0865 |  | 1 | NA
1422 | Standard Softwa | 2008 | 2010 | 1.0729 |  | 1 | 0.35858
1539 | Standard Softwa | 2009 | 2009 | 1.0367 |  | 1 | NA
4303 | System deployment - Integration | 2012 | 2012 | 1.0305 |  | 1 | 0.42546
1694 | Standard Softwa | NA | NA | 1 |  | 1 | NA
4307 | Other | 2011 | 2013 | 1 |  | 1 | 0.017232
2065 | IT Infrastructu | 2009 | 2009 | 1 |  | 1 | NA
2071 | IT Infrastructu | 2010 | 2010 | 1 |  | 1 | NA
2079 | IT Infrastructu | 2010 | 2010 | 1 |  | 1 | NA
2142 | Standard Softwa | 2009 | 2009 | 0.9944 |  | 1 | NA
2220 | Standard Softwa | 2009 | 2010 | 0.9768 |  | 1 | NA
2665 | Bespoke SW | 2008 | 2009 | 0.91 |  | 1 | 2.542
2753 | Bespoke SW | 2009 | 2009 | 0.8845 |  | 1 | 0.63639
3066 | Standard Softwa | 2010 | 2010 | 0.7502 |  | 1 | NA
3542 | Standard Softwa | 2009 | 2009 | 0.2422 |  | 1 | NA
3553 | Standard Softwa | NA | NA | 0.1795 |  | 1 | NA
3592 | Standard Softwa | 2009 | 2009 | 0.0377 |  | 1 | NA
936 | Integration | 2006 | 2007 | 1.4 | 1.5 | 1.2444 | 10.1614
798 | Standard SW | NA | NA | 1.55 | 2.1429 | 1.3333 | 7.0723
386 | Standard Softwa | 2008 | 2009 | 2.8556 |  | 1.7994 | 0.28634
2748 | Standard Softwa | 2008 | 2011 | 0.8864 |  | 2.4138 | 6.3047
1543 | Bespoke SW | 2006 | 2008 | 1.0354 | 2.7273 | 2.8889 | 1.6727
3107 | Bespoke SW | NA | NA | 0.74 | 4.79 |  | 7.3724
3552 | Other | 2009 | 2010 | 0.1799 | 4.6271 |  | 0.010866
4296 | System deployment - Standard SW | 2012 | 2013 | 1.7293 | 4.2976 |  | 0.39634
766 | NA | 2005 | 2008 | 1.5882 | 4.25 |  | 5.6524
3409 | Bespoke SW | 2007 | 2007 | 0.4919 | 4 |  | 0.23371
2170 | Infrastructure | 2010 | 2011 | 0.9878 | 3.7879 |  | 0.52162
1320 | Bespoke SW | 2010 | 2011 | 1.1143 | 3.4961 |  | 0.52937
1002 | Standard Softwa | 2009 | 2011 | 1.3325 | 3.4706 |  | 1951.1739

## Aerospace
Project name, dod-opening year | Launch date | Actual/estimated duration | Actual/ estimated cost
NASA - Calipso, 2006 | 2006 | 1.7517 | 2.4976
NASA - EO-1, 2000 | 2000 | 1.4916 | 2.1429
NASA - Cloudsat, 2006 | 2006 | 1.8384 | 1.7964
NASA - HETE-II, 2000 | 2000 | 1.3396 | 1.7144
NASA - SWAS, 1998 | 1998 | 1.5915 | 1.6673
NASA - Swift Gamma-Ray Burst Mission, 2004 | 2004 | 1.3315 | 1.6091
NASA - GALEX, 2003 | 2003 | 1.5048 | 1.5786
NASA - Messenger, 2004 | 2004 | 1.0985 | 1.5065
NASA - ICESAT, 2003 | 2003 | 1.2018 | 1.4583
NASA - RHESSI, 2002 | 2002 | 1.6159 | 1.4539
NASA - Gravity Probe B, 2004 | 2004 | 1.4967 | 1.4234
NASA - Spitzer Space Telescope (formerly SIRFT), 2003 | 2003 | 1.3125 | 1.3624
NASA - STEREO, 2006 | 2006 | 1.1554 | 1.3125
NASA - Deep Impact, 2005 | 2005 | 1.2356 | 1.2984
NASA - WIRE, 1999 | 1999 | 1.1647 | 1.2769
NASA - TIMED, 2001 | 2001 | 1.5373 | 1.2571
NASA - CONTOUR, 2002 | 2002 | 1.0014 | 1.2426
NASA - FAST, 1996 | 1996 | 1.1861 | 1.1883
NASA - Genesis, 2001 | 2001 | 1.189 | 1.185
NASA - MER, 2003 | 2003 | 1.0104 | 1.1609
NASA - Landsat-7, 1999 | 1999 | 1.0596 | 1.1601
NASA - MRO, 2005 | 2005 | 1 | 1.1412
NASA - TRACE, 1998 | 1998 | 1.0839 | 1.1316
NASA - DS-1, 1998 | 1998 | 1.1143 | 1.1262
NASA - GRACE, 2002 | 2002 | 1.1894 | 1.1149
NASA - SOURCE, 2003 | 2003 | 1.1444 | 1.0953
NASA - FUSE, 1999 | 1999 | 1.1776 | 1.0942
NASA - EOS-Aura, 2004 | 2004 | 1.1734 | 1.0806
NASA - IMAGE, 2000 | 2000 | 1.038 | 1.0672
NASA - MAP, 2001 | 2001 | 1.1437 | 1.0672
NASA - THEMIS, 2007 | 2007 | 1.03 | 1.0522
NASA - MCO/MPL, 1998 | 1998 | 1.0081 | 1.033
NASA - Lunar Prospector, 1998 | 1998 | 1.1071 | 1.0069

## Military Defense
Project name, dod-opening year | Sector | Decisi-on to build, yr:mo | Actual Completion:mo | Delay, months | Impl phase, years | Act/est duration | Est constr costs, mio, y est done | Actual contr costs, mio | Curren-cy, year | Act/ est cost
Typhoon | Air | 1991-01-02 | 2007-06-02 | 54.7667 | 16.4247 | 1.3775 | 15173 | 17543 | GBP, 2015 | 1.1562
Sonar2087 | Maritime | 2005-01-02 | 2010-05-02 | 0 | 5.3315 | 1 | 366 | 357 | GBP, 2015 | 0.97541
Lynx Wildcat | Air | 2010-01-02 | 2018-08-02 | 7.0667 | 8.5863 | 1.0726 | 1803 | 1663 | GBP, 2015 | 0.92235
Panther Command and Liaison Vehicle | Land | 2007-01-02 | 2011-09-02 | 10.1333 | 4.6685 | 1.2171 | 229 | 201 | GBP, 2015 | 0.87773
Support Vehicle | Land | 2005-01-02 | 2012-02-02 | 29.4333 | 7.0877 | 1.5182 | 1367 | 1272 | GBP, 2015 | 0.9305
Naval EHF/SHF Satellite Communication Terminals | Maritime | 2007-01-02 | 2016-05-02 | 31.4333 | 9.337 | 1.3826 | 269 | 200 | GBP, 2015 | 0.74349
Puma Life- Extension Programme | Air | 2011-01-02 | 2017-11-02 | 0 | 6.8384 | 1 | 339 | 326 | GBP, 2015 | 0.96165
A400M | Air | 2004-01-02 | 2019-03-02 | 73.9667 | 15.1726 | 1.6686 | 2238 | 2752 | GBP, 2015 | 1.2297
Tornado GR1 Mid Life Upgrade | Air | 1992-01-02 | 2002-09-02 | 63.9333 | 10.674 | 1.9697 | 613 | 943 | GBP, 2015 | 1.5383
Bowman | Land | 2005-01-02 | 2008-03-02 | 0 | 3.1644 | 1 | 1898 | 2009 | GBP, 2015 | 1.0585
Terrier | Land | 2006-01-02 | 2017-04-02 | 55.7667 | 11.2548 | 1.6871 | 295 | 322 | GBP, 2015 | 1.0915
Successor Identification Friend or Foe (SIFF) | Air | 2004-01-02 | 2008-03-02 | -1.0333 | 4.1671 | 0.98003 | 534 | 464 | GBP, 2015 | 0.86891
Next Generation Light Anti-Armour Weaoon | Land | 2006-01-02 | 2013-04-02 | 29.4 | 7.2521 | 1.4997 | 377 | 310 | GBP, 2015 | 0.82228
Precision Guided Bomb | Air | 2007-01-02 | 2011-09-02 | -3.0333 | 4.6685 | 0.9493 | 339 | 277 | GBP, 2015 | 0.81711
Modernised Target acquisition sight/pi lots night vision sensor | Air | 2010-01-02 | 2013-04-02 | 4.0333 | 3.2493 | 1.1136 | 245 | 228 | GBP, 2015 | 0.93061
Naval Afloat Reach and Sustainability | Maritime | 2016-01-02 | 2020-10-02 | 0 | 4.7534 | 1 | 596 | 562 | GBP, 2015 | 0.94295
Merlin HC Mk3 | Air | 1997-01-02 | 2004-06-02 | 6.1 | 7.4192 | 1.0725 | 794 | 755 | GBP, 2015 | 0.95088
Advanced Jet Trainer | Air | 2010-01-02 | 2013-11-02 | -3.0667 | 3.8356 | 0.93834 | 490 | 467 | GBP, 2015 | 0.95306
Typhoon Meteor integration | Air | 2017-01-02 | 2022-06-02 | 0 | 5.4164 | 1 | 130 | 124 | GBP, 2015 | 0.95385
Trojan and Titan | Land | 2005-01-02 | 2010-10-02 | 12.1667 | 5.7507 | 1.2105 | 348 | 336 | GBP, 2015 | 0.96552
Future Strategic Tanker Aircraft | Air | 2011-01-02 | 2018-05-02 | 0 | 7.3342 | 1 | 11779 | 11402 | GBP, 2015 | 0.96799
United Kingdom Military Flying Trainina Svstem | Air | 2012-01-02 | 2014-02-02 | 9.2 | 2.0877 | 1.5679 | 928 | 900 | GBP, 2015 | 0.96983
Merlin Capabi lity Sustainment Proqramme | Air | 2010-01-02 | 2018-06-02 | 4 | 8.4192 | 1.0406 | 805 | 791 | GBP, 2015 | 0.98261
Seawolf Mid-Life Update | Maritime | 2003-01-02 | 2010-06-02 | 21.2667 | 7.4192 | 1.3082 | 288 | 284 | GBP, 2015 | 0.98611
Watchkeeper | Land | 2009-01-02 | 2016-02-02 | 20.3333 | 7.0877 | 1.3085 | 847 | 839 | GBP, 2015 | 0.99055
Warrior Armoured Fighting Vehicle | Land | 2015-01-02 | 2023-07-02 | 8.0667 | 8.5014 | 1.0846 | 1319 | 1315 | GBP, 2015 | 0.99697
Chinook | Air | 2015-01-02 | 2018-11-02 | 6.1333 | 3.8356 | 1.1513 | 841 | 841 | GBP, 2015 | 1
Typhoon Storm Shadow Integration | Air | 2018-01-02 | 2022-08-02 | 0 | 4.5836 | 1 | 172 | 172 | GBP, 2015 | 1
Typhoon Attack Upgrade | Air | 2011-01-02 | 2017-12-02 | 18.2667 | 6.9205 | 1.277 | 403 | 403 | GBP, 2015 | 1
Note on E1: Bent Flyvbjerg User: Actual opening year minus estimated opening year
Note on F1: Bent Flyvbjerg User: Actual opening year minus year of decision to build

## Olympic Games
Games | Country | Events | Athletes | Cost, billion USD | Games | Country | Cost per event, mio. USD | Cost per athlete, mio. USD | Games | Country | Cost overrun %
Summer: |  |  |  |  | Summer: |  |  |  | Summer:
Rome 1960 | Italy | 150 | 5338 | n/a | Tokyo 1964 | Japan | 1.7 | 0.1 | Montreal 1976 | Canada | 720
Tokyo 1964 | Japan | 163 | 5152 | 0.282 | Munich 1972 | Germany | 5.2 | 0.1 | Barcelona 1992 | Spain | 266
Mexico City 1968 | Mexico | 172 | 5516 | n/a* | Montreal 1976 | Canada | 30.8 | 1 | Atlanta 1996 | United States | 151
Munich 1972 | Germany | 195 | 7234 | 1.009 | Moscow 1980* | Soviet Union | 31.2 | 1.2 | Sydney 2000 | Australia | 90
Montreal 1976 | Canada | 198 | 6048 | 6.093 | Los Angeles 1984 | United States | 3.3 | 0.1 | Athens 2004 | Greece | 49
Moscow 1980 | Soviet Union | 203 | 5179 | 6.331 | Barcelona 1992 | Spain | 37.7 | 1 | Beijing 2008 | China | 2
Los Angeles 1984 | United States | 221 | 6829 | 0.719 | Atlanta 1996 | United States | 15.3 | 0.4 | London 2012 | United Kingdom | 76
Seoul 1988 | South Korea | 237 | 8397 | n/a | Sydney 2000 | Australia | 16.8 | 0.5 | Rio 2016 | Brazil | 352
Barcelona 1992 | Spain | 257 | 9356 | 9.687 | Athens 2004 | Greece | 9.8 | 0.3 | Average, Summer | - | 213
Atlanta 1996 | United States | 271 | 10318 | 4.143 | Beijing 2008 | China | 22.5 | 0.6 | Median, Summer | - | 120
Sydney 2000 | Australia | 300 | 10651 | 5.026 | London 2012 | United Kingdom | 49.5 | 1.4
Athens 2004 | Greece | 301 | 10625 | 2.942 | Rio 2016† | Brazil | 44.7 | 1.3 | Winter:
Beijing 2008 | China | 302 | 10942 | 6.81 | Average, Summer | - | 22.4 | 0.7 | Grenoble 1968 | France | 181
London 2012 | United Kingdom | 302 | 10568 | 14.957 | Median, Summer | - | 19.7 | 0.6 | Lake Placid 1980 | United States | 324
Rio 2016 | Brazil | 306 | 10500 | 13.692 |  |  |  |  | Sarajevo 1984 | Yugoslavia | 118
Average, Summer | - | 239 | 8177 | 5.974 | Winter: |  |  |  | Calgary 1988 | Canada | 65
Median, Summer | - | 237 | 8397 | 5.56 | Innsbruck 1964 | Austria | 0.6 | 0.02 | Albertville 1992 | France | 137
[5 empty] | Grenoble 1968 | France | 25.4 | 0.8 | Lillehammer 1994 | Norway | 277
Winter: |  |  |  |  | Sapporo 1972 | Japan | 3.4 | 0.1 | Nagano 1998 | Japan | 56
Squaw Valley 1960 | United States | 27 | 665 | n/a | Innsbruck 1976 | Austria | 3.2 | 0.1 | Salt Lake City 2002 | United States | 24
Innsbruck 1964 | Austria | 34 | 1091 | 0.022 | Lake Placid 1980 | United States | 11.5 | 0.4 | Torino 2006 | Italy | 80
Grenoble 1968 | France | 35 | 1158 | 0.888 | Calgary 1988 | Canada | 24.1 | 0.8 | Vancouver 2010 | Canada | 13
Sapporo 1972 | Japan | 35 | 1006 | 0.117 | Albertville 1992 | France | 35 | 1.1 | Sochi 2014 | Russia | 289
Innsbruck 1976 | Austria | 37 | 1123 | 0.118 | Lillehammer 1994 | Norway | 36.5 | 1.3 | Average, Winter | - | 142
Lake Placid 1980 | United States | 38 | 1072 | 0.435 | Nagano 1998 | Japan | 32.7 | 1 | Median, Winter | - | 118
Sarajevo 1984 | Yugoslavia | 39 | 1272 | n/a* | Salt Lake City 2002 | United States | 32.3 | 1.1
Calgary 1988 | Canada | 46 | 1432 | 1.109 | Torino 2006 | Italy | 52 | 1.7
Albertville 1992 | France | 57 | 1801 | 1.997 | Vancouver 2010 | Canada | 29.5 | 1
Lillehammer 1994 | Norway | 61 | 1737 | 2.228 | Sochi 2014 | Russia | 223.4 | 7.9
Nagano 1998 | Japan | 68 | 2176 | 2.227 | Average, Winter | - | 39.2 | 1.3
Salt Lake City 2002 | United States | 78 | 2399 | 2.52 | Median, Winter | - | 29.5 | 1
Torino 2006 | Italy | 84 | 2508 | 4.366
Vancouver 2010 | Canada | 86 | 2566 | 2.54
Sochi 2014 | Russia | 98 | 2780 | 21.89
Average, Winter | - | 55 | 1652 | 3.112
Median, Winter | - | 46 | 1432 | 1.997